Ongoing Programme of Action

Monitoring Report

January 2009

Prepared by the Secretariat for the Taskforce for Action on Violence within Families

# Contents

Contents	1

Summary	3

Highlights	4

Hotspots	7

Variations	7

Alerts	7

Upcoming Objective Deadlines (next two months)	7

Changes to Monitoring Process	8

Monitoring Report	9

Three month summaries and milestone updates	11

Leadership	11

1.1  Facilitation of The Ongoing Programme of Action	11

1.2  Mäori Programme of Action	12

1.3  Pacific Programme of Action	13

1.4  Child Maltreatment	14

1.5  Family Violence Free Workplaces 	16

1.6  Iwi-Led Crime Prevention	18

1.7  Family Violence Clearinghouse	20

1.9  Mäori Research Agenda	21

1.10  Pacific Research Agenda	22

1.11  New Migrant and Refugee Research Agenda	23

1.12  Elder Abuse	24

1.13  Data on NGO Service Delivery	25

Changing Attitudes and Behaviour	27

2.1  Kia Puäwai	27

2.2  Improving Attachment	27

2.3  Conduct Disorder / Severe Anti-Social Behaviour	28

2.4  Curriculum Development	30

2.5  Violence in the Media	33

2.6  Campaign for Action on Family Violence	34

Ensuring Safety and Accountability	37

3.1  Family Violence Courts	37

3.3  Social Services Supporting Courts	38

Effective Support Services	42

4.1  Mäori Service Workforce Development	42

4.2  Pacific Service Workforce Development	43

First Programme of Action update	45

How this report works	51

Variation	52

# Summary

- The Taskforce for Action on Violence within Families’ (the Taskforce) first programme of action initially consisted of 76 actions, which were later consolidated to 53 actions. A progress summary on these actions is provided towards the end of this report.

- The Taskforce’s Ongoing Programme of Action (OPOA) originally consisted of 31 objectives which form the Taskforce’s work programme. Of the original 31 objectives, 22 remain. To meet each objective, actions and milestones have been identified. This report provides a progress report against the objectives, actions and milestones.

- For more information on this report, how it is organised and the current formal variation process, please refer to the “How this report works” section at the end of the document.

Objective status

| On track | 16 |
| --- | --- |
| Complete or ‘Business as Usual’ | 1 |
| Alerts | 1 |
| Variations | 4 pending |
| Total number of Objectives remaining | 22 |

## Highlights

This section provides an overview of key Taskforce initiatives for the reporting period of November 2008 to January 2009.

### Leadership

### Domestic Violence Act 1995 Review

Cabinet approved amendments to the Domestic Violence Act 1995 and related legislation in May 2008. The Domestic Violence Reform Bill was tabled in the House in October 2008. The remaining proposals in the Domestic Violence Reform Bill have been reinstated on the 2009 Legislative Programme and will be considered at a later stage.

The Government has decided, as a matter of immediate priority, to include many of the proposals that were in the Domestic Violence Reform Bill of a law enforcement nature in another Bill entitled the Domestic Violence (Enhancing Safety) Bill.

The Bill includes five amendments to the Domestic Violence Act 1995, the Sentencing Act 2002 and the Bail Act 2000. The amendments include: provision for ‘on-the-spot protection orders’ (Police orders); consideration of the safety of children when setting conditions of Police bail; consideration of whether a protection order on behalf of the victim should be made when sentencing for domestic violence offences in the Criminal Courts; repeal of the criteria for arrest without warrant for breach of a protection order, and amendment of the structure and penalties for the offence of breach of a protection order.

The Domestic Violence (Enhancing Safety) Bill has been introduced into the House and referred to the Justice and Electoral Select Committee, which has sought public submissions on the Bill by 27 February 2009.

### Changing Attitudes and Behaviour

### Campaign for Action on Family Violence

Book of Stories

The Minister for Social Development, Hon Paula Bennett, and Wellington Mayor, Kerry Prendergast launched It’s Time We Started Telling These Stories at Wellington Library on 9 December 2008. The book tells the stories of eight New Zealanders who grew up with family violence, and the impact it had on their lives. The launch saw significant media coverage – TV and print – which generated local and national interest.

Taiohi Morehu

As part of Taiohi Morehu, a campaign-initiated project, students from three Hutt Valley schools were chosen as leaders to work on developing strategies to address violence in their schools and communities. The young people presented a performing arts extravaganza in Upper Hutt on 5 December 2008 on the theme of family violence. Having learnt about family violence and traditional Mäori ways to address violence in the community, they developed their own powerful messages which were presented on the night.

Whänau Christmas

Television personalities Nicola Kawana, Jude Dobson and Kiel McNaughton joined thousands of families for a free day of entertainment in Auckland, celebrating Whänau Christmas. The very successful event at Roberta Reserve, Glendowie, on 20 December 2008, was supported by the It's not OK campaign and Family and Community Services.

### Ensuring Safety and Accountability

### Social Services Supporting Family Violence Courts

The Project Plan and Terms of Reference for this Objective have been finalised and agreed. The Ministry of Justice has begun work on developing the role of an independent victim advocate / support person to provide support and assistance to victims of domestic violence in the Family Violence Courts in conjunction with MSD.  A draft role description for the advocate role was sent out to NGOs and external government agencies in September 2008.  Agreement was reached in October 2008 for NGO representatives of the Taskforce, MoJ, MSD and Police to work on the development of a framework for a collaborative protocol.

A meeting has been set for February 2009 for NGO members of the Taskforce to meet with the MoJ, MSD, and NZ Police to progress the finalisation of the advocate role. At this meeting work will commence on developing national guiding principles and a process map to sit alongside the role description.  The guiding principles and the process map will be incorporated into the Ministry of Justice National Operating Guidelines for Family Violence Courts.

## Hotspots

This section highlights objectives that are subject to variation or have been identified as areas of risk. All objectives not mentioned in this section are on track to be completed as planned.

### Variations

Variations are formal requests for changes to objectives and/or actions in the Taskforce’s Ongoing Programme of Action. This table includes all approved variations of objectives from the Ongoing Programme of Action.

| Approved variations |  |  |  |
| --- | --- | --- | --- |
| Objective | Title | Variation summary | Status |
| 3.3 | Social Service Supporting Courts | The Objective remained the same, changes to the actions required. | Approved 4 April 2008. |
| 2.4 | Curriculum Development | The Objective remained the same, changes to the actions required. | Approved 28 March 2008. |

### Alerts

This table highlights areas that have been identified as at risk of not being delivered as planned.

| Objective | Title | Issue | Mitigation |
| --- | --- | --- | --- |
| 2.2 | Improving Attachment | Due to issues arising during the initial project scoping, this Objective is likely to be the subject of a variation. | To be confirmed in early 2009. |

### Upcoming Objective Deadlines (next two months)

This table highlights objective deadlines that are due over the next two months, or that have been completed and further deadlines need to be defined. If deadlines are not likely to be met, agencies should contact the Secretariat to discuss a possible variation.

| Objective | Title | Agency | Objective Deadline |
| --- | --- | --- | --- |
| 3.1 | Family Violence Courts | Judiciary / Ministry of Justice | A variation was submitted in July 2008 by the Judiciary (through MoJ). This variation will be overtaken before the next possible Taskforce meeting (April 2009) as the Objective is due to be completed by April 2009. |
| 3.3 | Social Services Supporting Courts | Ministry of Social Development / Ministry of Justice | April 2009. Information on the progression of this project will be provided following further discussions with key agencies and NGOs. |

## Changes to Monitoring Process

The Secretariat reviewed the monitoring process in late 2008. As a result of this review, the variation process has changed.  At the 10 December Taskforce meeting it was agreed that the Taskforce will now approve major changes at Taskforce meetings. The Taskforce member from the lead agency for an Objective will be given time on the agenda to answer any questions before a variation is approved.

Major changes are those that relate to the outcome of a piece of work, or the overall deadline for completion of the work. Any changes to key milestones will be flagged in the Monitoring Report.

Variation Request Process

The table below lists the variations that need to be discussed and agreed by the Taskforce at a future Taskforce meeting, the first of which is the 1 April 2009 meeting.

| Objective | Title | Variation summary | Status |
| --- | --- | --- | --- |
| 1.10 | Pacific Research Agenda | The Ministry of Pacific Island Affairs (MPIA) is seeking to withdraw from this action, and will instead focus on supporting the Pacific Programme of Action developed by the MSD’s Pacific Advisory Group (PAG). | Key stakeholders are being consulted over the variation to ensure agreement. |
| 2.5 | Violence in the Media | Objective and Actions will remain the same. The variation will change the final deadline only. | A variation is being drafted for consideration. |
| 4.2 | Pacific Service Workforce Development | This project plan is now part of the Pathway to Partnership work on workforce provider capacity and capability. A variation is being sought to extend the deadline for this work. | A variation is being drafted for consideration. |

Overtaken variations

This table lists variations that were not formally agreed but have subsequently been completed or are on track to be completed by the Taskforce meeting April 2009.

| Objective | Title | Variation summary | Status |
| --- | --- | --- | --- |
| 3.1 | Family Violence Courts | The variation sought a change to the deadline for this work. The Palmerston North Court became operational in September 2008, and the Whangarei Court is due to be operational in April 2009. | A variation was submitted in July 2008 by the Judiciary (through MoJ). This variation will be overtaken before the next full Taskforce meeting (April) as the Objective will be completed. |
| Action 66 (First Report) | Determine level of attendance and performance of perpetrators at programmes | The variation sought a change to the deadline for this work. The Ministry of Justice has collated and analysed the available data from a sample of courts. The summary paper has been completed and the results from this work will be used to inform Action 67. | Variation submitted July 2008, this variation has now been overtaken and the work is complete. |

### Complete or removed objectives

The table below lists the objectives that have been removed from the Monitoring Report due to being completed, merging, or now being business as usual.

| Objective | Objective title | Reason for removal | Lead agency | Removed from which report |
| --- | --- | --- | --- | --- |
| 1.8 | Case studies characterising good practice | Complete. | Ministry of Social Development (MSD). | February 2009 |
| 2.7 | Family Violence Death Reviews | Complete. The Family Violence Death Review Committee will report regularly to the Government. | Ministry of Health (MoH). The Secretariat for the Committee is Ms Aphra Green at MoH. | February 2009 |
| 4.3 | Service Demand Data | Complete. | MSD. | February 2009 |
| 4.4a | Training our Staff | Combining Objective 4.4a into 1.5 was recommended as the two Objectives cover the same action and outcomes. | ACC (HR). | February 2009 |
| 1.1a | Mapping the Ongoing Programme of Action | Outcomes covered in Objective 1.1 through monitoring of the work of the Taskforce by the Secretariat. | Non-Government Organisations (NGOs). | November 2008 |
| 1.5 a, b & c | Family Violence Free Workplaces | Three sub-sections merged into one (Objective 1.5). | ACC, MSD and Police. | First merged in November 2008 |
| 3.2 | Protocols for Family Violence Courts | Complete. | Ministry of Justice (MoJ). | November 2008 |
| 4.4b | Training of Staff (CYF) | Business as usual, will be monitored within CYF. | Child, Youth and Family (CYF). | November 2008 |

# Monitoring Report

The following section outlines progress on each key milestone and provides an update on work undertaken in the previous three months (November 2008 to January 2009) and work which is upcoming in the next three months (January to March 2009).

## Milestone updates and three month summaries

This section provides updates on each milestone, and updates on both work undertaken in the previous three months and work planned for the upcoming three months.

### Leadership

| ### 1.1 FACILITATION OF THE ONGOING PROGRAMME OF ACTION (OPOA) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Taskforce Secretariat / All Taskforce agencies |  |
| Project Manager |  |  |  | Carra Hamon |  |
| First Programme of Action reference |  |  |  | Action 3 |  |
| Objective and actions (as per Work Programme) Facilitation, implementation and strategic engagement of the Ongoing Programme of Action for specific groups and across all sectors in New Zealand. Actions include: - stewardship of the Ongoing Programme of Action work programme - stewardship of children specific work programme - stewardship of all other work programmes. |  |  |  |  |  |
| Objective deadline |  | Ongoing |  |  |  |
| Purpose To successfully monitor and ensure implementation of the Ongoing Programme of Action. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.1.7 | Protection Orders update to be sent to Minister. |  | April 2009 |  | On track. |
| 1.1.9 | Review of all Objectives, actions and milestones in the Monitoring Report. |  | 31 Dec 2008 |  | Complete. Changes to variation process agreed, and communicated to agencies, on 10 December 2008. |
| 1.1.12 | Monitoring Report for November prepared and sent with 10 December 2008 meeting papers. |  | 28 Nov 2008 |  | Complete. |
| 1.1.13 | Monitoring Report for February 2009 prepared. |  | 30 Jan 2009 |  | On track. |
| 1.1.14 | Facilitation of 11 February 2009 annual workshop. |  | 11 Feb 2009 |  | On track. |
| Progress to date (previous 3 months work) - Changes to the variation process were agreed at the 10 December 2008 meeting. Any major changes will now be taken to Taskforce meetings for approval of the Taskforce as a whole. - Planning for February 2009 workshop begun. Current ongoing work (next 3 months) - Preparing the Monitoring Report for the 11 February 2009 Taskforce meeting. - Planning for the February 2009 workshop. - Drafting one-year update on Protection Orders which will go to the Minister of Social Development and Employment (and possibly passed on to other relevant Ministers), draft to April 2009 Taskforce meeting. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 1.2 MĀORI PROGRAMME OF ACTION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agencies |  |  |  | Mäori Reference Group (MRG) Ministry of Social Development (MSD) |  |
| Contributors |  |  |  | Te Puni Kökiri, NGOs |  |
| Project Manager |  |  |  | Ann Dysart (MSD) |  |
| First Programme of Action reference |  |  |  | Action 7 |  |
| Objective and actions (as per Work Programme) A Programme of Action focused on eliminating violence in Mäori whänau is developed. Actions include: - developing a Mäori Programme of Action - ensuring the leadership and ownership of the actions at all levels of Te Ao Mäori - ensuring all designated actions are monitored and achieved. |  |  |  |  |  |
| Objective deadline |  | June 2013. |  |  |  |
| Purpose - To develop a process and plan that engages all areas of Te Ao Mäori in owning and addressing the issues of Family Violence and Child Abuse - To progress implementation of MRG’s Action Plan in order to achieve zero tolerance of whänau violence. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.2.6 | Develop initial Whänau Ora Indicators. |  | June 2009 |  | Project Plan developed identifying key work areas as follows: - develop a discussion document defining Whänau Ora - provide and co-ordinate Regional Hui - identify and work with existing Whänau Ora indicator workings. |
| 1.2.7 | Develop and publish initial Leadership Toolkit. |  | June 2009 |  | A Communications Plan has been developed providing for key work areas as follows: - rangatahi Hui - stocktake of current relevant communications material for Mäori - develop key messages for Mäori. |
| Background The Taskforce’s MRG has developed a Mäori Programme of Action (MPOA) which was presented to the Taskforce in late 2008. The Action Plan for 2008-2013 was presented to, and agreed by, the MRG in September 2008. Progress to date (previous 3 months work) - Regional hui notes have been discussed at MRG meetings and have been included as Actions where needed. - Action Plan for 2009 – 2013 was presented to MRG on 24 September 2008. - MRG’s collaboration with Taskforce agency champions is ongoing. Current ongoing work (next 3 months) - Whänau Ora Indicators: - discussion paper ready - be midway through Regional Hui - completed most of the existing Whänau Ora indicator models. - Leadership Toolkit: - rangatahi Hui completed - stocktake completed - key messages completed. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 1.3 PACIFIC PROGRAMME OF ACTION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Pacific Advisory Group (PAG) Ministry of Social Development (MSD) |  |
| Contributors |  |  |  | Ministry of Pacific Island Affairs, NGOs |  |
| Project Manager |  |  |  | Liz Tanielu (MSD) |  |
| First Programme of Action reference |  |  |  | Action 7 |  |
| Objective and actions (as per Work Programme) A Programme of Action focused on eliminating violence in Pacific families is developed. Actions include: - develop a Pacific Programme of Action (PPOA). - hold discussions with agencies to confirm action areas of responsibility and process for implementation. - develop the leadership action area to be coordinated by MSD with PAG. |  |  |  |  |  |
| Objective deadline |  | June 2013 |  |  |  |
| Purpose To develop and implement a plan to address family violence within Pacific families. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.3.5 | Hold discussions with agencies on the action areas and implementation process. |  | Oct 2008 |  | Complete. |
| 1.3.6 | Finalise implementation timeline and actions areas. |  | Nov 2008 |  | Complete. |
| 1.3.7 | Key agreed milestones incorporated into the Taskforce monitoring report. |  | Jan 2009 |  | On track. Milestones drafted. |
| 1.3.8 | PAG membership reviewed and updated. |  | Feb 2009 |  | On track. Appointment process being finalised. |
| Progress to date (previous 3 months work) - Work programmes developed for PPOA priority action areas. - PAG membership reviewed and updated. - Advice provided to projects such as Pathways to Partnership, Child Maltreatment, Pacific Research Agenda and Family Violence Court Community Service. Current ongoing work (next 3 months) - Commence work on specific action areas within the PPOA which include: - leadership engagement - community resources. - Continue to provide advice to projects such as Pathway to Partnership, Child Maltreatment, Pacific Research Agenda, and the Campaign for Action on Family Violence. - Hold first PAG meeting for the year. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 1.4 CHILD MALTREATMENT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Office of the Children’s Commissioner |  |
| Contributors |  |  |  | MSD, NGOs, NZ Police, Ministries of Justice, Health and Education |  |
| Project Sponsor |  |  |  | Dr Cindy Kiro |  |
| Project Manager |  |  |  | John Angus / Ruth Palmer (MSD) |  |
| First Programme of Action reference |  |  |  | N/A |  |
| Objective and actions (as per Work Programme) The objectives of the second phase are to agree and then carry out the work programme. The work programme comprises an integrated, cross sector approach to preventing child maltreatment. It draws on a growing evidence and knowledge base about the impacts of maltreatment. |  |  |  |  |  |
| Objective deadline |  | 30 June 2009 (second phase) |  |  |  |
| Purpose The Taskforce has agreed to give priority to the prevention of child maltreatment over the next three years, and has agreed the scope, focus and priorities of the proposed work programme. The purpose of the work for 2008 – 2009 is to: - enhance the contribution of the Health, Education and Social Services sectors to prevention of child maltreatment - understand better and take actions to reduce the incidence and prevalence of neglect, in particular of 0 – 5 year olds - strengthen effective community responses. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.4.7 | Project plans for the nine projects are completed. |  | Sept 2008 |  | Project plans for the five priority plans (1.4.8-9 and 1.4.12 are complete). Please see below for the remaining four project plans (‘Progress to date’). |
| 1.4.8 | Complete the review of the Health, Education and Social Service Sector Contributions to child maltreatment (3 of the 9 projects). |  | 31 Mar 2009 |  | On track. |
| 1.4.9 | Undertake research into neglect. |  | 30 Jun 2009 |  | On track. |
| 1.4.10 | Prepare advice on how development of the Campaign can further contribute to the prevention of child maltreatment. |  | 31 Aug 2008 |  | Decisions on national media work are being considered in the context of the future development and resourcing of the Campaign as a whole. |
| 1.4.11 | Development of the Campaign to include more specific actions on changing attitudes and behaviours around child abuse and neglect. NB: detail on changes to milestones 1.4.10 and 1.4.11 below (Progress to date). |  | 30 Jun 2009 |  | On track. Specific actions relating to child abuse and neglect include: - funding community actions through Community Action Fund (9 of 35 grants in October 2008 round) - community workshops - redevelopment of child focussed resources. |
| 1.4.12 | Take actions to work with communities to strengthen their preventive responses to child maltreatment including: - gathering evidence for what works by 31 December 2008 - providing greater support for successful community approaches by 31 March 2009 - supporting philanthropic sector plans for a trial of new approaches and commencing an evaluation of any trial by 30 June 2009. |  | 30 Jun 2009 |  | Evidence gathering complete. All other work on track. |
| Background The Ongoing Programme of Action includes developing a work programme on child maltreatment (including child sexual abuse) that: - focuses on improving outcomes for children - takes account of the different types of child maltreatment - identifies priority areas where the Taskforce can make a difference. Progress to date (previous 3 months work) - Milestones for the Campaign work stream have been changed to reflect the focus on integrating actions on child maltreatment into the media, community action and research components of the Campaign as a whole, rather than preparing a specific ‘Campaign phase’ on abuse and neglect. - Work continued on the review of the Health and Social Services Sectors, the Working with Communities project, Coordination, Neglect and Campaign work streams. - Preliminary literature review completed on ways to improve coordination and collaboration of prevention activities. - Project plans for the five priority areas (the three sector reviews, research into neglect, work through the Campaign and working with communities) are complete and on track. The remaining four project plans: - a project plan for the strategic conversation project will be completed in the new year after discussions with the project’s sponsor - project plans for the research into neglect and improving coordination and collaboration are on track to be completed in February 2009. Current ongoing work (next 3 months) - Continue work on the agreed 2008 – 2009 outputs, notably: completing sector reviews, undertaking the research on neglect, continuing to extend Campaign actions, and analysing the information obtained on community approaches. - The External Advisory Group (EAG) will meet with the Working Group to discuss the review of the Health, Education and Social Services Sector if time and work commitments of the EAG allow. The EAG will continue to be available for expert advice throughout 2009. - Completion of the Health, Education and Social Services Sector reviews by 31 March 2009. Timing / Ongoing / Recommendations / Conclusions Status = on track |  |  |  |  |  |

| ### 1.5 FAMILY VIOLENCE FREE WORKPLACES (MSD / ACC / NZ Police) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | MSD, ACC, Police |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | David Dick (MSD), Danielle George (ACC), Carol Train (Police) |  |
| First Programme of Action reference |  |  |  | N/A |  |
| Objective and actions (as per Work Programme) Family Violence Free Workplaces are developed and implemented through HR policy; link to Campaign, model for other agencies, role model for public and other workplaces. Actions include: - develop policy - put in place tools and resources - training of contact people/family violence co-ordinators - implementation - develop a model for replication in the public sector and private sector. |  |  |  |  |  |
| Objective deadline |  | May 2012 |  |  |  |
| Purpose Family Violence Free Workplaces means staff in these workplaces are aware of and supported around issues to do with family violence. These workplaces are expected to provide low cost, high impact prevention and recovery opportunities for members of the workplace who are affected by family violence. They may be victims, observers or perpetrators. Implementing Family Violence Free Workplaces is expected to decrease workplace stress and increase workplace productivity by empowering and supporting victims and observers of family violence and channelling perpetrators through appropriate channels to help them change their behaviour. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.5.1 | Policy developed and agreed. |  | Dec 2008 |  | Some delay. This date and deliverable will be reconsidered subject to revisions of agencies’ workplans. |
| 1.5.2 | Tools, resources and training to support and promote the policy, and raise awareness of family violence are developed, agreed, and implemented. |  | Dec 2009 |  | On track. |
| 1.5.3 | Assessment and evaluation of agency programmes. |  | Dec 2010 |  | On track. |
| 1.5.4 | Develop Blueprint/model for implementing Family Violence Free Workplaces in public, private and non-government sectors. |  | June 2011 |  | On track. This Blueprint will be a collaborative piece of work between Police, MSD and ACC. |
| Context and background Objective 1.5 was initially split into three project plans reflecting the work of MSD (1.5a), ACC (1.5b) and the NZ Police (1.5c). All three organisations have been working toward the same Objective since the development and agreement of the OPOA in late 2007. MSD, ACC and NZ Police have met regularly to work together, share knowledge and learning, and will continue to do so. MSD HR will liaise with Project Managers from all three organisations to provide updated information for each Monitoring Report. The consolidation of these work programmes into one project plan will more clearly reflect the overall objective of developing a Family Violence Free Workplaces model for replication in the public and private sectors. Completed work (since 2007) MSD - General awareness information sessions on family violence held for National Office staff. - In-depth sessions on family violence held for HR staff. - Campaign posters distributed and poster display in MSD National Office foyer. - Distributed resources eg. ‘Are you OK?’ booklets. - Establishment of Family Violence Peer Support Programme in Work and Income. - Published resources and information about referral service on the intranet. - Published a highly visible ‘It’s not OK’ advert on intranet homepage. - Included family violence campaign ‘It’s not OK’ page in 2008 Calendar for staff. - Ensured the provision of family violence counselling as a criterion in the RFP for an EAP provider. - Completed service line consultation on the draft Policy. - Completed service line consultation on the draft Managers’ Guidelines to support the Policy. ACC - In-depth training on family violence delivered to HR staff. - Partnership approach developed with Stratos. - Development of a support package on family violence for staff. - Support package and partnership launched to staff as part of Safety NZ Week – Safety in the Home, available on intranet and via text service. - Managers’ guide published on intranet. - Policy development, and policy launched as part of Staff Wellbeing Programme. Police - Timeline developed with key milestones. - Internal working group established (consisting of HR (lead), Operations group, Policy group, Training Service centre and District representation). - Draft policy consultation phase completed. - Working group to discuss feedback, make changes required and report to Taskforce in March/April 2009 for approval. - Policy for sign off in February. Progress to date (previous 3 months work) MSD - Policy and supporting Managers’ Guidelines provided to particular business units for consideration on the scope of these documents. Ongoing awareness raising includes: - Provided staff with white ribbons on White Ribbon Day (25 November 2008). - Included family violence campaign ‘It’s not OK’ page in 2009 Calendar for staff. - Story published on front page of staff intranet about the ‘It’s not OK’ campaign team at the Whänau Christmas event in Auckland. ACC - Support package publicised to staff via staff DVD and launched by the General Manager Strategic Policy & Research. - All programmes are now on track and in place across ACC (completion of first phase by December 2008). - Re-launched support package and the Policy to complement White Ribbon Day (25 November 2008). Chief Executive championing the messages across ACC. Police - A working group was established to provide feedback for the writing of the draft policy. The working group included representation from HR, Policy, Operations and District. - The final draft version is now complete. - Consultation phase completed Current ongoing work (next 3 months) MSD - Review the scope of Policy and Managers’ Guidelines documents and plan for family violence initiatives. - Ministry promotional material and resources will continue to be provided to staff to further raise awareness. Material and resources will support the launch of the Policy and Guidelines (pending the review of their scope). - Review of Work and Income Peer Support Programme delayed due to new work priorities, now due in the first 6 months of 2009. ACC - Complete a review into the effectiveness of the support package at the six month mark (end of December 2008). - Continue to research the development of the workplace Policy that extends influence to outside the workplace. - Develop ongoing communications plan to ensure staff awareness and track progress of programme. Police - Working group will make required changes from feedback and report to Taskforce meeting in the Monitoring Report for March 2009. - The policy will then go for Executive sign off. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 1.6 IWI-LED CRIME PREVENTION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | New Zealand Police |  |
| Contributors |  |  |  | Iwi, NGOs, Te Puni Kökiri, MoJ (including Crime Prevention Unit) |  |
| Project Manager |  |  |  | Wally Haumaha |  |
| First Programme of Action reference |  |  |  | N/A |  |
| Objective and actions (as per Work Programme) Iwi-led crime prevention plans which have a focus on the prevention of family violence Actions include: - provide support to iwi to develop plans - iwi-led crime prevention strategies developed in accordance with each iwi’s identified needs, values and timeframes. - Mäori Family Violence scoping studies. |  |  |  |  |  |
| Objective deadline |  | The NZ Police state that this is an iterative and evolving process that is being driven by iwi. Precise deadlines are neither available, nor appropriate at this stage. |  |  |  |
| Purpose In absolute numbers, a high number of Mäori churn through the criminal justice system every year. A new framework for action is being developed by Mäori with assistance from officials. That new framework is Iwi-led Crime Prevention Plans (ICPPs). ICPPs take a long-term, incremental approach to improving Mäori criminal justice outcomes. They are led by iwi, with assistance from officials. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.6.1 | Iwi to populate their crime prevention plan templates. |  | Ngati Whatua me Tainui ki te Tonga, and, Ngai Tahu have set deadlines for first drafts of June 2009. |  | Writers appointed by iwi are not using the template provided, so officials will condense and refine the core documents from iwi into the template, once drafts are received. |
| 1.6.2 | Officials to condense those templates into A3 summaries. |  | No deadline |  | Pending. |
| 1.6.3 | Summaries to be presented back to iwi for confirmation. |  | No deadline |  | Pending. |
| 1.6.4 | Ministerial briefing paper to Ministers of Justice, Police and Mäori Affairs. |  | March 2008 |  | Complete |
| New Action (as above) - Mäori Family Violence scoping studies. The Police Commissioner has asked his Mäori Focus Forum to go back to each of their Districts and begin compiling a comprehensive profile on family violence issues among Mäori regionally. He further requested Police Policy Group to provide technical assistance. This has culminated in a three page scoping document for each of the forum members to take back to their areas to complete. It is hoped that this will help facilitate ICPPs, by giving iwi a very specific focus (the idea is that they will start small and grow over time) while at the same time progressing whole-of-Government work on Family Violence. This is a work in progress Background recent work (2007/2008) Police and Te Puni Kökiri have been supporting iwi with the necessary tools to develop and design their own Plans. The type of support provided includes: - providing Police intelligence to iwi groups that enable iwi to understand the crime problems and profiles of Mäori (offenders and victims) within their geographical areas - providing specialised trained staff who are able to take iwi through a formal problem solving approach to crime prevention methodology training in SARA and POP models - providing draft ICPP templates and Guidance Notes for preparation of the Iwi Plans - funding writers nominated by iwi to begin drafting iwi-specific crime prevention plans. Progress to date (previous 3 months work) - Ngai Tahu have met with all three Police Districts in their regions and developed a preliminary project plan. Part of that plan includes holding discussions with Te Tau Ihu about a collaborative, South Island-wide plan, prior to engaging with iwi. - A writer has been appointed for the joint plan for Auckland-metro, and is supplying more detailed budget information for TPK's internal funding processes before his work can commence. A first draft is expected by the end of April 2009. - Ngapuhi have appointed a writer who is near completion of the first draft. - Consultation is underway (led by TPK, Hutt Office) to develop an urban approach to reducing offending by Mäori in Wellington. - Discussions have commenced about reinvigorating the EI: Programme of Action for Mäori, and including ICPPs as a lead project within that (MoJ lead). - A Mäori crime profile for Wellington has been supplied to TPK Hutt Office to inform their preliminary consultation about an urban approach to offending by Mäori in Wellington. Current ongoing work (next 3 months) - Police Policy group have suggested that officials condense and refine core iwi plans into the ten page template provided, and are awaiting feedback on that. - A status report has been developed and is being circulated monthly to the key inter-agency group, plus other Government Stakeholders. Latest circulation was 14 January 2009. - Corrections (through Uarnie More) will make contact with iwi plan writers, via TPK, to discuss how they can contribute to the plans. - A Mäori crime profile for Tasman will be distributed to the TPK RD responsible to inform his discussions with iwi there. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 1.7 FAMILY VIOLENCE CLEARINGHOUSE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | Families Commission, NGOs |  |
| Project Manager |  |  |  | Jeff Sheerin |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) The New Zealand Family Violence Clearinghouse (NZFVC) is enhanced to ensure its efficacy and to become the independent, sustainable, comprehensive one-stop shop for national and international information on family violence. Actions include: - develop a model and systems which optimise the operations of the NZFVC. |  |  |  |  |  |
| Objective deadline |  | June 2009 |  |  |  |
| Purpose To review NZ Family Violence Clearinghouse activities and services and develop a strategy for moving forward. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.7.2 | Scope redevelopment of NZFVC project, identify requirements and develop strategy |  | Sept 2008 |  | This work is well underway. We have been consulting with key stakeholders to look at requirements for the NZFVC. MSD IT to gather information requirements for the new website. |
| 1.7.3 | Develop 2-5 year strategy |  | 30 June 2009 |  | Continue discussions around the new strategic plan and associated work programme. In December 2008 we had a meeting with the NGO Consortium Managers to discuss the way forward for the NZFVC and will be meeting on a regular basis to look at the strategic direction over the next 2 – 5 years. |
| 1.7.4 | Develop project plan and secure funding |  | Sept 2008 |  | Complete. Planning for new long term sustainable clearinghouse website by June 2009. Cabinet funding is ongoing. |
| 1.7.5 | Implement new NZFVC website and service |  | 28 Feb 2009 |  | Site due to go live in March 2009. |
| Progress to date (previous 3 months work) - Work is underway for a new NZFVC website on the basis of bringing the IT operations for the NZFVC in-house to MSD. - Working closely with MSD IT to ensure that requirements are reflected in the new design. - Currently working with MSD IT to gain agreement on the capitalisation of redevelopment costs for the new website and associated applications. - Setting up regular meetings with the NGO consortium Managers to discuss strategic direction for the NZFVC and will continue to consult with key stakeholders and Advisory Group members. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 1.9 MĀORI RESEARCH AGENDA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Te Puni Kökiri |  |
| Contributors |  |  |  | MRG, MSD, Families Commission, NGOs |  |
| Project Manager |  |  |  | Te Atarangi Whiu |  |
| First Programme of Action reference |  |  |  | New initiative |  |
| Objective and actions (as per Work Programme) Improve our understanding of the nature of family violence in whänau Mäori and successful models of prevention and intervention. Actions include: - review existing literature - develop a research agenda - link to the Taskforce strategic research agenda for family violence prevention - recommend further action. |  |  |  |  |  |
| Objective deadline |  | 5 September 2008 (Complete to 5 September. Some rolling action outlined below) |  |  |  |
| Purpose To increase the evidence base by providing case studies of a minimum of three Mäori designed, developed and delivered programmes. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.9.3 | Final Report |  | 5 Sept 2008 |  | Complete. Final report and summary report submitted to the Taskforce in December 2008. An article highlighting the Mäori Research Agenda is to be published in the February/March 2009 issue of the Te Rito newsletter. |
| Background Te Puni Kōkiri identified current information regarding family violence for Mäori, and looked at culturally distinct models of prevention and intervention for Mäori. An agenda for research emerged from this work. Three key outputs for this work were: - Output One: A literature review intended to identify current information on Mäori family violence, information gaps, inconsistencies, and themes within the literature on family violence and Mäori. - Output Two: A case study analysis of existing Mäori designed, developed and delivered initiatives that address family violence. - Output Three: A summative report that analyses Outputs one and two and identifies research priorities to form a Mäori Research Agenda. Progress to date (previous 3 months work) - Key deliverables, literature review, case studies and summative report, completed. Current ongoing work (next 3 months) - Article to be published in the February/March 2009 Te Rito newsletter highlighting work complete on the Mäori Research Agenda. Discussions to be held with MSD and other departments regarding implementing the Mäori Research Agenda. Timing / Ongoing / Recommendations / Conclusions Status = complete to 5 September 2008. Some reporting of rolling action on this Objective. |  |  |  |  |  |

| ### 1.10 PACIFIC RESEARCH AGENDA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Pacific Island Affairs (MPIA) |  |
| Contributors |  |  |  | PAG, MSD, Families Commission, NGOs |  |
| Project Manager |  |  |  | Diane Anorpong |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) Key stakeholders are being consulted over the variation to ensure agreement. The below Objective and actions are the original. |  |  |  |  |  |
| Improve our understanding of the nature of family violence in Pacific families and successful models of prevention and intervention. Actions include: - review existing literature - develop research agenda - link to the Taskforce strategic research agenda for family violence prevention - recommend further action. |  |  |  |  |  |
| Objective deadline |  | Final deadline to be confirmed (subject to variation). |  |  |  |
| Purpose To develop an understanding of Pacific family violence research priority topics and the issues which surround Pacific family violence research. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.10.1 | Finalise project plan |  | April 2008 |  | Complete. Project plan finalised, stakeholder discussions complete. |
| 1.10.2 | Consult with Pacific Advisory Group (PAG) |  | June-July 2008 |  | Ongoing. |
| 1.10.3 | Consult with other Pacific stakeholders |  | August 2008 |  | Delayed. |
| 1.10.4 | Completion of report |  | September 2008 |  | Delayed. |
| Background The Pacific Family Violence Research Agenda will sit within a Pacific Research Agenda. Progress to date (previous 3 months work) - MPIA met with PAG to discuss how to best support the Pacific Programme of Action, and consulted with the Families Commission, MSD and PAG on the variation which was submitted to the Taskforce Chair on 14 November 2008. This variation has not yet been approved by the Taskforce. Current ongoing work (next 3 months) - Consultation on the variation is ongoing; the variation has not yet been approved. - The Ministry is committed to supporting the Pacific Programme of Action developed by PAG. The Ministry intends to: - assist with the development of a communications strategy to support stronger collaboration between government, Pacific people and NGOs - support opportunities for dialogue between Pacific leaders and other stakeholders with the intention of strengthening Pacific leadership and responsiveness to family violence - facilitate linkages between the Pacific Programme of Action and other complementary pieces of work. Timing / Ongoing / Recommendations / Conclusions Status = delayed. A variation submitted in November 2008 is still in consultation. |  |  |  |  |  |

| ### 1.11 NEW MIGRANT AND REFUGEE RESEARCH AGENDA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | Dorothy Adams |  |
| First Programme of Action reference |  |  |  | N/A |  |
| Objective and actions (as per Work Programme) Improve our understanding of the nature of family violence in new migrant and refugee families and successful models of prevention and intervention. Actions include: - review existing literature - develop a research agenda - link to the Taskforce strategic research agenda for family violence prevention - recommend further action. |  |  |  |  |  |
| Objective deadline |  | April 2009 |  |  |  |
| Purpose A statement of purpose will be developed in the scoping phase. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.11.1 | Synthesis of literature |  | April 2008 |  | Complete. Annotated bibliography has been completed. |
| 1.11.2 | Scoping paper |  | Dec 2008 |  | Complete. Draft research approach has been circulated internally for comment and feedback. |
| 1.11.3 | Recommendations for further action |  | March 2009 |  | On track. Further consultation to agree next steps in research programme. |
| Progress to date (previous 3 months work) - A scoping paper setting out an approach for research to build knowledge on family violence prevention in migrant and refugee families has been drafted and circulated internally for comment and feedback. Current ongoing work (next 3 months) - External consultation on draft research approach, which will be presented to Taskforce together with resource implications. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 1.12 ELDER ABUSE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | Cilla Corlett |  |
| First Programme of Action reference |  |  |  | N/A |  |
| Objective and actions (from work programme) Improve our understanding of the nature of elder abuse and successful models of prevention and intervention. Actions include: - review existing literature - develop a research agenda - link to the Taskforce strategic research agenda for family violence prevention - recommend further action. |  |  |  |  |  |
| Objective deadline |  | 2010 (Deadline as per 1.12.4; ‘Action Plan’ implementation) |  |  |  |
| Purpose/Expected Outcome Improved decision-making about viable programme and service delivery to eliminate elder abuse and neglect within the family setting. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.12.2 | Develop a research agenda. |  | 30 July 2008 |  | Complete. Recommended research agenda sent to the Families Commission for inclusion into the Commission’s research agenda. |
| 1.12.4 | Recommend further action. |  | 10 Dec 2008 Mid 2009 2009/10 |  | Complete. Reported to 10 December 2008 Taskforce meeting with recommended priorities for action. Broader consultation with sector to gain wider engagement with plans Implementation of action plan |
| Background The proposed research agenda on Elder Abuse and Neglect is covered in the report presented to the Taskforce in December 2008. Progress to date (previous 3 months work) - Priorities for further action identified. - Initial consultation with sector on issues and priorities. - Reported on proposed priorities for further action to the Taskforce at the Taskforce’s December 2008 meeting. Current ongoing work (next 3 months) - Broader consultation with sector to gain wider engagement with plans (timeframe to be confirmed). - Report back to the Taskforce for endorsement of leadership goal arising from the plan, for inclusion in the Taskforce’s Ongoing Programme of Action (timeframe to be confirmed). - Commence implementation of action plan. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 1.13 DATA ON NGO SERVICE DELIVERY |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | NGOs, ACC, MoJ, Police, MoH |  |
| Project Manager |  |  |  | Dorothy Adams |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (from work programme) High quality data available about services delivered by, and on the demand for, NGO and agency family violence services. Actions include: - develop systematic and accurate data on services. |  |  |  |  |  |
| Objective deadline |  | Ongoing |  |  |  |
| Purpose To understand the family violence services available and the ongoing demand for services; both volume and type. This work is aligned with the Pathway to Partnership (P2P) initiative. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.13.2 | Determine reporting and monitoring information requirements, data currently available and data collection methods. |  | 30 March 2009 |  | Work has been re-prioritised to allow resources to complete information model trial activity. Timeline, including completion date, being re-planned at present to align with outcomes framework. |
| 1.13.3 | Determine requirements for reporting and evaluation systems support (linked to the Outcomes Framework Project). |  | 30 March 2009 |  | Deferred until outcomes framework complete. Timeline aligned with 13.3.2. |
| 1.13.4 | Conduct a monitoring and reporting trial of an information model with NGO and MSD participants. |  | 30 Oct 2008 |  | Complete. Preliminary trial of the information model complete. Areas for enhancement and clarification identified and to be incorporated in the model before further trial is conducted. |
| 1.13.5 | Define the requirements that relate to potential ongoing information management solutions. |  | 15 June 2009 |  | Follows data collected in 1.13.2. The completion date has been amended, as set out below. |
| Background As part of P2P initiative, which is aimed at ensuring a sustainable social sector for NGOs providing essential services for families, children and young people, a data monitoring system that focuses on outcome measures will be developed and implemented in collaboration with the sector. This monitoring system will provide high quality data about service outcomes. All essential Family Violence prevention services will be part of this initiative. Current ongoing work (next 3 months) - Terms of Reference for investigating the development of a data collection system was approved by the P2P Management Group. - The key milestones and deliverables have been amended to align with interdependencies with other P2P workstreams as follows: - complete analysis of current MSD and NGO data collection systems by 30 March 2009 - recommendations paper for 'Go Forward' options for data collection systems completed by 15 June 2009. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

### Changing Attitudes and Behaviour

| ### 2.1 KIA PUĀWAI |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | All Taskforce members |  |
| Project Manager |  |  |  | Anne Riley |  |
| First Programme of Action reference |  |  |  | Not in first Programme of Action |  |
| Objective and actions (as per Work Programme) Kia Puäwai supported in its implementation by the Taskforce. Taskforce supports initiatives such as: - increasing coverage of intensive home visiting - providing free Early Childhood Education for all vulnerable children aged 18 months – 3 years - developing an integrated identification, assessment and referral system for young children - expanding Early Years hubs and teen parent co-ordinators initiatives - key workers to support at-risk families - expanding Social Workers in Schools. |  |  |  |  |  |
| Objective deadline |  | Ongoing |  |  |  |
| Purpose This cross-agency initiative is building an early years intervention system to help ensure all children flourish in early childhood and reach their potential as young adults capable of developing healthy, respectful and violence-free relationships throughout their lives. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 2.1.3 | B4School check pilot in place. |  | Aug 2008 |  | Complete. Pilot in place. |
| 2.1.4 | Report-back to Cabinet. |  | June 2009 |  | On track. |
| Progress to date (previous 3 months work) - Work has continued on evaluating six pilot programmes to improve outcomes for children and their families. This work will inform the June 2009 report back to Cabinet on future funding decisions. - All DHBs across the country had started delivery of the B4School Check by September 2008. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 2.2 IMPROVING ATTACHMENT |  |  |  |  |
| --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Health / Auckland District Health Board |  |
| Contributors |  |  | MSD, ACC, MinEdu, NGOs |  |
| Project Manager |  |  | Pat Tuohy / Carol Stott |  |
| First Programme of Action reference |  |  | N/A |  |
| Objective and actions (as per Work Programme) Promote and improve attachment between new-born babies and parents and caregivers. Actions include: - progress a pilot - see how well it works - report - draw on key findings from parent support and development programmes already focused on supporting attachment between young children and parents and caregivers. |  |  |  |  |
| Objective deadline |  | July 2009 |  |  |
| Purpose Supporting the promotion of healthy secure attachment in infants is important for the development of quality relationships between infants and parents and caregivers, and for its effect on human development and wellbeing. Promotion of secure attachment can be provided through provision of information to parents, and support with strategies that enhance attachment and address any parenting concerns. Early intervention is recommended for infants of high-risk carers if developmental or behavioural problems are detected. |  |  |  |  |
| Key Milestones |  |  | Date | Description of Progress |
| 2.2.1 | Inclusion of an additional visit in the WellChild Framework for first time parents, especially fathers and male partners. |  | July 2009 | Project planning commenced |
| 2.2.2 | Promotion of infant-parent attachment and assessment of parent /child relationship difficulties in revised WellChild Framework. |  | July 2009 | Project planning commenced |
| 2.2.3 | Training for WellChild Providers to promote secure infant-parent attachment. |  | July 2009 | Project planning commenced |
| 2.2.4 | Establishment of a pilot in the Auckland District Health Board area to prevent Shaken Baby Syndrome (head injuries to babies caused by violent shaking). |  | TBC | This pilot did not proceed due to issues that arose during scoping. |
| Background The pilot to prevent Shaken Baby Syndrome (key milestone 2.2.4) did not proceed as initial scoping highlighted issues with the pilot site. Timing / Ongoing / Recommendations / Conclusions Status = alert. This Objective is likely to be subject to variation, to be confirmed in early 2009. |  |  |  |  |

| ### 2.3 CONDUCT DISORDER / SEVERE ANTI-SOCIAL BEHAVIOUR |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Social Development |  |  |
| Contributors |  |  | MinEdu, MoH, MoJ and Police (Inter-Agency Plan partners). NGOs, Office of the Children’s Commissioner (OCC), and other relevant agencies will be consulted on policy development. |  |  |
| Project Manager |  |  | Saskia Patton |  |  |
| First Programme of Action reference |  |  | N/A |  |  |
| Objective and actions (as per Work Programme) Ensure comprehensive behavioural interventions for children aged 3 – 7 years with conduct problems and their families are delivered in accordance with the Inter-agency Plan by building on the specialist behaviours services already provided by the Ministry of Education. In addition, there will be the transitioning of existing services to older children and young people to evidence-based, best-practice interventions. The Taskforce supports the four action areas in the Inter-Agency Plan: - leadership, coordination, monitoring and evaluation - transition existing service provision to evidence-based, best-practice interventions - establish an intensive, comprehensive behavioural service for 3 -7 year olds - build a shared infrastructure for the delivery of specialist behavioural services. |  |  |  |  |  |
| Objective deadline |  | 2012 |  |  |  |
| Purpose Developing and delivering a suite of services for the 5% of early childhood and primary (and intermediate) school aged children who have conduct problems will reduce the prevalence of young people with these problems. Without appropriate interventions, these children are more at risk of becoming perpetrators of violence. Over time these services are anticipated to result in a subsequent reduction in cases of family violence. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 2.3.2 | Best practice report completed. |  |  | June 2008 | Complete – awaiting publication (expected at Education behavioural meeting 16/17 March 2009). |
| 2.3.3 | Agency service reviews/stocktake completed. |  |  | Dec 2008 | Complete – initial stocktake complete. Ongoing review continuing. |
| Ongoing deliverables still to be confirmed by new Government. Briefing going to new Minister early February 2009. |  |  |  |  |  |
| Background This is an inter-agency project which seeks to improve behavioural interventions for 0-17 year olds across service areas of the Ministries of Education, Health, Justice and Social Development (CYF). In particular, it will establish a comprehensive behavioural service for children aged 3-7 years (subject to further investment) and transition existing services for older children and young people to evidence-based, best-practice interventions. Progress to date (previous 3 months work) - The Advisory Group for Conduct Problems (AGCP) had its first meeting on 14 November 2007 and has met nine times in 2008. - Best practice report finalised, edited and proofed ready for publication. Release of document expected in February 2009, subject to sign off from Minister. - AGCP close to completing first draft of a second report: Translating Evidence into Practice which is looking at programme selection for 3-7 year olds and a research design to best support the implementation of selected programme(s). - Agencies continuing to undertake stocktake of current services that may need to be transitioned to evidence-based practice. Current ongoing work (next 3 months) - AGCP will continue drafting the Translating Evidence into Practice report (focus on 3-7 year olds’ services). - AGCP will commence drafting a report on services for teenagers. - AGCP work programme/ roadmap planning. - Attendance and discussion at Taumata Whanonga – From evidence to action behavioural summit being run by the Ministry of Education. - Officials and AGCP planning to run a workshop on implementation and transition issues utilising Steve Aos from the Washington State Institute for Public Policy. - MSD will be developing an implementation plan to support the delivery of the Inter-agency Plan. Timeframes on delivery of new services to 3-7 year olds subject to decisions on further investment/ re-investment. - Working Group on Conduct Problems will be drafting information on the project for the new Minister for Social Development on Conduct Problems work areas. - Te Roopu Kaitiaki will be drafting a report reviewing the evidence base and research requirements in considering the development of parallel Te Ao Mäori-based services and whänau ora based models of practice. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 2.4 CURRICULUM DEVELOPMENT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Education |  |  |
| Contributors |  |  | MSD (MYD), MoH, TPK, MPIA, OCC, NGOs |  |  |
| Project Manager |  |  | Hayley Corbett |  |  |
| First Programme of Action reference |  |  | N/A |  |  |
| Objective and actions (as per Work Programme) Children and young people aged 5-18 years develop the knowledge and skills that they need to support good decision-making, to make healthy choices, and to seek help when they need it. Actions include: - provide support to enable schools to develop their programmes within the New Zealand curriculum to suit the diverse learning needs of their community - strengthen whole-school, strengths-based approaches that promote resilience and confidence in young people and those adults who support them - seek opportunities to identify and respond to children who are affected by family violence. |  |  |  |  |  |
| Objective deadline |  | Ongoing |  |  |  |
| Purpose The purpose of education is to help children and young people reach their potential and develop the competencies they will need to live, learn, work and contribute as active members of their communities. Education contributes to the prevention and reduction of family violence in New Zealand communities by providing a safe environment that teaches and models skills to enable children and young people to manage their own wellbeing and to relate in healthy ways with others. It provides children and young people with the opportunity to learn skills they might not otherwise receive in the home environment. To experience the benefits of education, students must participate and be engaged with the education system. The Ministry of Education supports educators to identify students who are at risk as a result of experiencing, witnessing or engaging in family violence and to work with parents, families and whänau, and other agencies to ensure these students are appropriately supported. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 2.4.1 | Provide support to enable schools to develop their programmes within the New Zealand Curriculum (NZC) to suit the diverse learning needs of their community. - Release final curriculum and supporting resources for schools to support the implementation of the curriculum - Professional leaders are supported to lead curriculum development, establish the conditions for professional learning and involve families/ whänau in focusing on student achievement and educational outcomes based on the NZC. |  |  | Ongoing Ongoing | On track. Both Te Marautanga o Aotearoa (Māori Medium curriculum) and New Zealand Curriculum (English medium school) in place, ongoing support. MoE continues to plan for exemplars of the second report on the exploratory studies of ‘early adopters’ of the NZC to be published in early 2009. |
| 2.4.2 | Strengthen the implementation of whole-school, strengths-based approaches that promote resilience and confidence in children and young people and those adults who support them. - Support up to 730 teachers per year in developing effective teaching and leadership skills to support the implementation of school-wide approaches to student wellbeing / mental health. This involves strengthening teachers’ understanding of the connections between school organisation, curriculum design and delivery and community consultation and partnerships. - Identify successful professional learning approaches for teachers from the evaluation of the student wellbeing contracts and incorporate in the design and delivery of ongoing professional development contracts. |  |  | Ongoing Ongoing | On track. An initiative to prevent bullying in schools was launched in July 2008. Ongoing review of progress on school-wide approaches to student wellbeing and mental health. Plan for continuation of this work in participant schools until the end of June 2009. MoE, the national coordinator and facilitators continue to review and improve the models used in the delivery of the Student Well-Being and Mental Health contracts. |
| 2.4.3 | Seek opportunities to identify and respond to children and young people who are affected by family violence. - Review the quality and accessibility of support available to educators who are concerned about children and young people affected by family violence. - Develop a review of the support received by children and young people identified while at school as affected by family violence (in conjunction with Obj 1.4 Child Maltreatment). |  |  | Ongoing Ongoing | On track. Modifications to the education profile and plan guidelines and templates for children in care continue to be made as it continues to be rolled out into other trials sites throughout the country. Work has commenced on a review of the Education sector’s contribution to prevention of child maltreatment. |
| Background In 2002, the Ministry of Education’s Curriculum Stocktake Report identified that, while many students were achieving at world-class levels, there are wide disparities in outcomes for diverse students. Progress to date (previous 3 months work) 2.4.1 The New Zealand Curriculum MoE continues to plan for exemplars of the second report on the exploratory studies of ‘early adopters’ of the NZC to be published in early 2009. Te Marautanga o Aotearoa (Mäori Medium curriculum) was released in September 2008. Implementation of the curriculum will commence in January 2009 and continue through until December 2010. Implementation support includes development of resources and information to assist schools to design their own school-based curriculum. 2.4.2 Whole-school, strengths-based approaches that promote resilience and confidence in children and young people Facilitators continue to work with their contract schools to review progress towards meeting contract outcomes related to implementing school-wide approaches to student wellbeing and mental health. Data analysis is being used to plan for the continuation of this work in the participant schools until the end of June 2009. MoE, the national coordinator and facilitators are continuing to review and improve the models used in the delivery of the Student Well-Being and Mental Health contracts and to integrate the learning in ongoing professional development contracts. 2.4.3 Identifying and referring children affected by family violence to appropriate services Modifications to the education profile and plan guidelines and template for children in care have been made as a result of the trial currently underway within the Auckland District Health Board. Modifications continue to be made as it is rolled out into other trial sites throughout the country. Current ongoing work (next 3 months) 2.4.1 The New Zealand Curriculum Exemplars of the second report on the exploratory studies of ‘early adopters’ of the New Zealand Curriculum (NZC) to be published in early 2009. Work continues in preparation for the implementation of Te Marautanga o Aotearoa from January 2009 through until December 2010. MoE continues to plan for the release of the Principals’ Leadership Strategy in February 2009. This strategy will provide a three to five year plan outlining how the Government intends to work with the sector to achieve the goal of strong professional leadership in every New Zealand school by 2012. 2.4.2 Whole-school, strengths-based approaches that promote resilience and confidence in children and young people We continue to work on the development and medium of a resource called Making a Difference which will show how eight New Zealand schools are engaging students in positive learning and achievement. We will continue to update and promote the supporting positive behaviours website. Facilitators will continue to work with their contract schools to review progress towards meeting contract outcomes related to implementing school-wide approaches to student wellbeing and mental health. This work will continue in participant schools until the end of June 2009. MoE, the national coordinator and facilitators are continuing to review and improve the models used in the delivery of the Student Well-Being and Mental Health contracts and to integrate the learning in ongoing professional development contracts. 2.4.3 Identifying and referring children affected by family violence The trial of the education profile and plan has been extended to Counties Manukau, Wairarapa, Horowhenua and Lakes District. The trial is about to begin in Horowhenua/Wairarapa and Lakes District. Work has commenced on a review of the Education sector’s contribution to prevention of child maltreatment, with a particular focus on the Early Childhood Education sector. MoE continues to work with the Inter-Agency Working Group and internal stakeholders to agree the scope of the review and finalise the project plan. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 2.5 VIOLENCE IN THE MEDIA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Families Commission |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | Radha Balakrishnan |  |
| First Programme of Action reference |  |  |  | Action 23 |  |
| Objective and actions (as per Work Programme) Create awareness of impact of violence in the media on children aged between 6 to 11 years. Actions include: - scope an evidence-based public education and awareness programme aimed at parents - scope financial implications - develop an implementation plan. |  |  |  |  |  |
| Objective deadline |  | February 2009 (Variation to change deadline about to be submitted) |  |  |  |
| Purpose To scope a public education and awareness programme around violence in the media (its risks and impact) with an initial focus on parents of 6-11 year olds. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 2.5.2 | Develop plan |  | Oct 2008 |  | Planning work commenced |
| 2.5.3 | Draft Report circulated for comment |  | Dec 2008 |  | Not commenced |
| 2.5.4 | Report to the Taskforce |  | Feb 2009 |  | Not commenced |
| Background Violence in the media and its impact on society generally was raised at the meeting with the Family Violence Ministerial Team and with members of the Multi-Party Working Group on Family Violence, when the Taskforce’s First Report was presented in mid 2007. The first POA included an action to review how violence is portrayed in the media, utilising the 2004 Report on TV Violence in New Zealand, and to advise on implications for the next POA The Families Commission agreed to lead this work. The Taskforce supported raising awareness of the impact of violence within the media on children and young people. The 2004 report identified middle childhood (between 6-11 years) as a vulnerable group and it was agreed that this group should be the initial focus of any public education work. Timing / Ongoing / Recommendations / Conclusions Status = delayed. Variation to change deadline about to be submitted. |  |  |  |  |  |

| ### 2.6 CAMPAIGN FOR ACTION ON FAMILY VIOLENCE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | MSD / Families Commission |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | Gael Surgenor |  |
| First Programme of Action reference |  |  |  | Actions 29-39 |  |
| Objective and actions (as per Work Programme) Continue the Campaign for Action on Family Violence through: - an advertising campaign - resource development and distribution - Community Action Fund projects. |  |  |  |  |  |
| Objective deadline |  | 30 June 2009 (Ongoing to 2010) |  |  |  |
| Purpose This is a community-based social marketing campaign which aims to influence the behaviour of target audiences, including perpetrators of family violence and their influencers. The programme is based on research into attitudes towards family violence and motivators and barriers to behaviour change. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 2.6.5 | Administering two further rounds of the Community Action Fund to support local projects to support change at a local level. Mid 2008 and early 2009. |  | April 2009 |  | Third round complete. Fourth round opened for applications in November 2008 and will close March 2009. (NB: Key milestone date changed to reflect completion of the fourth round). |
| 2.6.6 | Continue to support the messages of the television campaign during 2008/09 using the website, the 0800 information line and print resources. |  | June 2009 |  | On track. The website continues to maintain a high number of visits, with more questions put to “Ask Vic” and “Ask Jude”. Resources continued to be distributed. |
| 2.6.7 | Continue a television advertising campaign addressing attitudes to family violence and intimate partners violence during 2008/09 – five weeks of advertising to be run. |  | 12 June 2009 |  | On track. The ‘It’s not OK’ adverts we aired in December 2008 and January 2009. |
| 2.6.8 | Continue to build on the media advocacy work with the national news media to promote more responsible coverage of stories of family violence and provide training and support to enable community spokespeople to engage effectively with local media |  | 12 June 2009 |  | On track. Media training workshops were held for some Police family violence coordinators and community agency representatives. Media support was also provided for White Ribbon Day. |
| 2.6.9 | Continue to identify and encourage campaign ‘champions’ and spokespeople, to develop partnerships in business, sport and youth related organisations and to continue to seek opportunities for promotion within popular culture. |  | 12 June 2009 |  | On track. Relationships with national and regional sports teams continued to grow, as did working with local government. |
| 2.6.10 | Continue to measure the level of public awareness of the key messages of the Changing Attitudes and Behaviours Campaign. |  | 30 June 2009 |  | #### On track. #### Findings from the third Reach and Retention survey (undertaken in September 2008) show that objectives were met. |
| Background The Campaign for Action on Family Violence (the Campaign) is a four year campaign that calls on everyone to help put an end to family violence in New Zealand. The national campaign was launched with TV advertisements in September 2007. The Campaign message “Family violence – It’s not OK” has struck a chord with New Zealanders and has quickly become part of the kiwi vernacular. The Campaign is supported by a website, an 0800 Information Line and a Community Action Fund (CAF) that provides financial support for community-led activities. Progress to date (previous 3 months work) - There were 23,327 visits to the Campaign website in the months October-December, and 899 calls to the Family Violence Information Line. The website continued to be maintained and updated, and in December saw an increase in the number of questions put to “Ask Vic” and “Ask Jude” and the addition of a calendar. - A total of 70,134 print resources were distributed throughout the 3-month period. - The ‘It’s not OK’ Campaign TV ads (Vic and Alfred) were on air in the week of 14-21 December, acknowledging that this is a stressful time for families and is historically associated with an increased reporting of family violence. - The Family Violence Information Line saw a two-fold increase in the number of calls during the week the adverts showed (compared to the previous week). - Media training workshops were held with Police family violence coordinators in Auckland (October) and Hamilton (November), and community agency representatives in Wellington (October). Media support was provided to White Ribbon Day events and the team worked with family violence networks to prepare for news media opportunities throughout the Christmas and holiday season. - The Campaign is continuing to grow relationships with sports teams – including the Breakers, the Hurricanes and Lions rugby teams and Touch Rugby NZ. The Campaign team is working with the Breakers to develop school resources and to promote Campaign messages through the Breakers radio spots. - Relationships are also continuing to be developed with local government – including Rotorua, Waitakere, Tararua and Hamilton Councils – Hamilton is running a localised ‘It’s not OK’ campaign through December and January. Reach and retention survey results Findings from the third Reach and Retention survey (undertaken in September 2008) show that media objectives were met. - Recall of at least one of the advertisements was at 95%, up from 87 % in the 2nd survey (visibility). - Overall the Campaign has two-thirds of the population aged 18 to 49 years acknowledging that they are thinking more about family violence (understanding and relevance), and two-thirds feel the advertisements have helped them to understand more about behaviours we should not tolerate (understanding and relevance). - There is very good understanding of how perpetrators can be motivated to change. #### The great majority felt the advertisements gave the impression of a potentially better life for perpetrators (91%) #### Among Pacific women it was felt by virtually all (95%). - Likewise, there is good understanding that change is possible, 88%. #### Also felt by virtually all Mäori women 95%, Mäori men 95%, and Pacific women 95%. Current ongoing work (next 3 months) - Libraries tour - Super Mäori Fullas Waitangi Day (6 February) will see the start of an 18 day nationwide motorcycle tour by the Super Mäori Fullas promoting the Campaign. Super Mäori Fullas are four Harley Davidson riding brothers who will be promoting the family violence message. They will attend community events organised by the Campaign's community action fund participants, distribute Campaign resources and undertake media interviews coordinated by the Campaign team. The brothers will be discussing the positive ways Mäori men can interact with partners and whänau. The tour starts at Cape Reinga, travels the length of New Zealand to Bluff and then back to the brothers’ home in Kaitaia. Sir Paul Reeves is patron of the SMF Trust and entertainer Pio Terei will be lending his support to the tour. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

### Ensuring Safety and Accountability

| ### 3.1 FAMILY VIOLENCE COURTS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Judiciary / Ministry of Justice |  |
| Contributors |  |  |  | Police, NGOs |  |
| Taskforce Liaison |  |  |  | Justine Cornwall |  |
| Project Manager |  |  |  | Karyn McLean/Dominic Lepa |  |
| First Programme of Action reference |  |  |  | Action 56 |  |
| Objective and actions (as per Work Programme) Two new Family Violence Courts established. Actions include: - project planning - identification of locations - stakeholder consultation - implementation. |  |  |  |  |  |
| Objective deadline |  | A variation was sought to extend this deadline to April 2009. This variation date will be overtaken as the second Family Violence Court will be operational by April 2009. |  |  |  |
| Purpose To ensure all parties are prepared ahead of the implementation to support new Family Violence Courts being established. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 3.1.3 | Stakeholder consultation |  | Sept 2008 |  | A variation has been submitted to allow for the new timeframe for the Whangarei Family Violence Court opening in April 2009. The Palmerston North court has been operational since 12 September 2008. |
| 3.1.4 | Communications strategy |  | Early 2009 |  | A variation was sought in July 2008 to delay the communications strategy to allow for the implementation of new courts. |
| 3.1.5 | Implementation of two new Family Violence Courts |  | April 2009 |  | The Palmerston North Family Violence Court became operational on 12 September 2008. A Variation was sought in July 2008 regarding the opening of the Whangarei Court moving to April 2009 and Palmerston North to September 2008. |
| Progress to date (previous 3 months work) The Palmerston North Family Violence Court was implemented in September 2008. The Whangarei Family Violence Court is due to follow in April 2009 and a training date has been confirmed for February 2009. Current ongoing work (next 3 months) Planning for the opening of the Whangarei Family Violence Court in early 2009 continues, and a training date has been confirmed for February 2009. Timing / Ongoing / Recommendations / Conclusions Status = on track (Whangarei Family Violence Court) = complete (Palmerston North Family Violence Court). |  |  |  |  |  |

| ### 3.3 SOCIAL SERVICES SUPPORTING COURTS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development / Ministry of Justice |  |
| Contributors |  |  |  | Police, MWA, NGOs, ACC |  |
| Project Manager |  |  |  | Anne Riley / Justine Cornwall |  |
| First Programme of Action reference |  |  |  | Action 52 |  |
| Objective and actions (as per Work Programme) A social services system modelled around family violence courts to support the courts by linking services to ensure victims and observers are kept safe, perpetrators are kept accountable and responsible, and families are assisted with their recovery needs. Actions include: - introduction of Independent Victim Advocate / support person role in all Family Violence Courts - introduce specialist enhanced case management staff in all Family Violence Courts - referral and funding for non-mandated stopping violence programme providers for offenders. |  |  |  |  |  |
| Objective deadline |  | April 2009 |  |  |  |
| Purpose A social services system modelled around family violence courts to support the courts by linking services to ensure victims and observers are kept safe, perpetrators are kept accountable and responsible, and families are assisted with their recovery needs. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 3.3.2 | Scoping and developing Family Violence Court Community Service (FVCCS), formerly called Independent Victim Advocate (IVA). |  | March 2009 |  | Scoping and development of the FVCCS has been underway since July. There has been some delay in the consultation with NGOs, Judiciary, and key stakeholders, which will now be completed by the end of January/early February 2009 with a view to signing-off the role and framework for a collaboration protocol, by March (milestone date adapted to reflect this date, was Dec 2008). |
| 3.3.3 | Introduce specialist enhanced case management staff in all Family Violence Courts (FVCs) |  | TBC |  | MoJ is currently assessing other funding streams to fund this initiative. This work is ongoing. No completion date confirmed as yet. |
| 3.3.5 | Consultation with other agencies and non-government organisations on the development of the role of the FVCCS |  | Feb 2009 |  | The Ministry of Justice ran two workshops with NGOs in August and November, to discuss the FVCCS role description. NGOs have also worked with MoJ, the Chief District Court Judge, Police and MSD in drafting a framework for a collaboration protocol. A set of guiding principles and a process map will be developed with the work commencing in February 2009. The development of guiding principles and a process map has been extended until March 2009. A collaboration protocol will outline the roles and responsibilities of the FVCCS, Police Prosecutor, and Victim Advisor in the provision of victim information to the Court. This framework will be developed at the local level once contracts have been awarded to NGO service providers. The milestone date has been adapted to reflect the planned completion date. |
| 3.3.6 | The FVCCS will be rolled out in FVCs. |  | From Sept 2009 |  | MSD will manage the selection process for the organisations to tender for the FVCCS. It is expected that the contracts for organisations to provide the FVCCS will be signed off in September 2009, and FVCCS recruited and trained by the end of 2009. The milestone date has been changed from July 2009 to reflect the delay due to the development of a framework for a collaboration protocol as outlined in 3.3.5. |
| Background A variation to this Objective was approved by the Chair of the Taskforce on 4 April 2008. The variation was sought because the previous deliverables and milestones did not align with the direction the Chief District Court Judge has set for the Family Violence Courts (FVCs). The former Government announced that it would move towards fully funding actions 1 and 3 of this Objective from 2008/2009 (Introduction of Independent Victim Advocate/support person role in all FVCs, and referral and funding for non-mandated stopping violence programme providers for offenders). Progress to date (previous 3 months work) - Consultation with other agencies, NGOs, and the Judiciary took place from August to December 2008. In mid-November, discussions took place with NGOs, Police, MSD and key stakeholders to finalise the role description and develop a framework for a protocol. The protocol will outline the roles and responsibilities of the FVCCS, Police Prosecutor, and Victim Advisor in the provision of victim information to the Court. - The role description for the FVCCS has been completed. Finalisation and sign off will be sought once national guiding principles and a process map have been completed. Current ongoing work (next 3 months) - The management of the selection process, including preparing documentation, for the provider(s) that will recruit and train the eight FVCCS. - Development of the framework for a collaboration protocol has been delayed. A meeting has been set for February 2008 for NGO members of the Taskforce to meet with the Ministry of Justice, MSD, and NZ Police to progress the finalisation of the FVCCS role. At this meeting work will commence on developing national guiding principles and a process map to sit alongside the role description. The process map will detail the entry points for the process of information sharing between agencies in the FVC. The guiding principles and the process map will be incorporated into the MoJ National Operating Guidelines for FVCs. The three Government agencies consider that collaborative protocols are more effective if they are developed at a local level within each Family Violence Court in order to reflect the local relationships between Courts, Police and NGOs. The proposed process, after the national guiding principles and the process map have been completed in collaboration with Taskforce NGOs, is that the collaborative protocol will be developed once contracts had been set in place for the service to be delivered in the FVCs. - Recruiting for the FVCCS role has been delayed until the guiding principles and process map have been developed and agreed to. Timing / Ongoing / Recommendations / Conclusions Status = delayed. Further information on the progression of this project will be provided following further discussions with key agencies and NGOs. |  |  |  |  |  |

### Effective Support Services

| ### 4.1 MĀORI SERVICE WORKFORCE DEVELOPMENT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Social Development |  |  |
| Contributors |  |  | TPK, NGOs, MinEdu |  |  |
| Project Manager |  |  | Ann Dysart |  |  |
| First Programme of Action reference |  |  | Action 7 |  |  |
| Objective and actions (as per Work Programme) Mäori Service Workforce Development. Actions include: - 60 Mäori trained to work with the Mauriora framework - ongoing support of trained practitioners. |  |  |  |  |  |
| Objective deadline |  | June 2009 |  |  |  |
| Purpose This proposal will allow for continued investment in the training and support of practitioners who work with Mäori whänau/communities where there is violence. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 4.1.6 | Ongoing assessment and further training, including assisting Mauri Ora practitioners to meet annual licensing and supervision requirements (follows 4.1.3). |  |  | Dec 2008 | Complete. Training underway. |
| 4.1.7 | Training modules completed (follows 4.1.4). |  |  | Nov 2008 | Complete. |
| 4.1.8 | Development of supervision systems (follows 4.1.5). |  |  | Dec 2008 | Complete. Training now underway. |
| 4.1.9 | Cross Credit Whänau Ora Training to a Diploma in Social Work. |  |  | May 2009 | Currently have one PTE recognising prior learning, working toward wider PTE acceptance. Due date has been brought forward. |
| 4.1.10 | Development of a new Leaders’ Strategy aimed at programmes for rangatahi. |  |  | Dec 2008 | Complete and has been included in Te Korowai Aroha O Aotearoa’s plan for 2009. |
| 4.1.11 | Develop strategy for attendance on Mauri Ora Training to meet high demand for placement. |  |  | April 2009 | Finalise and have placement issues consolidated / completed. |
| 4.1.12 | Ensure expansion into identified areas is seamless. |  |  | March 2009 | Ensure expansion is completed. |
| Progress to date (previous 3 months work) - Funding was successfully negotiated for another round of training. - Anamata (a Private Training Establishment in Whakatane) had 25 Mauri Ora practitioners applying for recognition of prior learning (RPL) for their Diploma of Social Services which will constitute 2/3 of their Degree in Social Work. Current ongoing work (next 3 months) - Due to high demand to attend Mauri Ora training programmes a waiting list for programmes is to be developed. - Expansion of the programme into the areas of: Mataatua; Bay of Plenty and Taamaki Makaurau-Auckland Central. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 4.2 PACIFIC SERVICE WORKFORCE DEVELOPMENT |  |  |  |  |
| --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Social Development |  |
| Contributors |  |  | MPIA, NGOs, MinEdu |  |
| Project Manager |  |  | Richard Joblin |  |
| First Programme of Action reference |  |  | Action 7 |  |
| Objective and actions (as per Work Programme) Variation to adjust Objective about to be submitted. Pacific Service Workforce Development. Actions include: - preparation of a project plan to guide workforce training and development in family violence services for Pacific families - developing a long-term approach to NGO provider capability building under the Pathway to Partnership plan. This approach will support the development of Pacific family violence social service providers and workforce. |  |  |  |  |
| Objective deadline |  | July 2008 (Variation to change deadline about to be submitted) |  |  |
| Purpose This work plans to increase the quality and diversity of services working to eliminate family violence in the Pacific communities. This will include identifying the capacity and capability of this workforce and the avenues needed to further build and support Pacific People in working to stop family violence in Pacific Families. |  |  |  |  |
| Key Milestones |  |  | Date | Description of Progress |
| 4.2.1 | Project plan developed under Pathway to Partnership (P2P) to address building provider workforce capability and capacity. This will include the development of the Pacific workforce. |  | July 2008 | Complete. However, on 8 August 2008 the then Minister for Social Development and Employment considered a report on strengthening collaborative action under P2P. The Minister agreed to the development of a longer-term investment approach to provider capability building by March 2009. |
| 4.2.2 | The project plan on development of the Pacific workforce developed within the P2P plan to further develop the NGO social services sector. |  | April 2009 | On track. |
| New Action added Note that an additional action has been added to this Objective. The initial action was completed in July 2008. However, the P2P Steering Group decided that funding should be reallocated to accelerate the move of essential services to full funding. Subsequently the then Minister for Social Development and Employment agreed to a longer-term investment approach to provider and workforce capability building being developed by March 2009. Pacific NGO provider and workforce development has been included in this longer-term approach. The new additional action reflects this work. Background Pacific service workforce development is now incorporated under the P2P plan on a work-stream to address providers’ ability to build workforce capability and capacity. A Steering Group made up of representatives from community-based organisations have overseen the development of the P2P plan. A representative from the Pacific Advisory Group (PAG) is on this steering group. A variation to this Objective is in the submission process. Current ongoing work (next 3 months) - Work has begun on reviewing the current investment in NGO capacity and capability and on developing an investment framework for 2009 onwards that includes existing and new funding. Pacific Service Work Force Development in Family Violence will be part of this. Timing / Ongoing / Recommendations / Conclusions Status = delayed. Variation to change deadline about to be submitted. |  |  |  |  |

# First Programme of Action update

Summary Analysis

The Taskforce for Action on Violence within Families’ (the Taskforce) first programme of action initially consisted of 76 actions which were developed from the Taskforce’s First Report. This was consolidated to 53 actions.

Of these 53 actions, 29 are complete. Work has commenced on another 15 actions and these are now either ongoing, business as usual, or are annual events. The remaining nine actions have been subsumed into the Ongoing Programme of Action and, along with other ongoing work, are now reported on and monitored through the regular Monitoring Reports provided to every Taskforce meeting.

Key to ‘Status’ column

Complete = Action complete. May have informed development of work in Ongoing Programme of Action.

OPOA = Work in these actions has been incorporated into the Ongoing Programme of Action, refer to Objective number.

Ongoing or Annual = Initial stage complete, currently Ongoing or business as usual. Some are Annual occurrences.

| # | Action | Agency | Information | OPOA # | Status |
| --- | --- | --- | --- | --- | --- |
| Leadership |  |  |  |  |  |
| 1 | Developing the next Programme of Action (POA) | All TF | OPOA released Feb 2008 | 1.1 | Complete |
| 3 | Successful implementation of POA | All TF | Incorporated into OPOA | 1.1 & 1.1a | Complete, ongoing reporting |
| 7 | Drawing on Mäori and Pacific advisory groups | MSD | Representatives on Taskforce (TF), ongoing MRG and PAG meetings advise the TF. | Led to 1.2, 1.3, 1.6, 1.9, 1.10, 2.4, 4.1, 4.2 | OPOA |
| 8 | Incorporating migrant and refugee perspectives | MSD | Informed OPOA. Research in OPOA. | 1.11 | OPOA |
| 9 | Aligning business planning to reflect Taskforce vision | Sec. | Next round of SOIs to be monitored. | 1.1 | Annual Ongoing |
| 12 | Maintain overview of government strategies to ensure goals and activities are complementary with our work | All TF | Business as usual. Secretariat watching brief to ensure TF are aware of all relevant govt strategies. All TF agencies info share on new strategies, and maintain overview of relevant govt strategies. | 2.1 2.3 | Complete to date, Ongoing |
| 13 | Family Violence research strategy | FC | Initial report provided Oct 2007. Ongoing work being done in consultation with other research agendas. | Informs 1.9-1.12 Led to 1.13 NGO data | Ongoing |
| 14 | Monitoring the level of family violence in NZ | FC | Refer to Research Strategy, Action 13. | Led to 1.13 & 1.7 | Ongoing |
| 15 | Horizontal learning | MSD | Incorporated into OPOA. | 1.7 | OPOA |
| 19 | Evaluate the first POA | MSD | Ongoing actions from POA will be monitored through regular Monitoring Reports. | 1.1a | Complete |
| 21 | Families Commission research programme | FC | 3 year research complete 21a Improving Family Violence surveillance data 21b Elder abuse and neglect research – released Feb 2008 | Informed OPOA | Complete |
| 22 | ACC research programme | ACC | 22a Sensitive claims 22b Effectiveness evaluation 22c Whänau Ora research - ongoing 22d Evidence based guidelines. |  | Complete 22c only is Ongoing |
| Changing attitudes and behaviour |  |  |  |  |  |
| 23 | Review violence in media | FC | Informed development of 2.5 | 2.5 | Complete |
| 29 | Using research to guide Campaign strategy | MSD | The Campaign continues to 2010, with further development being guided by research and evaluation | 2.6 | OPOA |
| 35 | Campaign strategy | MSD / FC | As above | 2.6 | OPOA |
| 36 | Mass media campaign | MSD / FC | Phase one started Sept 2007, Phase two started Feb 2008. Both phase adverts repeated in 2008 and early 2009. | 2.6 | OPOA |
| 37 | Nurturing leaders… | MSD | Business as usual. Identified (and funded) through the Community Action Fund. | 2.6 | OPOA |
| 38 | Partnerships with NGOs | MSD/ FC | NGO groups are contracted to be funded for services. | P2P | Ongoing |
| 39 | Community Action Fund | MSD | 97 initiatives funded in first three rounds. Fourth round open. | 2.6 | OPOA |
| 40 | Building knowledge – media advocacy etc | MSD/ FC | 40a media advocacy - FACS 40b FV awareness training – also led to 1.5 40c Toolkit re-released 40d White Ribbon day | 2.6 2.6 1.5 2.6 - | OPOA Ongoing Ongoing Complete Annual |
| 4142 | Family violence death reviews | MoH | Family Violence Death Review Committee established. | 2.7 | OPOA |
| Ensuring Safety and Accountability |  |  |  |  |  |
| 43 | Sharing information in a way that promotes safety and wellbeing | Previously MoJ | The Law Commission and the Privacy Commissioner are exploring approaches to the issue of government information sharing. The Law Commission is due to release an issues paper in the first half of 2009. |  | Initial work complete, Ongoing |
| 44 | Family Violence victims know what support and services are available | MoJ | Comms material developed and distributed. Available on Family Court website. |  | Complete |
| 45 | Maximising safety factors when managing court rosters | MoJ | Security policy complete, sent to all courts as a circular on 1 April 2008. |  | Complete |
| 46 | Increased thresholds for legal aid eligibility | MoJ | Thresholds increased. New legal aid regulations in force from Mar 2007. |  | Complete |
| 47 | Begin a review of legal aid remuneration rates | LSA | Review complete. Changes recommended. Budget 2008 approved 10% increase for 2008/2009. |  | Complete |
| 48 | Improving information courts provide about legal aid | MoJ | Info updated and provided in court info packs and in DV packs, Dec 2007. Court staff also provided with info for public enquiries. |  | Complete |
| 49 | Testing fixed fees for legal aid | MoJ / LSA | Testing complete. Three things were tested – fixed fees, the removal of prior approval requirements for standard family grants and proforma invoices. The removal of prior approval was implemented in October 2008 alongside revised family steps and disbursements. Fixed fees and proforma invoices are on hold. |  | Complete |
| 50 | Building safe and effective programmes for couples and families | MSD / MoJ | Service specifications set. MoJ in consultation with NZ Assoc of Counsellors, timeframes to be set. |  | Ongoing |
| 51 | Build capacity of interpreters in Courts | MSD / MoJ | More interpreters available in courts. Business as usual to continue building availability. |  | Complete |
| 52 | Investigate introduction of advocates in courts | MWA / MoJ / MSD | Investigation completed by MWA. Refer OPOA Objective 3.3 for further work. | 3.3 | Complete |
| 53 | Enhanced ability for courts to contact victims directly | MoJ / Police | Already possible, MoJ and Police will continue improving standardised process for CSV1 compliance and referral. |  | Complete |
| 54 | Review purchasing plans for programmes | MoJ | Reviewed. 2008 tender round complete. |  | Complete |
| 55 | Improve process for prosecutions for non-attendance at programmes | MoJ / Police | Memorandum of understanding between MoJ and Police for the transfer of prosecutions to Police signed. Transfer completed in June 2008. |  | Complete |
| 56 | Establish four additional Family Violence Courts | Judiciary / MoJ | Four established. Another established in Palmerston North in Sept 2008, one more due to open in early 2009 in Whangarei. | 3.1 | Complete |
| 57 | Family Violence Courts Evaluation | MoJ | Waitakere and Manukau evaluation complete. Released August 2008. | 3.2 | Complete |
| 58 | Forum to identify best practice for information exchange | MoJ | Held March 2007. Best practice ideas generated informed development of guidelines by agencies. |  | Complete |
| 60 | Enforcement of protection orders (POs) – police training, performance measures and policies | Police | Initiatives on addressing family violence “big picture” (which include PO’s) complete. Ongoing work continuing. 60a Training 60b Performance measures 60c National investigation and prosecution policies. Protection Orders research response also monitors this work, next report due to Minister early 2009. | Many & 4.4 | Complete. Ongoing work |
| 61 | Support and training for lawyers working in family violence-related areas | Judge Boshier | Workshops for FC lawyers done in 2007, Law Soc also produced a resource booklet. Similar training is likely to be ongoing. |  | Complete |
| 62 | Define options to improve information sharing between agencies and the Courts | MoJ | Information sharing already occurs between the Family Court and the District Court. Background papers and process maps have been drafted for internal review. Consultation with external stakeholders was planned for Nov/Dec 08. The project has been put on hold while MoJ responds to the Government’s priorities under the first 100 Days action plan. |  | First stage complete Ongoing 2008 & beyond |
| 63 | Simplify application forms for Protection orders | MoJ | An explanatory leaflet has been produced and is available online. Simplifying the protection order forms is ongoing and will be undertaken when a review of the Domestic Violence Act’s Rules and Regulations is undertaken. The review is subject to ministerial priorities and direction. |  | Form complete. Simplifying forms is ongoing. |
| 64 | Improve the use of security resources available to courts | MoJ | MoJ is currently preparing another new initiative bid for additional resources. It will also be reviewing how it uses existing resources to ensure it is getting best value for money. MoJ accords DVA hearings the highest priority for allocating security resources and will continue to do so. |  | First stage complete, Ongoing 2008 & beyond. Subject to Ministerial Budget priorities. |
| 65 | Consider an office to provide DVA-specific legal services | LSA MoJ | Currently developing objective and milestones as part of business planning. |  | Ongoing 2008 & beyond |
| 66 | Determine level of attendance and performance of perpetrators at programmes | MoJ | A report into the findings was completed on 30 September 2008 The report summarised data collected from a sample of Family Courts and provides an indication of attendance of respondents at stopping violence programmes. The results will be fed into Action 67. |  | Complete |
| 67 | Develop options to ensure perpetrators attend and complete programmes | MoJ | Further phase of Action 66. Options are currently being considered. This work is ongoing but has been put on hold while MoJ responds to the Government’s priorities under the first 100 Days action plan. |  | Ongoing 2008/2009 & beyond |
| 68 | Information for perpetrators on programmes | Police | Information distributed |  | Complete |
| 70 | Ensure the range of programmes matches the profiles of perpetrators | Corrections / MoJ | Options to potentially address gaps in programmes for prisoners with DV-related offences formulated. Corrections currently analysing these options. |  | Ongoing 2007/2008 & beyond |
| 71 | Local Case Collaboration (FVIARS) | CYF / Police | FVIARS nationwide roll-out complete. | Informs 3.3 | Phase one complete, Ongoing 2008 & beyond |
| Effective Support Services |  |  |  |  |  |
| 72 | Govt investing $9 million over the next four years | MSD | 2006/2007 contracts and funding took place. Continued funding of contracts from baseline. |  | Dev. Complete Ongoing to 09/10 |
| 73 | Develop new funding model | MSD | Pathway to Partnership (P2P) developed and ongoing. $20.4 million allocated in 2007. $446 million announced 12 Feb 2008 to fund essential NGO child and family services. | 2.1/4.2 | Complete OPOA |
| 74 | Cost family violence and family support services | MSD | Costing tool developed as part of P2P as above. |  | Complete |
| 75 | Build on existing workforce and organisational development initiatives | MSD | P2P Funding announced on 12 Feb 2008 to build a sustainable NGO sector. Ongoing. | 2.1/4.2 | Dev. complete. Ongoing 2008 & beyond |
| 76 | Continue to promote the use of integrated contracts | MSD | Funding for Outcomes developed and implemented. These contracts now part of FACS core business under the Integrated Contracts team. |  | Complete |

# How this report works

The Ongoing Programme of Action Monitoring Report is organised into two sections:

- A summary section – which provides an overview of the key highlights over the previous two months, and identifies the hotspots that need to be monitored closely over the upcoming two months to ensure Objectives remain on track.

- A monitoring report section – which includes two key parts:

    - Summary information from the project plans for each Objective.

    - A summary of the progress of each Objective over the last three months and an overview of the work that is expected to occur over the next three months.

The Taskforce’s planning and reporting hierarchy consists of the following:

- Objectives – specific work that has been signalled in the programme of action

- Actions –  specific work signalled in the programme of action, as part of an Objective and/or in the Taskforce’s work programme which sits beneath the programme of action

- Key Milestones – taken from individual agency project plans.

We have also introduced a formal variation process, which aims to:

- maintain the integrity of the Taskforce’s programme of action

- ensure there is transparent communication within the Taskforce about changes to Objectives and/or actions

- ensure the Objective and actions remain relevant to the Taskforce and its priorities.

A formal variation is required when a Taskforce agency wants to change an Objective, action or both. Formal variations are not currently required to change key milestones. However, any key milestone changes must be provided to the Secretariat so that a log can be kept and changes can be tracked over time.

The variation template is attached to this report. An electronic copy can be obtained from the Taskforce Secretariat.

Reporting frequency

Ongoing Programme of Action Monitoring Reports will be produced for each Taskforce meeting. If a Taskforce meeting is changed to a workshop then a report will still be produced but will be circulated in hard copy only.

Other information

- The information in the monitoring report centres on the key milestone information provided by each Taskforce agency.

- To ensure the monitoring report remains current, as each milestone is reported complete it will be dropped from the report. The Secretariat will keep a record of all milestones so that this information can be used at a later date, if necessary.

| To | The Taskforce for Action on Violence within Families | Date |  |
| --- | --- | --- | --- |
| From |  |  |  |
| Security Level | In Confidence |  |  |
| Variation: request to amend Work Programme Objective |  |  |  |
| Action | For your approval |  |  |

I am seeking the Taskforce’s approval to change an Objective or action from the work programme for the Taskforce for Action on Violence within Families.

Current Deliverable:

[Insert Project / Work Programme Objective and/or Action]

[Insert current milestone/s (from project plan template)]

Changed to:

[Insert Project / Work Programme Objective and/or Action]

[Insert new milestone/s (also complete new project plan template)]

Reasons for a Variation Request

A variation to this deliverable has become necessary as:

- [please insert reason/s for variation]

Consultation

In seeking a variation to this deliverable, I have consulted and gained agreement from the following people:

| Name | Position and organisation |
| --- | --- |

Impact

The impacts in agreeing to this change are:

- [add details of any impact such as reporting to Cabinet, other key project timeframes, budget initiatives, reputation, legislation.]

The impacts in not agreeing to this change are:

- [add details of any impact such as reporting to Cabinet, other key project timeframes, budget initiatives, reputation, legislation.]

Recommendation

It is recommended that you:

- agree to a variation to an Objective or action found in the Taskforce’s work programme

[Insert Project / Work Programme Objective and/or Action]

[Insert new milestone/s (also complete new project template)]

Approve / Decline

| Xxxxx (Taskforce representative) |  |  |
| --- | --- | --- |
| XXXXX (Taskforce agency) |  | Date |

| Peter Hughes |  |  |
| --- | --- | --- |
| Chair |  | Date |
| Approved  Not Approved  |  |  |

Note that the Inter-agency Plan references establishing an intensive, comprehensive behavioural service for 3 -7 year olds, while the ongoing work programme discusses delivery to 3-8 year olds.