Ongoing Programme of Action

Monitoring Report

May 2008

Prepared by the Secretariat for the Taskforce for Action on Violence within Families

# Contents

Contents	0

Summary	3

Highlights	3

Leadership	3

Changing Attitudes and Behaviour	4

Ensuring Safety and Accountability	4

Effective Support Services	5

Hotspots	7

Variations	7

Alerts	7

Monitoring Report	9

Three month summaries	11

Leadership	11

Changing Attitudes and Behaviour	19

Ensuring Safety and Accountability	24

Effective Support Services	26

Detailed Milestone Updates	29

Leadership	29

Changing Attitudes and Behaviour	40

Ensuring Safety and Accountability	47

Effective Support Services	50

First Programme of Action traffic light report	53

How this report works	59

# Summary

- The Taskforce for Action on Violence within Families’ (the Taskforce) first programme of action initially consisted of 76 actions, which were consolidated to 53 actions. A progress summary on these actions is provided towards the end of this report.

- The Taskforce’s Ongoing Programme of Action (OPOA) consists of 31 objectives, which form the Taskforce’s work programme. To meet each objective, actions and milestones have been identified. This report provides a progress report against the objectives, actions and milestones.

- Any variation to objectives or actions requires a formal variation. A variation template must be completed and signed by the appropriate Taskforce member, and then forwarded to the Secretariat. The Secretariat will then forward it on to the Chair of Taskforce for approval. Completed variations are kept by the Secretariat for referral if required. For more information on this report, how it is organised and the formal variation process refer to the “How this report works” section at the end of the document.

Objective status

| Total number of objectives | 31 |
| --- | --- |
| On track | 26 |
| Variations | 1 pending (2 approved) |
| Alerts | 4 |

## Highlights

This section provides an overview and points of note for the reporting period of January 2008 to May 2008.

### Leadership

### Maori Programme of Action

- The Taskforce’s Mäori Reference Group (MRG) and the Ministry of Social Development are jointly leading development of a Mäori Programme of Action, which will form part of the Taskforce’s Ongoing Programme of Action.

The MRG facilitated a successful Family Violence Whanau Summit on 3-4 April 2008 in the Waikato. The Summit was hosted by Tainui and King Tuheitia, and brought together Mäori leaders to discuss the issues that affect whänau, to share current knowledge of issues and solutions, and to develop a plan for the future. The outcomes from the Summit will feed into the Regional Hui which are to be held around the country.

### Domestic Violence Act 1995 review

- The Ministry of Justice is currently reviewing the Domestic Violence Act 1995 (DVA) and related legislation.  Although not driven by the Taskforce, this review aligns closely with the Taskforce’s direction and impacts on much of the Taskforce’s work. The review focuses on matters that will improve the current law in achieving its objective of reducing and preventing violence in domestic relationships.

- Papers have been developed with policy proposals for amendments to the DVA and related legislation. The papers were considered by the Government on 21 May 2008.

- If proposals are approved it is anticipated that the Ministry will have legislation drafted and ready to be tabled in the House in July 2008.

### Changing Attitudes and Behaviour

### Campaign for Action on Family Violence

The second phase of the Campaign for Action on Family Violence was launched on 14 February 2008. The new advertisements, featuring four men telling their stories, went to air on 17 February 2008. The ads will be aired on TV for a further three weeks over the May-June period.

The 0800 information line and the website continue to have very high traffic since the launch of the second phase. To continue monitoring the effect of the Campaign, a second reach and retention survey took place in March and April 2008. The results of this most recent survey are consistent with the first survey at the end of 2007. Recall of the Campaign remained very high with 89% of the total sample recalling something from the Campaign, and 66% of those surveyed recalled seeing one or more of the TV advertisements from the second phase of the Campaign. Recall was high across all ethnic groups, but more so for Mäori males and Mäori females (79% and 76% respectively). Almost one in five (19%) of those who have seen the TV advertisements reported taking some action as a result of seeing the advertisements.

The third round of the Community Action Fund opened on 8 April. The closing date for applications is 10 June 2008.  Successful applicants will be announced by the end of July 2008. In addition to the general advice to applicants, this round of funding encourages applications on initiatives that create change in the community and make protecting children everyone’s business.

### Family Violence Death Reviews

In April, the Ministry of Health issued a call for nominations for the inaugural members of the Family Violence Death Review Committee. Nominations closed on 1 May 2008, and 59 applications were received.  The Minister of Health is currently considering the nominees. The Ministry plans to undertake the Cabinet appointments process during May and June to appoint members to the Committee. A written notice will be presented to the House of Representatives by the Minister of Health to establish the Committee (in late June 2008).

### Ensuring Safety and Accountability

### Family Violence Courts

National Operating Guidelines for Family Violence Courts have been developed.  The Guidelines have been considered by the Family Violence Courts Judges and approved by the Chief District Court Judge. The Guidelines went out for broader consultation on 21 April 2008 to key staff and stakeholders with feedback due 16 May 2008.

Following approval, the National Operating Guidelines will form the basis for DV Training which will be delivered to staff and key stakeholders at all Family Violence Courts by June 2008. Successful training will result in successful implementation of protocols in all Family Violence Courts prior to this date.

The locations and dates for implementation of the further two Family Violence Courts are yet to be confirmed. However, the Chief District Court Judge has indicated that Palmerston North and Whangarei are likely locations for new FV Courts to exist from September 2008.

### Social Services Supporting Family Violence Courts

The Independent Victim Advocate (IVA) role is currently being developed by the Ministry of Justice and Ministry of Social Development.  The IVA roles will be implemented in eight Family Violence Courts in April 2009.  The funding for non-mandated stopping violence programmes was funded under the Pathways to Partnership initiative in February 2008.  Internal funding streams for these programmes will be established and implemented in July 2008.  Funding for the specialist enhanced case management staff in all Family Violence Courts was not funded in the 2008 Budget round.  The Ministry of Justice are currently determining how these programmes can be met within existing baselines.

### Effective Support Services

### Pathway to Partnership

Pathway to Partnership is a multi-year plan to build strong, sustainable and more effective community-based services for families, children and young people. At its core is the strong, supportive working relationship between government and the community sector.

It recognises that community-based providers of services for children, young people and families play an essential role in supporting families, reducing family violence and making sure children and young people get the best start in life.

Over the next four years the Government is increasing its investment in these services by $446 million. This money will be progressively introduced from 1 July 2008, with an extra $52 million available in 2008/09. The funding increases to $192.8 million in 2011/12.

The funding is for existing services that currently have a contract with Family and Community Services, Child, Youth and Family, the Ministry of Youth Development, or parenting support services currently with the Ministry of Education that will transfer to the Ministry of Social Development on 1 July 2008. It is also for Ministry of Justice funded victim support and family violence perpetrator services.

Key elements of the Pathway to Partnership project are:

- moving existing essential family, child and youth focused services to full funding by 2011

- providing for annual cost adjustment payments

- addressing forecast volume increases

- focusing  more on achieving outcomes and less on inputs / programmes

- enabling providers to build workforce capability and capacity

- supporting NGOs to work more closely together to reduce duplication and get more resources into services.

Progress to date includes:

- Determining the cost pressure payment for all services – 3.4% from July 2008.

- Agreeing essential and grant funded service categories to inform implementation of full funding.

- Developing an approach to full funding for essential services, including a transition approach for 2008/09.

- In May and June 2008, community forums are being held across the country so social service providers can find out more about the Pathway to Partnership plan.

## Hotspots

This section highlights objectives that are subject to variation or have been identified as areas of risk. All objectives not mentioned in this section are on track to be completed as planned.

### Variations

Variations are formal requests for changes to objectives and/or actions in the Taskforce’s Ongoing Programme of Action.

| Objective | Title | Variation summary | Status |
| --- | --- | --- | --- |
| 1.10 | Pacific Research Agenda | Changes required to actions, although the objective will remain the same. Further development of the project plan has clarified actions required to achieve Taskforce objectives. | Variation due to be submitted before June 2008 Taskforce meeting. |
| 3.3 | Social Service Supporting Courts | The objective remains the same, with changes to the actions required. The variation was requested due to the need to align with the direction the Chief District Court Judge has set for the Family Violence Courts, and to ensure consistency with a 2008 Budget bid. | Approved 4 April 2008. |
| 2.4 | Curriculum development | Changes were required to actions, although not the objective. “Whole school strength based approaches” could not be extended due to an increase in costs for delivery of student wellbeing contracts. The use of this approach is being strengthened by incorporating successful professional learning approaches for student wellbeing in the design and delivery of ongoing professional development contracts. | Approved 28 March 2008. |

### Alerts

This table highlights areas that have been identified as at risk of not being delivered.

| Objective | Title | Issue | Mitigation |
| --- | --- | --- | --- |
| 1.1a | Mapping of the Ongoing Programme of Action | The objective and actions for this work need to be clarified. | The Secretariat will seek clarification from Taskforce members about this work. |
| 1.9 | Maori Research Agenda | There has been some delay to this project, this is related to the contractor engaged. | The completion date for this project has been delayed one month, from 30 June 2008 to 31 July 2008. |
| 2.2 | Improving Attachment | A variation may be required as the Auckland DHB has decided not to proceed with the pilot to prevent Shaken Baby Syndrome. Initial scoping highlighted issues with the pilot site. | The Ministry of Health has been approached to fund a regional pilot and is currently considering the possibility. |
| 4.2 | Pacific Service Workforce Development | This project plan is now part of development of Pathway to Partnership work on workforce provider capacity and capability. The project plan has not yet been finalised as the Pathway to Partnership project plan is currently being formulated after the funding announcement on 12 February 2008. | Pathway to Partnership project plan is currently being clarified and will be confirmed in July 2008. |

# Monitoring Report

The Three Month Summaries section provides an update on work undertaken in the previous three months and work which is upcoming in the next three months.

The Detailed Milestone Updates section outlines progress on each milestone in table format.

| # | Objective | Page |
| --- | --- | --- |
| 1.1 | Facilitation of the Ongoing Programme of Action | 11 and 29 |
| 1.1a | Mapping of the Ongoing Programme of Action | 11 and 29 |
| 1.2 | Mäori Programme of Action | 11 and 30 |
| 1.3 | Pacific Programme of Action | 12 and 30 |
| 1.4 | Addressing child maltreatment | 12 and 30 |
| 1.5 | Family Violence Free Workplaces | 13 and 31 |
| 1.6 | Iwi led crime prevention | 15 and 34 |
| 1.7 | Family Violence Clearinghouse | 15 and 35 |
| 1.8 | Case studies characterising good practice | 15 and 36 |
| 1.9 | Mäori research agenda | 16 and 36 |
| 1.10 | Pacific research agenda | 16 and 37 |
| 1.11 | New migrant and refugee research agenda | 17 and 37 |
| 1.12 | Elder abuse and neglect research agenda | 17 and 38 |
| 1.13 | Data on NGO service delivery | 18 and 39 |
| 2.1 | Kia Puawai | 19 and 40 |
| 2.2 | Improving attachment (new-born babies and parents and caregivers) | 19 and 40 |
| 2.3 | Conduct disorder/severe antisocial behaviour | 19 and 41 |
| 2.4 | Curriculum Development | 19 and 42 |
| 2.5 | Violence in the media | 21 and 43 |
| 2.6 | Campaign for Action on Family Violence | 21 and 44 |
| 2.7 | Ongoing action on the Family Violence Death Review project | 21 and 45 |
| 3.1 | Family Violence Courts | 24 and 47 |
| 3.2 | Family Violence Courts protocols | 24 and 47 |
| 3.3 | Social Services supporting Family Violence Courts | 24 and 48 |
| 4.1 | Mäori Service Workforce Development | 26 and 50 |
| 4.2 | Pacific Service Workforce Development | 26 and 50 |
| 4.3 | Service demand data | 26 and 51 |
| 4.4 | Training our staff | 27 and 51 |

## Three month summaries

This section provides background and updates on work undertaken in the previous three months and work planned for the upcoming three months.

### Leadership

1.1 Facilitation of the Ongoing Programme of Action (OPOA) Lead agencies: All agencies and the Secretariat

Progress to date (previous 3 months work) The April 2008 Monitoring Report sets out the new format and was included in meeting papers for the 9 April 2008 Taskforce meeting. Agencies were contacted to provide updates for this Monitoring Report (May 2008) which included any updates on ongoing actions from the First Report. Many of the actions from the First Report have been subsumed into objectives for the Ongoing Programme of Action. An interim update of the Waikato University research on Protection Orders was prepared, which will be sent to the Taskforce with the June 2008 papers. Current ongoing work (next 3 months) - Preparing the Monitoring Report for the 4 June 2008 meeting of the Taskforce. - Organising the agenda and the papers for the next Taskforce meeting and assisting in the organisation of the Ministerial Team and Multi-Party Group meetings. - Facilitating and writing of the Protection Orders report due to the Minister for Social Development and Employment at the end of August 2008. Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.1a Mapping of the Ongoing Programme of Action (OPOA) Lead agency: NGOs

Alert: Next steps to be confirmed.

1.2 Mäori Programme of Action (MPOA) Lead agency: The Mäori Reference Group and the Ministry of Social Development.

Background The Taskforce’s Mäori Reference Group (MRG) is developing a Mäori Programme of Action (MPOA). Progress to date (previous 3 months work) The Whanau Summit held over the period 3 – 4 April was successful in raising family violence awareness within Mäori leaders. To this end, the Chairman of Ngai Tahu, in collaboration with Tainui leaders, presented at their Iwi Leader’s forum the issue of family violence. As a result, 18 other Iwi have agreed to take the message back to their respective boards / Iwi. Regional Hui will be held over May and June, to reinforce the message on prevention of family violence, to disseminate the findings and outcomes of the Summit, and to gain input into the development of the MPOA. Current ongoing work (next 3 months) - Completion of the Regional Hui. - Development of the MPOA. Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.3 Pacific Programme of Action (PPOA) Lead agency: The Pacific Advisory Group / Ministry of Social Development

Progress to date (previous 3 months work) A draft Pacific POA, which includes a communications plan, has been developed. The document is still being circulated to stakeholders for comment. PAG provided advice on specific projects including the ‘It’s not OK’ campaign and the Pathways to Partnership project. Current ongoing work (next 3 months) A final draft of the Pacific POA is due for completion by end of June 2008. PAG is actively involved in ongoing projects within the OPOA including; leading information workshops with Pacific providers on the Pathways to Partnership project and advising on the implementation of identified Pacific related Changing Attitudes and Behaviour initiatives. Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.4 Child maltreatment Lead agency: Office of the Children’s Commissioner / Ministry of Social Development

Background The Ongoing Programme of Action, includes developing a work programme on child maltreatment (including child sexual abuse) that: - focuses on improving outcomes for children - takes account of the different types of child maltreatment - identifies priority areas where the Taskforce can make a difference. An overview paper on child sexual abuse that summarises the issue and current response was prepared for the Taskforce meeting in April 2008. Progress to date (previous 3 months work) - A briefing note was presented to the Taskforce seeking approval for a proposed structure and approach for developing the work programme on Child Maltreatment Prevention (CMP). Approval of the approach was given by the Taskforce at the 9 April 2008 meeting. - A CMP Working Group and an External Advisory Group is being set up. - The final version of the Child Sexual Abuse: An Overview of the Issue and Current Response was presented to the Taskforce for noting at the 9 April 2008 Taskforce meeting. Current ongoing work (next 3 months) - Establish and consult with an external Expert Advisory Group. - Develop a draft work programme for the Taskforce’s consideration by the end of June 2008. - Subject to Taskforce approval, begin to carry out the work programme. Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.5a Family Violence Free Workplaces Lead agency: Ministry of Social Development

Overall Context The current HR plan to support the goal of becoming a family violence free workplace involves a longitudinal approach founded on raising and maintaining staff awareness of family violence - the workplace impacts and supports. This work involves developing a family violence policy and initial support mechanisms (eg information and resources, and referral options through the Employee Assistance Programme provider). The next stages involve identifying and building further support mechanisms for staff and managers. Underpinning this work is the ongoing awareness raising initiatives which includes information sessions, posters, and “family violence” messages through Corporate communication channels. Consistent with Te Rito principles, MSD HR will also continue to enhance initiatives as information and better ways of working are identified. This will involve testing or piloting some initiatives (such as peer support groups) and information sharing across other Taskforce contributors (ACC and NZ Police). 1.5a.2 Policy development Background The purpose of the family violence policy is to raise awareness of the impact of family violence in the workplace and to provide and raise awareness of the support mechanisms for employees who are experiencing family violence, want assistance to help others, or want assistance to stop their violence. Progress to date (previous 3 months work) MSD has invited the PSA to review the draft policy, and subject to their input we will continue to progress the sign-off process. Current ongoing work (next 3 months) Progress the draft policy through the approval process and plan for its implementation. Timing / Ongoing / Recommendations / Conclusions Status = on track. 1.5a.3 Establish internal steering group to oversee Family Violence initiatives Completed – An internal Steering Group to guide the HR Family Violence initiatives has been established. Timing / Ongoing / Recommendations / Conclusions Status = Complete. 1.5a.4 Manager guidelines developed to support policy Progress to date (previous 3 months work) The Manager Guidelines have been developed as a companion resource to the family violence policy and will be implemented once the family violence policy has been approved. Current ongoing work (next 3 months) No further developments this quarter. Will be progressed in conjunction with 1.5a.2 Timing / Ongoing / Recommendations / Conclusions Status = on track. 1.5a.5 Regional information sessions Background The information sessions are part of the broader “family violence awareness raising” activities. Current ongoing work (next 3 months) - Exploring delivery options for family violence information sessions for regional staff. - Canvass demand and deliver regional sessions accordingly. This may link with 1.5a.7 (tools and resources) and the possible development of online resources. Timing / Ongoing / Recommendations / Conclusions Status = on track. 1.5a.6 Providing accessible information and resources Progress to date (previous 3 months work) Information and links are on the MSD intranet. Information on the Work and Income Peer Support Network (refer 1.5a.9) is also on the intranet. Family violence posters (from the Campaign) are displayed in the entrance way to the Bowen State building in National Office. Current ongoing work (next 3 months) A communication plan for 2008 is being developed, which will identify opportunities to raise awareness and maintain the profile of violence family-related initiatives. Timing / Ongoing / Recommendations / Conclusions Status = on track. 1.5a.7 Tools and resources Ongoing (long term) Still in earlier exploration stages – options for the development of web-based family violence resources for the workplace, with implementation in 2009. Timing / Ongoing / Recommendations / Conclusions Status = on track 1.5a.8 Training Progress to date (previous 3 months work) No specific training has taken place over the previous three months. Current ongoing work (next 3 months) Training will be planned and delivered subject to demand. Nothing currently confirmed. Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.5b Family Violence Free Workplaces Lead agency: ACC

Progress to date (previous 3 months work) A refresh launch of the FV policy and guidelines took place in February 2008. ACC continues to work with Preventing Violence in the Home (PVH) to adapt the tools used in training for human resources staff within the MSD so they are relevant for ACC. An initial half-day pilot training by PVH took place in early 2008, however this was found not to meet the needs of the organisation. An alternative provision for support has been identified and will be implemented in June. Current ongoing work (next 3 months) Continuing work on developing training for staff. This includes additional resource development. Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.5c Family Violence Free Workplaces Lead agency: NZ Police

Progress to date (previous 3 months work) - A meeting took place on 17 March 2008 with MSD to discuss the approach other agencies are using to progress work - collaborating and sharing where appropriate. Current ongoing work (next 3 months) - Continuing work on developing draft policy. Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.6 Iwi-led crime prevention Lead agencies: NZ Police

Progress to date (previous 3 months work) Police and Te Puni Kökiri have been supporting iwi with the necessary tools to develop and design their own Plans. The type of support provided includes: - providing Police intelligence to iwi groups that enable iwi to understand the crime problems and profiles of Mäori (offenders and victims) within their geographical areas. - providing specialised trained staff who are able to take iwi through a formal problem solving approach to crime prevention crime prevention methodology training in SARA and POP models - providing draft Iwi Crime Prevention Plan templates and Guidance Notes for preparation of the Iwi Plans - funding writers nominated by iwi to begin drafting iwi-specific crime prevention plans. Current ongoing work (next 3 months) Police are continuing to work with iwi in six Police districts (through individual workshops) to support them in "trailblazing" this work, while work continues across the remaining six Police districts with ongoing dialogue between Police and major iwi groups. Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.7 Family Violence Clearinghouse Lead agency: Ministry of Social Development

Progress to date (previous 3 months work) 1.7.1 - The contract for the provision for a Family Violence Clearinghouse for the 2007-2008 year has been approved and signed by MSD and the University of Canterbury. A further variation to the contract, providing for an additional two months services for the Clearinghouse, to 31 August 2008 has also been signed. Management and the NZFVC team are exploring options to provide an interim service to maintain the Clearinghouse while development of a new NZFVC takes place. 1.7.2 - Work has commenced on gathering requirements for a new NZFVC on the basis of bringing the IT operations for the NZFVC in-house to MSD. Development work will also include developing users needs and ideas around the look and feel of a new NZFVC Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.8 Case studies characterising good practice Lead agency: Ministry of Social Development

Background Current evaluative activities will be used to identify good practice models. The project will commence by drawing on one of the evaluative activities that support the Campaign for Action on Family Violence (the Campaign). The case studies will therefore focus on the practice of family violence prevention through social marketing. The aim of the evaluation project is to investigate and illustrate the impact of the Campaign on selected communities. It will focus on collecting information on observable and recorded changes relating to family violence over time in selected communities. As part of this evaluation two case studies will be produced that illustrate and explain “significant changes” arising from the Campaign. Progress to date (previous 3 months work) The communities for the study have been selected, and the project plan has been finalised. Current ongoing work (next 3 months) The data collection tools are currently being designed. Community researchers will be contracted. Fieldwork will be conducted. Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.9 Mäori Research Agenda Lead agency: Te Puni Kökiri

Background Te Puni Kōkiri is working to identify current information regarding family violence for Mäori, and looking at culturally distinct models of prevention and intervention for Mäori. It is expected that an agenda for research will emerge from this work. Progress to date (previous 3 months work) The scope of this project has been defined, and a stocktake of existing initiatives has been completed. There are three key outputs: Output One: A literature review intended to identify current information on Mäori family violence; information gaps; inconsistencies; and themes within the literature on family violence and Mäori. Output Two: A case study analysis of existing Mäori designed, developed and delivered initiatives that address family violence. Output Three: A summative report that analyses output one and two and identifies research priorities to form a Mäori Research Agenda. Consultation with other agencies has been completed. An external Reference Group to review the work is currently being established. Current ongoing work (next 3 months) A selection process to identify three providers of Māori designed, developed and delivered initiatives for the case study analysis has been completed. The work has been contracted and work on both the case study analysis and literature review is currently underway. Consultation with sector experts is ongoing. Timing / Ongoing / Recommendations / Conclusions Status = some delay [expected completion date of 31 July 2008, one month later than initially planned]

1.10 Pacific Research Agenda Lead agency: Ministry of Pacific Island Affairs (MPIA)

Background The Family Violence Research Agenda will sit within a Pacific Research Agenda. Progress to date (previous 3 months work) MPIA met with the Families Commission and MSD to discuss the development of a Pacific research agenda to ensure it is in line with the Family Violence Research Strategy, and complements to the Pacific Programme of Action. Project specifications have been finalised. Current ongoing work (next 3 months) The MPIA will continue to consult with PAG about what research on Pacific peoples and family violence is needed both now and in the future. A report will be developed which will outline the issues associated with Pacific family violence research and culminate in the development of Pacific family violence research priority topics. Timing / Ongoing / Recommendations / Conclusions Status = on track. Variation due to be submitted May 2008.

1.11 New Migrant and Refugee Research Agenda Lead agency: Ministry of Social Development

Progress to date (previous 3 months work) A draft literature review covering national and international literature relating to family violence within the refugee and migrant communities has been completed and is under review. Current ongoing work (next 3 months) An expert research group will be convened to review the document and conduct a gap analysis to illustrate how the existing literature covers the topics of interest for this project: - The nature of family violence in new migrant and refugee families - Successful models of prevention - Successful models of intervention A scoping paper outlining the completion of this project will be developed from that discussion. Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.12 Elder Abuse and Neglect Lead agency: Ministry of Social Development

Background 1.12.2 and 1.12.3 The research agenda on Elder Abuse and Neglect (EAN) will be informed by the environmental scan (see 1.12.4 below). 1.12.4 Following a joint Age Concern NZ/MSD presentation to the Taskforce in April 2006 on a proposed national action plan/strategy on EAN, MSD and Age Concern have commenced an environmental scan with the view to preparing an ongoing national programme of action on EAN Policy. Progress to date (previous 3 months work) - Cross-MSD reference group for EAN Policy established. - Draft environmental scan completed (Age Concern NZ and MSD). Current ongoing work (next 3 months) - Report to Minister seeking approval of a proposed work programme, timeline and governance arrangements for working towards developing a national action plan for elder abuse and neglect. - Complete consultation with sector on issues and priorities. - Report to Minister SDE and to FVT (for FVT October 2008 meeting) with recommended priorities for action. Timing / Ongoing / Recommendations / Conclusions Status = On track

1.13 Data on NGO Service Delivery Lead agency: Ministry of Social Development

Background The initiative to support a sustainable NGO social service sector (part of Pathway to Partnership) will roll-out a sustainable funding path for essential NGO services for families, children and young people. All essential Family Violence prevention services will be part of this initiative. As part of implementing this project, a data monitoring system that focuses on outcome measures will be developed in collaboration with the sector and implemented. This monitoring system will provide high quality data about service outcomes. Current ongoing work (next 3 months) Within the Pathway to Partnership Plan there is a workstream focused on monitoring and evaluation. One objective of this workstream is to develop a monitoring and reporting programme that ensures a reliable data stream including the ability to report on who has received what services and support and what difference these have made, i.e. outcomes. A confirmed monitoring and reporting plan is due by July 2008. Timing / Ongoing / Recommendations / Conclusions Status = on track.

### Changing Attitudes and Behaviour

2.1 Kia Puawai Lead agency: Ministry of Social Development

Progress to date (previous 3 months work) An early years budget package was developed in November 2007. This package was not funded in Budget 2008. Current ongoing work (next 3 months) The B4School pilot being progressed by the Ministry of Health will be in place by August 2008. Work has continued on evaluating four pilot programmes to improve outcomes for children and their families. This work will inform a report back to Cabinet on future funding decisions. Timing / Ongoing / Recommendations / Conclusions Status = on track.

2.2 Improving Attachment Lead agency: Ministry of Health

Alert: Not commenced as initial scoping highlighted issues with the pilot site. A new approach is currently being considered by Ministry of Health.

2.3 Conduct Disorder / Severe Anti-Social Behaviour Lead agency: Ministry of Social Development

Background This is an inter-agency project which seeks to improve behavioural interventions for 0-17 year olds across service areas of the Ministries of Education, Health, and Social Development (CYF). In particular, it will establish a comprehensive behavioural service for children aged 3-7 years. Progress to date (previous 3 months work) The Expert Advisory Group (EAG) had its first meeting on 14 November 2007 and has met four times in 2008 with a further meeting scheduled for 11 June 2008. Members of the EAG are progressing the best practice report which is on track for completion in June 2008. Current ongoing work (next 3 months) Agencies are finishing a stock-take of services and the EAG will write a second report: Translating Evidence into Practice. Timing / Ongoing / Recommendations / Conclusions Status = on track

2.4 Curriculum development Lead agency: Ministry of Education

Background In 2002, the Ministry of Education’s Curriculum Stocktake Report identified that, while many students were achieving at world-class levels, there are wide disparities in outcomes for diverse students. Progress to date (previous 3 months work) 2.4.1 The New Zealand Curriculum Since the launch of the New Zealand Curriculum in November 2007, a range of resources and supports have been made available to help schools implement the new curriculum and over 100 sector leaders have been selected to lead professional learning communities. The draft Te Marautanga o Aotearoa (Mäori Medium curriculum) was launched for consultation in November 2007. Since the launch, facilitators have conducted regional workshops with teaching staff, whänau and iwi groups during the consultation period which ended 18 April 2008. During May submissions are being analysed and recommendations will be included in the final document. We have met with more than 18 groups of principals around New Zealand to discuss the draft position paper, Kiwi Leadership for Principals. The written feedback to the draft position paper is currently being analysed and the results will contribute towards the development of a national Professional Leadership Strategy. 2.4.2 Whole-school, strengths-based approaches that promote resilience and confidence in children and young people Initial evaluation findings have been used to develop the practice of the agencies delivering the contract. Participating schools have been provided with a summary of the report and a summary of ‘strength-based approaches’. 2.4.3 Identifying and referring children affected by family violence to appropriate services MoE and CYF have consulted on and identified the key components for an education profile and plan for children in care. This work has included: identifying the process needed to establish an educational profile and plan; designing templates; developing privacy and information sharing protocols; and clarifying the roles and responsibilities of different agencies. Current ongoing work (next 3 months) 2.4.1 The New Zealand Curriculum Further resource packs for implementing the New Zealand Curriculum will be published in July 2008 and early 2009. We will complete the final document for Te Marautanga o Aotearoa and will develop second tier support materials to support the implementation of the curriculum. A draft of the Professional Leadership Strategy is planned to be released in August 2008. 2.4.2 Whole-school, strengths-based approaches that promote resilience and confidence in children and young people The Ministry, the national coordinator and facilitators will use progress to date the review the models used in the delivery of the Student Well-Being and Mental Health contracts. The strengths based approach used in this programme along with evidence from the Teacher Professional Learning and Best Evidence Synthesis Iteration will be used to strengthen the focus on improving outcomes for students and their families. 2.4.3 Identifying and referring children affected by family violence Guidelines and templates will be developed for early childhood services and schools to support the implementation of the education profile and plan. Timing / Ongoing / Recommendations / Conclusions Status = on track.

2.5 Violence in the Media Lead agency: Families Commission

Background Violence in the media and its impact on society generally was raised at the meeting with the Family Violence Ministerial Team and with members of the Mulri-Party Working Group on Family Violence, when the Taskforce’s First Report was presented in mid 2007. The first Programme of Action included an action to review how violence is portrayed in the media and in particular the 2004 Report on TV Violence in New Zealand, and advise on implications for the next Programme of Action. The Families Commission agreed to lead this work. The Taskforce supported raising awareness of the impact of violence within the media on children and young people. The 2004 report identified middle childhood (between 6- 11 years) as a vulnerable group and it was agreed that this group should be the initial focus of any public education work. Progress to date (previous 3 months work) The Broadcasting Standards Authority has recently released a report - Seen and Heard: Children’s Media Use, Exposure, and Response and reports the findings of a qualitative study of children’s use of electronic media, and the way parents and children mediate that use. The research involved interviewing more than 600 children aged between six and 13 and their primary caregivers. The focus of the research was how New Zealand children use and respond to television, radio, the internet, and cellphones. Work is underway to consider the implications of the research for this action. Current ongoing work (next 3 months) An advisory group will be convened and options will be developed. Timing / Ongoing / Recommendations / Conclusions Status = on track.

2.6 The Campaign for Action on Family Violence Lead agency: Families Commission / Ministry of Social Development

Background The Campaign for Action on Family Violence (the campaign) is a four year campaign that calls on everyone to help put an end to family violence in New Zealand. The national campaign was launched with TV advertisements in September 2007. The campaign message ‘Family violence – It’s not OK’ has struck a chord with New Zealanders and has quickly become part of the kiwi vernacular. The campaign is supported by a website, an 0800 Information Line and a Community Action Fund that provides financial support for community-led activities. Progress to date (previous 3 months work) The second phase of the campaign was launched in February 2008. This phase focuses on intimate partner violence and features TV advertisements of men who have chosen to be violence free and the impact on their families. The four advertisements went to air 17 February and ran to the end of March 2008. Existing resources (the booklets, Community Action Tool Kit, Resources for journalists and web-based information and support) continue to be distributed. New resources have now been developed and are also being distributed. The 0800 telephone line continues to provide information and support. The number of male callers to the line averages just over 40%. There has been an increase in the number of visitors to the campaign website. The highest monthly level of visits to the site since the national launch in September 2007 was recorded during April at just under 8,000 visits. There has been an increased number of email enquiries to the Campaign team via the website since the second phase of advertising started. To continue monitoring the effect of the Campaign, a second reach and retention survey took place in March and April 2008. The results of this most recent survey are consistent with the first tracking survey from the end of 2007. Recall of the Campaign remained very high with 89% of the total sample recalling something from the Campaign, and 66% of those surveyed recalled seeing one or more of the TV advertisements from the second phase of the Campaign. Recall was high across all ethnic groups, but more so for Māori males and Māori females (79% and 76% respectively). Almost one in five (19%) of those who have seen the TV advertisements reported taking some action as a result of seeing the advertisements. The most common action reported by those who recalled the advertisements were that they: - talked to family or friends about violence they were worried about (12%) - obtained information about family violence (8%) - contacted some other organisation, professional or community leader to talk about violence they were worried about (3%). The campaign’s media advocacy work is proving highly effective. Community spokespeople are being given media training and an increasing number of reporters and media organisations are showing an interest in the family violence media training package. The campaign team has just received its third media audit report for the October-December 2007 quarter. It shows that media interest in the Campaign and the issue of family violence has been sustained. The number of stories portraying family violence as unacceptable has doubled; the number of stories containing a family violence message has increased, the number of stories containing a family violence myth has decreased. Community agency spokespeople are visible in the media and local coverage of national family violence issues has increased. Current ongoing work (next 3 months) Three additional weeks of the phase two advertisements going to air have been booked for early May, late May and mid-June. A third and fourth round of the Community Action Fund have been agreed, with round three open currently, and closing on 10 June. Successful applicants will be announced by the end of July. A series of Community Action Fund regional hui are taking place to bring together recipients to share ideas and plan ahead. Timing / Ongoing / Recommendations / Conclusions Status = on track.

2.7 Family Violence Death Review Project Lead agency: Ministry of Health

Background The Ministry of Health has established a cross-agency Family Violence Death Review Project in close collaboration with the MSD, the MoJ, the Police and other key government and non-government organisations. The MoH reported to the Taskforce on 30 June 2007 and recommended that a formal mechanism for an interagency, multidisciplinary family violence-related death review system be established under the New Zealand Public Health and Disability Act 2000 (the NZPHD Act). The family violence death review system proposed involves the establishment of a ministerial committee that is parallel to, but separate from, the current mortality review committees mandated under the NZPHD Act. The Taskforce agreed to the recommendations in the report. An implementation manager was appointed in December 2007 to progress the establishment of the Family Violence Death Review Committee (FVDRC). On 13 February 2008, the Government considered a paper from the Minister of Health and noted that the Minister intends to establish a FVDRC under the NZPHD Act. On 20 February 2008, the draft Terms of Reference for the FVDRC were released for external consultation. Progress to date (previous 3 months work) - In March, the Minister of Health approved the finalised Terms of Reference. - A Senior Analyst (Legal) and a Senior Business Analyst were appointed in April to work on specific implementation issues, such as the FVDRC’s information requirements and death review process issues. - In April, the MoH issued a call for nominations for the inaugural members of the Family Violence Death Review Committee. Nominations closed on 1 May, and 59 applications were received. The Minister of Health is currently considering the nominees. - The FVDR Implementation Advisory Group had its first meeting in May to discuss implementation issues associated with the establishment of the FVDRC. Current ongoing work (next 3 months) - The MoH plans to undertake the Cabinet appointments process during May and June to appoint members to the Committee. - A written notice will be presented to the House of Representatives by the Minister of Health to establish the Committee (late June 2008). Timing / Ongoing / Recommendations / Conclusions Status = on track.

### Ensuring Safety and Accountability

3.1 Family Violence Courts Lead agency: Judiciary / Ministry of Justice

Progress to date (previous 3 months work) The locations and dates for implementation of the further two Family Violence Courts are yet to be confirmed. The Chief District Court Judge has indicated that Palmerston North and Whangarei are likely locations for the new FV Courts to exist from September 2008. Current ongoing work (next 3 months) Once the location and implementation dates for the new Family Violence Courts are confirmed the MoJ will work closely with the Judiciary, court staff and key stakeholders (including Police Prosecutions, Community Probation and community agencies) at these locations to plan the implementation of the courts. The Ministry will also be looking to ensure that the staff and key stakeholders who will be working in those Family Violence Courts will receive specialist training on the dynamics of domestic violence and the philosophy of Family Violence Courts prior to the courts being implemented. A communications strategy will be developed in preparation for the launch of the new courts, in consultation with the Chief District Court Judge and the Minister for Courts. Timing / Ongoing / Recommendations / Conclusions Status = on track.

3.2 Family Violence Court Protocols Lead agency: Judiciary / Ministry of Justice

Progress to date (previous 3 months work) National Operating Guidelines for Family Violence Courts have been developed. The Guidelines have been considered by the Family Violence Courts Judges and approved by the Chief District Court Judge. The Guidelines went out for broader consultation on 21 April 2008 to key staff and stakeholders. The deadline for feedback was 16 May 2008. Current ongoing work (next 3 months) Following approval, the National Operating Guidelines will form the basis for DV Training which will be delivered to staff and key stakeholders at all Family Violence Courts by June 2008. Successful training will result in successful implementation of protocols in all Family Violence Courts prior to this date. Six Family violence Courts workshops have been scheduled across all courts in two phases from 20 May to the end of July 2008. Phase 2 will incorporate sessions relating to the National Operating Guidelines. Timing / Ongoing / Recommendations / Conclusions Status = on track.

3.3 Social Services supporting Courts Lead agencies: Ministry of Justice / Ministry of Social Development

Progress to date (previous 3 months work) A Variation to this objective was approved by the Chair of the Taskforce on 4 April 2008. The previous deliverables and milestones did not align with the direction the Chief District Court Judge has set for the Family Violence Courts. Current ongoing work (next 3 months) The Government has announced that it will move towards fully funding actions 1 and 3 of this objective from 2008/2009 (Introduction of Independent Victim Advocate/support person role in all Family Violence Courts and referral and funding for non-mandated stopping violence programme providers for offenders). MoJ and MSD will meet fortnightly from 7 April 2008 to discuss and agree the proposed approach to this work in light of this announcement. The Project Plan and Terms of Reference for this objective have been finalised and agreed. Work has commenced on the development of the Independent Victim Advocate (IVA) role. Timing / Ongoing / Recommendations / Conclusions Status = on track.

### Effective Support Services

4.1 Mäori Service Workforce Development Lead agency: Ministry of Social Development

Progress to date (previous 3 months work) - Resources for practitioners and facilitators of groups have been developed. - All Mauri Ora training is well underway, numbers are currently higher than contracted and the courses are generating excellent feedback. Current ongoing work (next 3 months) - A DVD of key Mäori leaders giving messages around the kaupapa of family violence is being developed. - Existing resources are being distributed. - Facilitation training for practitioners working with groups is underway. - The recruitment and training of supervisors for Mauri Ora practitioners is underway. Timing / Ongoing / Recommendations / Conclusions Status = on track.

4.2 Pacific Service Workforce Development Lead agency: Ministry of Social Development

Background This work is now incorporated within the Pathway to Partnership (P2P) plan. Pacific service workforce development is incorporated under the work-stream to address providers’ ability to build workforce capability and capacity. Progress to date (previous 3 months work) On 12 February 2008, the Government announced an additional funding package for the P2P plan worth $446 million, to be phased in over the next four years. A steering group for the P2P plan has overseen the development of P2P over the last year. A representative from the MSD’s PAG is on this steering group. Current ongoing work (next 3 months) The P2P workforce and provider development project plan is currently being clarified and will be confirmed in July 2008. Timing / Ongoing / Recommendations / Conclusions Status = some delay.

4.3 Service Demand Data Lead agency: Ministry of Social Development

Background Monitoring systems were developed to measure the initial impact in service demand associated with the Campaign for Action on Family Violence. These monitoring systems included data from the 0800 number, CYF and Police. The quantitative measures included in these monitors will be repeated. Qualitative data collected from the NGO sector in selected communities will compliment the quantitative monitors providing data directly from the NGO sector. The qualitative data collection will focus on the contribution that the Campaign for Action on Family Violence has had on any change in service demand experienced by the NGO sector since the commencement of the Campaign. Progress to date (previous 3 months work) Original data sets have been requested. Current ongoing work (next 3 months) Available data will be analysed to provide an estimate of service demand since the commencement of the Campaign. Timing / Ongoing / Recommendations / Conclusions Status = on track.

4.4a Training our Staff Lead agency: ACC

NB: there are only some agencies for whom it is relevant to complete a training project plan. This objective relates directly to Objective 1.5b – Family Violence Free Workplaces (FVFW). Ongoing work - Continuing work underway to scope FVFW training requirements, attended MSD FVFW training - Continued scoping of ACC requirements. Initial training provider assesses did not meet requirements. - Modular based training identified as best solution – in development.

4.4b Training our Staff Lead agency: CYF/All agencies

Ongoing work (next three months) - Where identified as part of their professional development plan, frontline social work staff attend a Family Violence workshop. This workshop has been available for some time, this is being reviewed as part of an ongoing quality assurance process and will now be available as part of the specialists stream within the new Practice Induction programme. - Family Violence is discussed in numerous other parts of the new Practice Induction in the workplace learning modules, the classroom based two week Practice Foundation and various learning forums that are part of the new Practice Induction programme.

## Detailed Milestone Updates

This section provides short-form updates on objectives, and actions and milestones within each objective.

### Leadership

| 1.1 FACILITATION OF THE ONGOING PROGRAMME OF ACTION (OPOA) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Taskforce Secretariat / All Taskforce agencies |  |
| Project Manager |  |  |  | Carra Hamon |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Facilitation, implementation and strategic engagement of the Ongoing Programme of Action for specific groups and across all sectors in New Zealand. Actions include: - Stewardship of the Ongoing Programme of Action work programme - Stewardship of children specific work programme - Stewardship of all other work programme |  |  |  |  |  |
| Deadline |  | Ongoing |  |  |  |
| Purpose |  |  |  |  |  |
| To successfully monitor and ensure implementation of the Ongoing Programme of Action. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.1.4 | Officials contacted for updates for June Taskforce meeting monitoring report |  | 5 April |  | Complete. |
| 1.1.5 | Protection Orders interim update |  | Beg May |  | This paper will now be sent out with 4 June meeting papers. |
| 1.1.6 | Monitoring Report for May prepared and sent with 4 June meeting papers. |  | 20 May |  | On track. Includes updates on ongoing actions from First Report. |
| 1.1.7 | Protection Orders update to be sent to Minister end August |  | 30 August |  | On track. Draft version will be distributed to the Taskforce for 6 August meeting. |
| 1.1.8 | Monitoring Report for July prepared and sent with 6 August meeting papers. |  | 22 July |  | Not yet commenced. |

| 1.1a MAPPING OF THE ONGOING PROGRAMME OF ACTION (OPOA) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | NGOs |  |
| Contributors |  |  |  |  |  |
| Project Manager |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Actions include: - Ongoing Programme of Action mapped to its outcome. |  |  |  |  |  |
| Deadline |  | Alert |  |  |  |
| Purpose |  |  |  |  |  |
| Alert |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
|  | Alert |  |  |  |  |

| 1.2 MAORI PROGRAMME OF ACTION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agencies |  |  | Mäori Reference Group Ministry of Social Development |  |  |
| Contributors |  |  | Te Puni Kokiri, NGOs |  |  |
| Project Manager |  |  | Ann Dysart (MSD) |  |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| A Programme of Action focused on eliminating violence in Maori whänau is developed. Actions include: - Developing a Maori Programme of Action - Ensuring the leadership and ownership of the actions at all levels of Te Ao Maori |  |  |  |  |  |
| Deadline |  | June 2008 |  |  |  |
| Purpose |  |  |  |  |  |
| To develop a process and plan that engages all areas of Te Ao Maori in owning and addressing the issues of Family Violence and Child abuse. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 1.2.1 | Draft Maori Communication Strategy |  |  | Jan 08 | Completed and implemented for the Whanau Summit. |
| 1.2.2 | Maori Whanau Summit |  |  | 3 & 4 April 08 | Completed with success. |
| 1.2.3 | Local regional hui with Maori family providers and practitioners |  |  | April / May 08 | Regional Hui schedules under development. |
| 1.2.4 | Launch Maori Programme of Action. Work towards establishing action plan for 08/09 and priorities for next five years |  |  | June 08 | On track. |

| 1.3 PACIFIC PROGRAMME OF ACTION |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  |  | Pacific Advisory Group Ministry of Social Development |  |  |
| Contributors |  |  |  |  | Ministry of Pacific Island Affairs, NGOs |  |  |
| Project Manager |  |  |  |  | Liz Tanielu (MSD) |  |  |
| First Programme of Action reference |  |  |  |  |  |  |  |
| Objective and actions (as per Work Programme) Note that a Variation is due to be submitted for this objective. This will be submitted before the June 2008 Taskforce meeting. |  |  |  |  |  |  |  |
| Programme of Action focused on eliminating violence in Pacific families is developed. Actions include: - Develop a Pacific Programme of Action |  |  |  |  |  |  |  |
| Deadline |  |  |  |  |  |  |  |
| Purpose |  |  |  |  |  |  |  |
| To articulate the status of Family Violence as it impacts on Pacific People and outline specific action to address it. |  |  |  |  |  |  |  |
| Key Milestones |  |  |  | Date |  |  | Description of Progress |
| 1.3.1 | Draft Pacific POA |  |  | Jan 08 |  |  | Draft developed, circulated to PAG. |
| 1.3.2 | Stakeholder Meetings for input into POA |  |  | March 08 |  |  | Consultation begun. |
| 1.3.3 | Final POA |  |  | June 08 |  |  | On track. |
| 1.4 CHILD MALTREATMENT |  |  |  |  |  |  |  |
| Lead agency |  |  |  |  | Office of the Children’s Commissioner |  |  |
| Contributors |  |  |  |  | MSD, NGOs, Justice, Health, Education, Police |  |  |
| Project Sponsor |  |  |  |  | Dr Cindy Kiro |  |  |
| Project Manager |  |  |  |  | John Angus / Ruth Palmer (MSD) |  |  |
| First Programme of Action reference |  |  |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |  |  |
| A long term plan is developed for government’s work on addressing child maltreatment (including child sexual abuse) within families. Actions include: - Assess current work on prevention and reduction of child sexual abuse - Review existing literature - Develop a research agenda - Link to the Taskforce strategic research agenda for family violence prevention - Include children with disabilities within this work - Plan future work - Ensure ongoing communications between Taskforce and Taskforce for Action on Sexual Violence |  |  |  |  |  |  |  |
| Deadline |  | 30 June 2008 |  |  |  |  |  |
| Purpose |  |  |  |  |  |  |  |
| Child maltreatment in New Zealand has been difficult to quantify and fully understand. General consensus holds that child maltreatment occurs predominantly within families. This work will develop an integrated, cross government approach to work on child maltreatment which has attached to it a growing evidence and knowledge base. |  |  |  |  |  |  |  |
| Key Milestones |  |  | Date |  |  | Description of Progress |  |
| 1.4.3 | Final paper on child sexual abuse |  | Feb 2008 |  |  | Complete. Circulated to agencies and forwarded to the Taskforce at 9 April meeting. |  |
| 1.4.4 | Draft work programme developed |  | June 2008 |  |  | Work is ongoing to develop a work programme for the TF on child maltreatment, as agreed from outline presented to 9 April TF meeting. An External Advisory Group is being established, due to be confirmed in June. A draft work programme will be taken to the TF in July 2008. This will supersede previous milestones. |  |
| 1.4.5 | Work programme agreed |  | TBC |  |  | Due to be presented to 6 August TF meeting. Further milestones will then be developed. |  |

| 1.5a FAMILY VIOLENCE FREE WORKPLACES |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | ACC, Police, NGOs |  |
| Project Manager |  |  |  | David Dick |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Family Violence -Free Workplaces are developed and implemented through HR policy – link to Campaign, model for other agencies, role model for public and other workplaces. Actions include: - develop policy - put in place tools and resources - training of contact people/family violence co-ordinators - implementation - develop a model for replication in the public sector and private sector |  |  |  |  |  |
| Deadline |  | May 2012 |  |  |  |
| Purpose |  |  |  |  |  |
| Family Violence Free Workplaces means staff in those workplaces is aware and supported around issues to do with family violence. These workplaces are expected to provide low cost high impact prevention and recovery opportunities for members of the workplace who are affected by family violence. They may be victims, observers or perpetrators. Implementing Family Violence Free Workplaces is expected to decrease workplace stress, and increase workplace productivity by empowering and supporting victims and observers of family violence and channelling perpetrators through appropriate channels to help them change their behaviour. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.5a.1 | Human Resources Plan |  | Oct 2007 |  | Complete. Presented to the Human Resource Governance Committees for Policy and Service Delivery business areas. |
| 1.5a.2 | Policy development |  | Oct 2007 |  | Draft completed – to be progressed through approval processes |
| 1.5a.3 | Establish internal steering group to oversee Family Violence initiatives |  | Dec 07 |  | Held up due to change of DCE in Policy Group. |
| 1.5a.4 | Manager guidelines developed to support policy. Published on MSD intranet site |  | Dec 2007 |  | Draft guidelines developed and to be progressed through approval process |
| 1.5a.5 | Raising Awareness of Family Violence - National Office information sessions - Regional info sessions |  | Sep 2007 Mar 2008 |  | Completed. Information sessions scheduled for National Office staff. Developing information session package. To liaise with ACC to explore combined sessions. |
| 1.5a.6 | Providing accessible information and resources - Information and links placed on intranet site - Provide informational resources for workplaces – such as posters, booklets, toolkits |  | Sep 2007 Dec 2007 |  | Completed. FV Campaign logo on front page of intranet as a link. Will use resources from the FV Campaign. Posters distributed to business units. |
| 1.5a.7 | Tools and resources - address concerns about Family Violence counselling services available through current EAP provider - Explore the development of web-based family violence resources for the workplace |  | Oct 2007 2009 |  | Completed. Provided information to feed into RFP process for new Employee Assistance Program provider. Still in earlier exploration stages. Subject to potential joint development between Family and Community Services and PVH and funding. |
| 1.5a.8 | Training - In-depth family violence training for line HR staff and HR consultancy. - Deliver additional training programmes for key support people and all staff as required |  | Sep 2007 |  | Completed. PVH (Preventing Violence in the Home) delivered two-half day training sessions for HR staff. To be programmed subject to demand. |
| 1.5a.9 | Peer support framework developed - approval - developed - pilot - track and assess roll-out to other areas. |  | Dec 2008 |  | Complete. Peer support programme launched in Dec 2007 to provide in-house support on family violence and information services. A review meeting will be held in June 2008. CYF considering as part of broader peer support framework for staff |

| 1.5b FAMILY VIOLENCE FREE WORKPLACES |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  |  | Accident Compensation Corporation |  |
| Contributors |  |  |  |  | MSD, Police, NGOs |  |
| Project Manager |  |  |  |  | Danielle George |  |
| First Programme of Action reference |  |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |  |
| Family Violence -Free Workplaces are developed and implemented through HR policy – link to Campaign, model for other agencies, role model for public and other workplaces. Actions include: - develop policy - put in place tools and resources - training of contact people/family violence co-ordinators - implementation - develop a model for replication in the public sector and private sector |  |  |  |  |  |  |
| Deadline |  |  | December 2008 |  |  |  |
| Purpose |  |  |  |  |  |  |
| Family Violence Free Workplaces means staff in those workplaces is aware and supported around issues to do with family violence. These workplaces are expected to provide low cost high impact prevention and recovery opportunities for members of the workplace who are affected by family violence. They may be victims, observers or perpetrators. Implementing Family Violence Workplaces is expected to decrease workplace stress, and increase workplace productivity by empowering and supporting victims and observers of family violence and channelling perpetrators through appropriate channels to help them change their behaviour. |  |  |  |  |  |  |
| Key Milestones |  |  |  | Date |  | Description of Progress |
| 1.5b.1 |  | Family Violence staff resources |  | 14/09/2007 |  | Complete. Intranet site published and resources available. |
| 1.5b.2 |  | Release of Family Violence Policy |  | 15/11/2007 |  | Ongoing. Policy currently being updated |
| 1.5b.3 |  | HR Co-ordinator skills development |  | 31/12/2007 |  | Ongoing. Working with PVH to adapt MSD tools for ACC |
| 1.5b.4 |  | Training programmes and managers guides |  | 31/03/2008 |  | Initial half day pilot run for HR staff by PVH. Training did not meet the needs of the organisation and alternative supplier or modifications to PVH module under investigation. |
| 1.5b.5 |  | Policy and guideline refresh |  | 31/03/2008 |  | Complete. Refresh launch of policy and guidelines, Family Violence Support also launched as part of ACC’s Staff Wellbeing programme in February 2008 |
| 1.5b.6 | FVFW established across ACC |  |  | 31/12/2008 |  | On track for fully embedded across ACC by end of 2008 |

| 1.5c FAMILY VIOLENCE FREE WORKPLACES |  |  |  |  |
| --- | --- | --- | --- | --- |
| Lead agency |  |  | New Zealand Police |  |
| Contributors |  |  | MSD, ACC, NGOs |  |
| Project Manager |  |  | Carol Train |  |
| First Programme of Action reference |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |
| Family Violence -Free Workplaces are developed and implemented through HR policy – link to Campaign, model for other agencies, role model for public and other workplaces. Actions include: - develop policy - put in place tools and resources - training of contact people/family violence co-ordinators - implementation - develop a model for replication in the public sector and private sector. |  |  |  |  |
| Deadline |  | May 2012 |  |  |
| Purpose |  |  |  |  |
| Family Violence Free Workplaces will raise the awareness of staff in the Police about family violence and provide support where appropriate. Police staff may be victims, observers or perpetrators of family violence. Implementing Family Violence Workplaces is expected to decrease workplace stress, and increase workplace productivity by empowering and supporting victims and observers of family violence and channelling perpetrators through appropriate channels to help them change their behaviour. |  |  |  |  |
| Key Milestones |  |  | Date | Description of Progress |
| 1.5c.1 | Policy developed and agreed |  | Dec 2008 | On track, meeting with MSD as have progressed this project further. |
| 1.5c.2 | Training and resource developed |  | Dec 2009 | On track |
| 1.5c.3 | Communications package completed |  | Jan 2010 | On track |
| 1.5c.4 | Training Delivered in all Districts |  | Dec 2010 | On track |
| 1.5c.5 | Family Violence Free Workplaces established in Police |  |  | On track |
| 1.5c.6 | Evaluation of Police model |  | Dec 2011 | On track |
| 1.5c.7 | Finalise Blueprint for implementing Family Violence Free Workplaces in public, private and non-government sectors |  | May 2012 | On track |

| 1.6 IWI LED CRIME PREVENTION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | New Zealand Police |  |
| Contributors |  |  |  | Iwi, NGOs, Te Puni Kokiri |  |
| Project Manager |  |  |  | Wally Haumaha |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Iwi led crime prevention plans which have a focus on the prevention of family violence Actions include: - Provide support to iwi to develop plans - Iwi led crime prevention strategies developed in accordance with each iwi identified needs, values and timeframes |  |  |  |  |  |
| Deadline |  | This is an iterative and evolving process that is being driven by iwi. Precise deadlines are neither available, nor appropriate at this stage. |  |  |  |
| Purpose |  |  |  |  |  |
| In absolute numbers, more Maori churn through the criminal justice system every year than graduate from University. A new framework for action is being developed by Maori with assistance from officials. That new framework is Iwi-led Crime Prevention Plans (ICPPs). ICPPs take a long-term, incremental approach to improving Maori criminal justice outcomes. They are led by iwi, with assistance from officials. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.6.1 | Iwi to populate their crime prevention plan templates |  | No deadline |  | On track |
| 1.6.2 | Officials to condense those templates into A3 summaries |  | No deadline |  | Pending |
| 1.6.3 | Summaries to be presented back to iwi for confirmation |  | No deadline |  | Pending |
| 1.6.4 | Ministerial briefing paper to Ministers of Justice, Police and Maori Affairs |  | March 2008 |  | On track |

| 1.7 FAMILY VIOLENCE CLEARINGHOUSE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | Families Commission, NGOs |  |
| Project Manager |  |  |  | Jeff Sheerin |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| The Family Violence Clearinghouse (FVC) is enhanced to ensure its efficacy and to become the independent, sustainable, comprehensive one-stop shop for national and international information on family violence. Actions include: - Develop a model and systems which optimise the operations of the FVC |  |  |  |  |  |
| Deadline |  | June 2009 |  |  |  |
| Purpose |  |  |  |  |  |
| To review Family Violence Clearing House activities and services and develop a strategy for moving forward. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.7.1 | Negotiate contract with Canterbury University |  | 30 Jan 2008 |  | Negotiations concluded April 2008. A variation to the contract extending it by two months to 31 August 2008 has been agreed and signed by parties. |
| 1.7.2 | Scope redevelopment of NZFVC project, identify requirements and develop strategy |  | 30 June 2008 |  | Now underway. |
| 1.7.3 | Develop 2-5 year strategy |  | 30 June 2008 |  | * subject to human resource availability |
| 1.7.4 | Develop project plan and secure funding |  | 30 June 2008 |  | * subject to human resource availability |
| 1.7.4 | Implement new clearinghouse website and service |  | 28 February 2009 |  | * subject to human resource availability |

| 1.8 CASE STUDIES CHARACTERISING GOOD PRACTICE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | NGOs, Justice, Police |  |
| Project Manager |  |  |  | Dorothy Adams |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Case studies characterising good practice in service aimed at eliminating family violence are developed and made publicly available. Actions include: - Scope and identify existing good practice models - Record the characteristics of their success - Index and deposit in Family Violence Clearinghouse. |  |  |  |  |  |
| Deadline |  | October 2008 |  |  |  |
| Purpose |  |  |  |  |  |
| To describe and generalise good practice principles as they apply to family violence prevention. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.8.1 | Identification of case study subjects |  | April 2008 |  | Generating options for case study development |
| 1.8.2 | Draft case studies |  | Sept 2008 |  | Selecting community researchers to conduct data collection for case studies. |
| 1.8.3 | Final case studies |  | Oct 2008 |  | On track |

| 1.9 MAORI RESEARCH AGENDA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Te Puni Kokiri |  |
| Contributors |  |  |  | MRG, MSD, Families Commission, NGOs |  |
| Project Manager |  |  |  | Te Atarangi Whiu |  |
| First Programme of Action reference |  |  |  | New initiative |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Improve our understanding of the nature of family violence in whänau Mäori and successful models of prevention and intervention. Actions include: - Review existing literature - Develop a research agenda - Link to the Taskforce strategic research agenda for family violence prevention - Recommend further action. |  |  |  |  |  |
| Deadline |  | 31 July 2008 |  |  |  |
| Purpose |  |  |  |  |  |
| To increase the evidence base by providing case studies of a minimum of three Maori designed, developed and delivered programmes. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.9.1 | Progress Report |  | 31 Jan 08 |  | Scope of project defined. Three key outputs. |
| 1.9.2 | Final Report |  | 31 July 08 |  | Some delay. Expected completion date of 31 July 2008, one month later than initially planned. |

| 1.10 PACIFIC RESEARCH AGENDA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Pacific Island Affairs |  |
| Contributors |  |  |  | PAG, MSD, Families Commission, NGOs |  |
| Project Manager |  |  |  | TBC |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) A Variation is about to be submitted to the Chair of the Taskforce. Content may differ in this objective from previous reporting. |  |  |  |  |  |
| Improve our understanding of the nature of family violence in Pacific families and successful models of prevention and intervention. Actions include: - Finalise project plan - Consultation with Pacific Advisory Group - Consultation with other Pacific stakeholders - Development of report including identification of Pacific Family Violence Research priorities |  |  |  |  |  |
| Deadline |  | Final deadline to be confirmed |  |  |  |
| Purpose |  |  |  |  |  |
| To develop an understanding of Pacific family violence research priority topics and the issues which surround Pacific family violence research. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.10.1 | Finalise project plan |  | April 2008 |  | Complete. Project plan finalised, stakeholder discussions completed. |
| 1.10.2 | Consult with Pacific Advisory Group |  | June 2008 |  | Scheduled, but not yet commenced. |
| 1.10.3 | Consult with other Pacific stakeholders |  | July 2008 |  | Not yet commenced |
| 1.10.4 | Completion of report |  | August 2008 |  | Not yet commenced |

| 1.11 NEW MIGRANT AND REFUGEE RESEARCH AGENDA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | Dorothy Adams |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Improve our understanding of the nature of family violence in new migrant and refugee families and successful models of prevention and intervention. Actions include: - Review existing literature - Develop a research agenda - Link to the Taskforce strategic research agenda for family violence prevention - Recommend further action |  |  |  |  |  |
| Deadline |  | To be provided after the scoping phase |  |  |  |
| Purpose |  |  |  |  |  |
| A statement of purpose will be developed in the scoping phase. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.11.1 | Synthesis of literature |  | April 2008 |  | Annotated bibliography drafted. |
| 1.11.2 | Scoping paper |  | June 2008 |  | On track |

| 1.12 ELDER ABUSE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | Cilla Corlett |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions |  |  |  |  |  |
| Improve our understanding of the nature of elder abuse and successful models of prevention and intervention. Actions include: - Review existing literature - Develop a research agenda - Link to the Taskforce strategic research agenda for family violence prevention - Recommend further action |  |  |  |  |  |
| Deadline |  |  |  |  |  |
| Purpose |  |  |  |  |  |
| Expected Outcome: Improved decision-making about viable programme and service delivery to eliminate elder abuse and neglect within the family setting. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.12.1 | Review existing literature |  | Jan 2006 |  | Literature Review completed by CSRE: refer http://www.msd.govt.nz/work-areas/social-research/older-people/elder-abuse-neglect.html |
| 1.12.2 | Develop a research agenda |  | 30 June 2008 Feb 2008 |  | On track. MSD is currently working with Age Concern and the Families Commission in drafting a cross-sectoral national Action Plan for elder abuse and neglect. As part of the Action Plan a Research Strategy for EAN is also being developed. The Families Commission commissioned research exploring the risk and protective factors associated with elder abuse and neglect. The research report was released on 26 February 2008. |
| 1.12.3 | Link to the Taskforce strategic research agenda for family violence prevention |  | Ongoing |  | Although the proposed programme of action on EAN will encompass all forms of elder abuse and neglect across all settings, not just within families, strong links will be made between the EAN research strategy and the Taskforce strategic research agenda for family violence prevention. |
| 1.12.4 | Recommend further action |  | - May 2008 On track - August 2008 - Sep 2008 |  | - Report to Minister seeking approval of a proposed work programme, timeline and governance arrangements for working towards developing a national action plan for elder abuse and neglect. - Complete consultation with sector on issues and priorities - Report to Minister SDE and to FVT (for FVT October 2008 meeting) with recommended priorities for action. |

| 1.13 DATA ON NGO SERVICE DELIVERY |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Social Development |  |  |
| Contributors |  |  | NGOs, ACC, Justice, Police, Health |  |  |
| Project Manager |  |  | Dorothy Adams |  |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions |  |  |  |  |  |
| High quality data available about services delivered by, and on the demand for NGO and agency family violence services. Actions include: - Develop systematic and accurate data on services |  |  |  |  |  |
| Deadline |  | To be confirmed after scoping work completed |  |  |  |
| Purpose |  |  |  |  |  |
| A purpose statement will be derived from the scoping study. This work is aligned with the “Supporting a Sustainable NGO Social Service Sector” initiative. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 1.13.1 | Scoping study and project plan |  |  | July 2008 | On track |
|  | No further milestones provided |  |  |  |  |

### Changing Attitudes and Behaviour

| 2.1 KIA PUAWAI |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | All Taskforce members |  |
| Project Manager |  |  |  | Bede Hogan |  |
| First Programme of Action reference |  |  |  | Not in first Programme of Action |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Kia Puawai supported in its implementation by the Taskforce. Taskforce supports initiatives such as: - increasing coverage of intensive home visiting - providing free Early Childhood Education for all vulnerable children aged 18 months – 3 years - developing an integrated identification, assessment and referral system for young children - expanding Early Years hubs and teen parent co-ordinators initiatives - key workers to support at-risk families - expanding Social Workers in Schools. |  |  |  |  |  |
| Deadline |  | Ongoing |  |  |  |
| Purpose |  |  |  |  |  |
| This cross-agency initiative is building an early years intervention system to help ensure all children flourish in early childhood and reach their potential as young adults capable of developing healthy, respectful and violence free relationships throughout their lives. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 2.1.1 | Early years budget package developed |  | Mid Nov 07 |  | Completed. Submitted December 2007. |
| 2.1.2 | Progress report delivered to Ministers on results of +evaluations of pilot programmes to improve outcomes for children and their families. |  | Nov 08 |  | Evaluations commenced. |
| 2.1.3 | B4School check pilot in place |  | Aug 08 |  | Work underway. |

| 2.2 IMPROVING ATTACHMENT |  |  |  |  |
| --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Health / Auckland District Health Board |  |
| Contributors |  |  | MSD, ACC, Education, NGOs |  |
| Project Manager |  |  | Pat Tuohy / Carol Stott |  |
| First Programme of Action reference |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |
| Promote and improve attachment between new-born babies and parents and care givers. Actions include: - Progress a pilot - See how well it works - Report - Draw on key findings from parent support and development programmes already focused on supporting attachment between young children and parents and caregivers |  |  |  |  |
| Deadline |  | July 2009 |  |  |
| Purpose |  |  |  |  |
| Supporting the promotion of healthy secure attachment in infants is important for the development of quality relationships between infants and parents and caregivers, and for its effect on human development and wellbeing. Promotion of secure attachment can be provided through provision of information to parents, and support with strategies that enhance attachment and address any parenting concerns. Early intervention is recommended for infants of high-risk carers if developmental or behavioural problems are detected. |  |  |  |  |
| Key Milestones |  |  | Date | Description of Progress |
| 2.2.1 | Inclusion of an additional visit in the Well Child Framework for first time parents especially for fathers and male partners |  | July 2009 | Not commenced |
| 2.2.2 | Promotion of infant-parent attachment and assessment of parent /child relationship difficulties in revised Well Child Framework |  | July 2009 | Not commenced |
| 2.2.3 | Training for Well Child Providers to promote secure infant- parent attachment |  | July 2009 | Not commenced |
| 2.2.4 | Establishment of a pilot in the Auckland District Health Board area to prevent Shaken Baby Syndrome (head injuries to babies caused by violent shaking). |  | TBC | Delayed. The Auckland DHB has decided not to proceed with this pilot as it was not considered a funding priority. The reason being is that the majority of babies admitted to Starship Hospital with head injuries as a result of Shaken Baby Syndrome are from outside the Auckland DHB’s area. The Ministry has been approached to fund a regional pilot across the three Auckland DHBs and is currently considering whether funding could be made available for this initiative. |

| 2.3 CONDUCT DISORDER / SEVERE ANTI-SOCIAL BEHAVIOUR |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Social Development |  |  |
| Contributors |  |  | Education, Health, Justice, NGOs, OCC |  |  |
| Project Manager |  |  | Bede Hogan |  |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Ensure comprehensive behavioural interventions for children aged 3 – 7 years with conduct disorder/severe antisocial behaviour and their families are delivered in accordance with the Inter-agency Plan by building on the specialist behaviours services already provided by the Ministry of Education. Taskforce supports the four action areas in the Inter-Agency Plan: - leadership, co-ordination, monitoring and evaluation - transition existing service provision to evidence-based, best-practice interventions - establish an intensive, comprehensive behavioural service for 3 -7 year olds - build a shared infrastructure for the delivery of specialist behavioural services. |  |  |  |  |  |
| Deadline |  | 2012 |  |  |  |
| Purpose |  |  |  |  |  |
| Developing and delivering a suite of services for the 5% of primary and intermediate aged children who have conduct disorder/severe anti-social behaviour will reduce the prevalence of children at intermediate schools with these problems. Without appropriate interventions, these children are more at risk of becoming perpetrators of violence. Over time these services are expected to result in a reduction in severe cases of family violence. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 2.3.1 | Establish experts advisory group |  |  | Mid Nov 2007 | Completed |
| 2.3.2 | Best practice report completed |  |  | June 2008 | On track |
| 2.3.3 | Agency service reviews completed |  |  | Dec 2008 | On track |

| 2.4 CURRICULUM DEVELOPMENT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Education |  |  |
| Contributors |  |  | MSD (MYD), Health, TPK, MPIA, OCC, NGOs |  |  |
| Project Manager |  |  | Sue van Daatselaar |  |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Children and young people aged 5-18 years develop the knowledge and skills that they need to support good decision-making, to make healthy choices, and to seek help when they need it. Actions include: - Provide support to enable schools to develop their programmes within the New Zealand curriculum to suit the diverse learning needs of their community - Strengthen whole-school, strengths-based approaches that promote resilience and confidence in young people and those adults who support them - Seek opportunities to identify and respond to children who are affected by family violence. |  |  |  |  |  |
| Deadline |  | Ongoing |  |  |  |
| Purpose |  |  |  |  |  |
| The purpose of education is to help children and young people reach their potential and develop the competencies they will need to live, learn, work and contribute as active members of their communities. Education contributes to the prevention and reduction of family violence in New Zealand communities by providing a safe environment that teaches and models skills to enable children and young people to manage their own well-being and to relate in healthy ways with others. It provides children and young people with the opportunity to learn skills they might not otherwise receive in the home environment. To experience the benefits of education, students must participate and be engaged with the education system. The Ministry of Education supports educators to identify students who are at risk as a result of experiencing, witnessing or engaging in family violence and to work with parents, families and whänau, and other agencies to ensure these students are appropriately supported. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 2.4.1 | Provide support to enable schools to develop their programmes within the New Zealand curriculum (NZC) to suit the diverse learning needs of their community. - Release final curriculum and supporting resources for schools to support the implementation of the curriculum - Professional leaders are supported to lead curriculum development, establish the conditions for professional learning and involve families/whanau in focusing on student achievement and educational outcomes based on the NZC. |  |  | Dec 07 & ongoing June 08 & ongoing | Ongoing. First set of resources to support the implementation of the NZC have been released. We are analysing the findings from the consultation on the draft Te Marautanga o Aotearoa (Mäori Medium Curriculum) and the draft position paper, Kiwi Leadership for Principals. |
| 2.4.2 | Strengthen the implementation of whole-school, strengths-based approaches that promote resilience and confidence in children and young people and those adults who support them. - Support up to 730 teachers per year in developing effective teaching and leadership skills to support the implementation of school-wide approaches to student well being / mental health. This involves strengthening teachers’ understanding of the connections between school organisation, curriculum design and delivery and community consultation and partnerships. - Identify successful professional learning approaches for teachers from the evaluation of the student wellbeing contracts and incorporate in the design and delivery of ongoing professional development contracts. |  |  | June 08 & ongoing | Ongoing. Initial evaluation findings have been used to develop the practice of the agencies delivering the contract. Participating schools have been provided with a summary of the report and a summary of ‘strength-based approaches’. |
| 2.4.3 | Seek opportunities to identify and respond to children and young people who are affected by family violence. - Review the quality and accessibility of support available to educators who are concerned about children and young people affected by family violence. - Develop and implement an action plan to ensure that children and young people identified while at school as affected by family violence receive the support they need (in conjunction with obj 1.4 Child Maltreatment). |  |  | June 08 Sept 08 & ongoing | Ongoing. The Ministry of Education and Child Youth and Family have consulted on and identified the key components for an education profile and plan for children in care. This work has included: identifying the process needed to establish an Educational Profile and Plan; designing templates; developing privacy and information sharing protocols; and clarifying the roles and responsibilities of different agencies. |

| 2.5 VIOLENCE IN THE MEDIA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Families Commission |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | Radha Balakrishnan |  |
| First Programme of Action reference |  |  |  | Action 23 |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Create awareness of impact of violence in the media on children aged between 6 to 11 years. Actions include: - Scope an evidence-based public education and awareness programme aimed at parents - Scope financial implications - Develop an implementation plan. |  |  |  |  |  |
| Deadline |  | February 2009 |  |  |  |
| Purpose |  |  |  |  |  |
| To scope a public education and awareness programme around violence in the media (its risks and impact) with an initial focus on parents of 6-11 year olds. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 2.5.1 | Convene Advisory Group |  | Aug 2008 |  | On track |
| 2.5.2 | Develop plan |  | Oct 2008 |  | Not commenced |
| 2.5.3 | Draft Report circulated for comment |  | Dec 2008 |  | Not commenced |
| 2.5.4 | Report to the Taskforce |  | Feb 2009 |  | Not commenced |

| 2.6 CAMPAIGN FOR ACTION ON FAMILY VIOLENCE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Families Commission / MSD |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | Nick Farland / Gael Surgenor |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Continue the Campaign for Action on Family Violence through: - An advertising campaign - Resource development and distribution - Community Action Fund projects |  |  |  |  |  |
| Deadline |  | 30 June 2008 (ongoing to 2010) |  |  |  |
| Purpose |  |  |  |  |  |
| This is a community-based social marketing campaign which aims to influence the behaviour of target audiences, including perpetrators of family violence and their influencers. The programme is based on research into attitudes and towards family violence and motivators and barriers to behaviour change. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 2.6.1 | Run a television advertising campaign addressing attitudes to family violence and intimate partners violence during 2007/08 |  | 30 June 2008 |  | On track The first set of television adverts was aired from September to January. The second set of four advertisements, focussing on stories of positive change went to air 17 February and ran to the end of March. Three additional weeks of the advertisements going to air have been booked for early May, late May and mid-June. |
| 2.6.2 | Develop a range of resources to support the messages of the television campaign during 2007/08 |  | 30 June 2008 |  | On track We have distributed over 30,000 copies of the Men’s booklet, and 35,000 of the Children’s booklet, both of which were first produced in February. Over 79,000 of the “Are you OK? booklet have been distributed since the beginning of the Campaign in September 2007. The 0800 telephone line continues to provide information and support. There has been an increase in the number of visitors to the campaign website. |
| 2.6.3 | Support local projects to support change at a local level by administering at least one round of the Community Action Fund |  | 15 June 2008 |  | Achieved A total of 62 community initiatives have been funded in the first two rounds of the Community Action Fund. . A third and fourth round have been agreed, with round three open currently, and closing on 10 June. Successful applicants will be announced by the end of July. The campaign’s media advocacy work is proving highly effective. Community agency spokespeople are more visible in the media, and local coverage of national family violence issues has increased. |
| 2.6.4 | Measure the level of public awareness of the key messages of the Changing Attitudes and Behaviours Campaign |  | 30 June 2008 |  | On track CSRE has released two sets of reach and retention survey results on the effectiveness of the Family Violence It’s not OK campaign. Both results show that the campaign has been extremely effective to date. |

| 2.7 FAMILY VIOLENCE DEATH REVIEW PROJECT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Health |  |
| Contributors |  |  |  | MSD, Justice, Police, NGOs |  |
| Project Manager |  |  |  | Tanith Robb |  |
| First Programme of Action reference |  |  |  | Action 42 |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| To establish the Family Violence Death Review Committee |  |  |  |  |  |
| Deadline |  | 31 June 2008 |  |  |  |
| Purpose |  |  |  |  |  |
| The Family Violence Death Review Committee is being established to understand why family violence deaths occur and to enable changes to systems and practices that may contribute to the prevention of future deaths. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 2.7.1 | Undertake consultation on draft Terms of Reference |  | 29/02/08 |  | Completed |
| 2.7.2 | Finalise Terms of Reference and seek Ministerial sign-off |  | 31/03/08 |  | Completed |
| 2.7.3 | Seek nominations for the inaugural members of the Committee |  | 31/03/08 |  | Completed |
| 2.7.4 | Undertake Cabinet appointments process |  | 20/06/08 |  | On track |
| 2.7.4 | Appoint members to the Committee |  | 31/06/08 |  | On track |
| 2.7.4 | Establish Committee |  | 31/06/08 |  | On track |

### Ensuring Safety and Accountability

| 3.1 FAMILY VIOLENCE COURTS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Judiciary / Ministry of Justice |  |
| Contributors |  |  |  | Police, NGOs |  |
| Taskforce Liaison |  |  |  | Justine Cornwall |  |
| Project Manager |  |  |  | Maria McDonald |  |
| First Programme of Action reference |  |  |  | Action 56 |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Two new Family Violence Courts established. Actions include: - Project planning - Identification of locations - Stakeholder consultation - Implementation. |  |  |  |  |  |
| Deadline |  | June 2008 |  |  |  |
| Purpose |  |  |  |  |  |
| To ensure all parties are prepared ahead of the implementation to support new Family Violence Courts being established. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 3.1.1 | Project planning for implementation and establishment of two new Family Violence Courts |  | 30 June 2008 |  | On track. High level project planning has been completed and the Ministry is awaiting direction from the Chief District Court Judge on the court locations and dates for implementation. The Chief District Court Judge has indicated that Palmerston North and Whangarei are likely locations for new Family Violence Courts from September 2008. More detailed project planning will be developed once the Judge has decided the locations. |
| 3.1.2 | Identification of locations |  | TBC |  | Subject to the Chief District Court Judge confirming the new Family Violence Court locations. |
| 3.1.3 | Stakeholder consultation |  | TBC |  | Awaiting decisions as above |
| 3.1.4 | Communications strategy |  | TBC |  | Awaiting decisions as above |
| 3.1.5 | Implementation of two new Family Violence Courts |  | 30 June 2008 |  | Judiciary responsible. Likely to be September 2008. |

| 3.2 PROTOCOLS FOR FAMILY VIOLENCE COURTS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Judiciary / Ministry of Justice |  |
| Contributors |  |  |  | Police, NGOs. |  |
| Liaison |  |  |  | Justine Cornwall |  |
| Project Manager |  |  |  | Maria McDonald / Hayley Corbett |  |
| First Programme of Action reference |  |  |  | Action 57, 58 |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| A national protocol for improving how Family Violence courts are established and run. Actions include: - Develop protocols - stakeholder consultation - Implementation. |  |  |  |  |  |
| Deadline |  |  |  |  |  |
| Purpose |  |  |  |  |  |
| The purpose of this protocol will be to: - Outline the requirements of key staff involved in Family Violence Courts - Outline key areas of best practice to ensure there is consistency across all Family Violence Courts. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 3.2.1 | Development of Operating Guidelines to ensure consistency across all Family Violence Courts |  | 21 Dec 2007 |  | Complete mid Nov - Draft Operating Guidelines have been developed for internal consultation. |
| 3.2.2 | Consultation and communication of Operating Guidelines with key staff and stakeholders |  | 21 Dec 2007 |  | Broader consultation is ongoing through early 2008. |
| 3.2.3 | Approval and distribution of Operating Guidelines across all Family Violence Courts |  | Completed by 30 June 08 |  | On track |
| 3.2.4 | Communications strategy |  | End of June 08 |  | On track |

| 3.3 SOCIAL SERVICES SUPPORTING COURTS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development / Ministry of Justice |  |
| Contributors |  |  |  | Police, MWA, NGOs, ACC |  |
| Project Manager |  |  |  | Bede Hogan / Justine Cornwall |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| A social services system modelled around family violence courts to support the courts by linking services to ensure victims and observers are kept safe, perpetrators are kept accountable and responsible, and families are assisted with their recovery needs. Actions include: - Introduction of Independent Victim Advocate / support person role in all Family Violence Courts - Introduce specialist enhanced case management staff in all Family Violence Courts - Referral and funding for non-mandated stopping violence programme providers for offenders. |  |  |  |  |  |
| Deadline |  | 2009 |  |  |  |
| Purpose |  |  |  |  |  |
| A social services system modelled around family violence courts to support the courts by linking services to ensure victims and observers are kept safe, perpetrators are kept accountable and responsible, and families are assisted with their recovery needs. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 3.3.1 | Project plan with on-going milestones and agency roles completed |  | April 2008 |  | MoJ and MSD meet fortnightly to monitor the progress of this project. |
| 3.3.2 | Scoping and developing Independent Victim Advocate (IVA). |  | July 2008 |  | Government announced funding for this role in February 2008. Scoping and development of the IVA role is underway. |
| 3.3.3 | Introduce specialist enhanced case management staff in all Family Violence Courts |  | April 2008 |  | MoJ is currently assessing other funding streams to fund this initiative. |
| 3.3.4 | Referral and funding for non-mandated stopping violence programme providers for offenders |  | July 2008 |  | Government announced funding for this role in February 2008. MoJ to determine and establish internal funding streams and processes for this initiative. |

### Effective Support Services

| 4.1 MAORI SERVICE WORKFORCE DEVELOPMENT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Social Development |  |  |
| Contributors |  |  | TPK, NGOs, Education |  |  |
| Project Manager |  |  | Ann Dysart |  |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Maori Service Workforce Development. Actions include: - 60 Mäori trained to work with the Mauriora framework. |  |  |  |  |  |
| Deadline |  | June 2008 |  |  |  |
| Purpose |  |  |  |  |  |
| This proposal will allow for continued investment in the training and support of practitioners who work with Mäori whänau/communities where there is violence. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 4.1.1 | Mäori Reference Group established to advise the Taskforce for Action on Violence within Families on the implementation of this and other initiatives aimed at reducing violence in Mäori whänau and communities. |  |  | 1 July 07 | Complete. Meetings ongoing at least every two months. |
| 4.1.2 | Contract in place with Te Korowai Aroha. |  |  | 30 Aug 07 | Complete - ongoing reporting. Contract signed, relationship in place, monitoring and reporting underway to schedule. |
| 4.1.3 | Funding and support for trained practitioners working to prevent violence in Mäori whänau and communities, including assisting Mauri Ora practitioners to meet annual licensing and supervision requirements; |  |  | June 08 | An analysis is underway of the needs of practitioners in this field. It is expected that some of the identified training will be available early in December |
| 4.1.4 | Delivery of training (including Mauri Ora training) to a minimum of 60 practitioners in 2007/08. The trainees will be Mäori Practitioners who are working in both Mäori and non-Mäori provider organisations; |  |  | June 08 | Training is underway for practitioners in Tamaki Makaurau, Manawatu, Taranaki and the Central plateau. Training is also underway in the South Island |
| 4.1.5 | Contract in place for the development of supervision systems and the training of appropriate supervisors for the graduates of the programme. |  |  | Jan 08 | Complete. Contract in place. Development of supervision systems underway, appropriate people currently being selected for training. |

| 4.2 PACIFIC SERVICE WORKFORCE DEVELOPMENT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Social Development |  |  |
| Contributors |  |  | MPIA, NGOs, Education |  |  |
| Project Manager |  |  | Richard Joblin |  |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Pacific Service Workforce Development. Actions include: - Preparation of a project plan to guide workforce training and development in family violence services for Pacific families. |  |  |  |  |  |
| Deadline |  | July 2008 |  |  |  |
| Purpose |  |  |  |  |  |
| This work plans to increase the quality and diversity of services working to eliminate family violence in the Pacific communities. This will include identifying the capacity and capability of this workforce and the avenues needed to further build and support Pacific People in working to stop family violence in Pacific Families. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 4.2.1 | Project plan developed under Pathway to Partnership to address building provider workforce capability and capacity. This will include the development of the Pacific workforce. |  |  | July 2008 | This work is now incorporated under the Pathway to Partnership plan, the project plan for which is currently being confirmed. |

| 4.3 SERVICE DEMAND DATA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Social Development |  |  |
| Contributors |  |  | NGOs, Justice, Health, ACC, Police |  |  |
| Project Manager |  |  | Dorothy Adams |  |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Monitor increases in demand for family violence services resulting from the Campaign to create sustainable responses to increased demand. Actions include: - Develop monitoring framework - Create a system response mechanism. |  |  |  |  |  |
| Deadline |  | October 2008 |  |  |  |
| Purpose |  |  |  |  |  |
| To identify changes in service demand associated with the roll out of The Campaign for Action on Family Violence. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 4.3.1 | Measure initial service impact after the launch of the mass media campaign. |  |  | October 2007 | Completed |
| 4.3.2 | Repeat quantitative measures as above. |  |  | June 2008 | Requested original data sets |
| 4.3.3 | Triangulation of quantitative data from qualitative field work. |  |  | October 2008 | Not commenced |

| 4.4a TRAINING OUR STAFF NB: there are only some agencies for whom it is relevant to complete a training project plan. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | ACC |  |
| Contributors |  |  |  | All agencies |  |
| Project Manager |  |  |  |  |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Taskforce agencies at the point of contact with communities are enabled to respond to victims, observers and perpetrators effectively and safely. Actions include: - Assess available training options - Develop training that meets organisational needs - Plan and implement |  |  |  |  |  |
| Deadline |  | Refer to objective 1.5b |  |  |  |
| Purpose |  |  |  |  |  |
| To ensure frontline ACC staff are equipped with the skills and tools to respond to victims, spectators or perpetrators of Family Violence whether they be staff, clients of ACC or members of the communities in which ACC staff belong. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 4.4.1 | Frontline staff skills developed |  | 31/03/2008 |  | Continuing work underway to scope requirements, attended MSD training |
| 4.4.2 | Establishment of specialist family Violence support people |  | 31/03/2008 |  | Continued scoping of ACC requirements. Initial training provider assesses did not meet requirements. |
| 4.4.3 | Training plan developed for all staff |  | 31/03/2008 |  | Modular based training identified as best solution – in development. |

| 4.4b TRAINING OUR STAFF |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | All agencies |  |
| Contributors |  |  |  | CYF |  |
| Project Manager |  |  |  | MSD contact – Sarah James/Gerard Boomfield |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Taskforce agencies at the point of contact with communities are enabled to respond to victims, observers and perpetrators effectively and safely. Actions include: - Assess available training options - Develop training that meets organisational needs - Plan and implement |  |  |  |  |  |
| Deadline |  |  |  |  |  |
| Purpose |  |  |  |  |  |
| So that frontline social work staff are able to recognise and respond to the dynamics present in situations of family violence. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 4.4.1 | Where identified as part of their professional development plan, frontline social work staff attend a Family Violence workshop |  | As scheduled in training calendar |  | A workshop has been available for some time, this is being reviewed as part of an ongoing quality assurance process and will now be available as part of the specialists stream within the new Practice Induction programme |
| 4.4.2 | Family Violence is discussed in numerous other parts of the new Practice Induction in the workplace learning modules, the classroom based two week Practice Foundation and various learning forums that are part of the new Practice Induction programme |  | As scheduled in training calendar |  | Ongoing |

# First Programme of Action traffic light report

Summary Analysis

The Taskforce for Action on Violence within Families’ (the Taskforce) first programme of action initially consisted of 76 actions which were developed from the Taskforce’s First Report. This was consolidated to 53 actions.

Of these, 22 are complete. Work has commenced on another 21 actions and these are now either ongoing, business as usual, or are annual events. The remaining actions have been subsumed into the Ongoing Programme of Action and, along with other ongoing work, are now reported on and monitored through the regular Monitoring Reports provided to every Taskforce meeting.

Status

Complete = Action complete. May have informed development of work in Ongoing Programme of Action.

OPOA = Work in these actions has been incorporated into the Ongoing Programme of Action, refer to objective number.

Ongoing or Annual = Initial stage complete, currently Ongoing or ‘business as usual’. Some are Annual occurrences.

| # | Action | Agency | Information | OPOA # | Status |
| --- | --- | --- | --- | --- | --- |
| Leadership |  |  |  |  |  |
| 1 | Developing the next Programme of Action (POA) | All TF | OPOA release Feb 2008 | 1.1 | Complete |
| 3 | Successful implementation of POA | All TF | Incorporated into OPOA | 1.1 & 1.1a | Complete |
| 7 | Drawing on Maori and Pacific advisory groups | MSD | Representatives on TF, ongoing MRG and PAG meetings advise the TF. | Led to 1.2, 1.3, 1.6, 1.9, 1.10, 2.4, 4.1, 4.2 | OPOA |
| 8 | Incorporating migrant and refugee perspectives | MSD | Informed OPOA | 1.11 | OPOA |
| 9 | Aligning business planning to reflect Taskforce vision | Sec. | Next round of SOI’s (2008/2009) to be monitored. | 1.1 | Annual Ongoing |
| 12 | Maintain overview of government strategies to ensure goals and activities are complementary with our work | All TF | Business as usual. Secretariat watching brief to ensure TF are aware of all relevant govt strats. All TF agencies info share on new strats, and maintain overview of relevant govt strats. Also links to other actions. | 2.1 2.3 | Complete to date, Ongoing |
| 13 | Family Violence research strategy | FC | Initial report provided Oct 2007, gaps analysis and other areas where work needed. Discussion doc sent early ’08 on topic priority – ongoing work being done through 08 in consultation with other research agendas. | Informs 1.9-1.12 led to 1.13 NGO data | Ongoing |
| 14 | Monitoring the level of family violence in NZ | FC | Refer to Research Strategy | Led to 1.13 & 1.7 | Ongoing |
| 15 | Horizontal learning | MSD | Incorporated into OPOA, Ongoing | 1.7 | OPOA |
| 19 | Evaluate the first POA | MSD | Remaining ongoing actions will be monitored through regular Monitoring Reports. | 1.1a | Complete |
| 21 | Families Commission research programme | FC | 3 year research complete 21a Improving Family Violence surveillance data 21b Elder abuse and neglect research – released Feb ’08 | Informed OPOA | Complete |
| 22 | ACC research programme | ACC | 22a Sensitive claims 22b Effectiveness evaluation 22c Whanau Ora research - extended to June 2008 22d Evidence based guidelines. |  | Complete 22c only is Ongoing |
| Changing attitudes and behaviour |  |  |  |  |  |
| 23 | Review violence in media | FC | Informed development of 2.5 | 2.5 | Complete |
| 29 | Using research to guide Campaign strategy | MSD | The Campaign continues to 2010, with further development being guided by research and evaluation | 2.6 | OPOA |
| 35 | Campaign strategy | MSD / FC | As above | 2.6 | OPOA |
| 36 | Mass media campaign | MSD / FC | Phase one started Sept 07, Phase two started Feb 08. | 2.6 | OPOA |
| 37 | Nurturing leaders… | MSD | Business as usual. Identified (& often funded) through the Community Action Fund. | 2.6 | OPOA |
| 38 | Partnerships with NGOs | MSD/ FC | NGO groups are contracted to be funded for local initiatives. | P2P | Ongoing |
| 39 | Community Action Fund | MSD | Round two complete, 62 initiatives funded in total. Applications for third round closing 10 June 08. | 2.6 | OPOA |
| 40 | Building knowledge – media advocacy etc | MSD/ FC | 40a media advocacy - FACS 40b FV awareness training – also led to 1.5 40c Toolkit re-released 40d White Ribbon day | 2.6 2.6 1.5 2.6 X | OPOA Ongoing Ongoing Complete Annual |
| 4142 | Family violence death reviews | MoH | Ministerial committee to be established by June 2008 | 2.7 | OPOA |
| Ensuring Safety and Accountability |  |  |  |  |  |
| 43 | Sharing information in a way that promotes safety and wellbeing | MoJ | Privacy Act amendment bill scheduled for introduction this year will not include a new information sharing mechanism. The Law Commission and the Privacy Commissioner are to explore alternative approaches to the issue of government information sharing. |  | Initial work complete, Ongoing |
| 44 | Family Violence victims know what support and services are available | MoJ | New comms material developed and distributed at end 07/early 08. Available on Family Court website. |  | Complete |
| 45 | Maximising safety factors when managing court rosters | MoJ | Security policy complete, and was sent to all courts as a circular on 1 April 08. |  | Complete |
| 46 | Increased thresholds for legal aid eligibility | MoJ | Thresholds increased. Legal aid regs in force from Mar ’07. |  | Complete |
| 47 | Begin a review of legal aid remuneration rates | LSA | Review complete. Changes recommended, likely to happen mid ’08. |  | Complete |
| 48 | Improving information courts provide about legal aid | MoJ | Info updated and provided in court info packs, and in DV packs. Court staff also provided with info for public enquiries. |  | Complete |
| 49 | Testing fixed fees for legal aid | MoJ | Testing complete. Recommendation from analysis of testing will go to Agency Board in 2008. |  | Complete |
| 50 | Building safe and effective programmes for couples and families | MSD / MoJ | MoJ in consultation with NZ Assoc of Counsellors, timeframes to be set. |  | Ongoing |
| 51 | Build capacity of interpreters in Courts | MSD / MoJ | More interpreters available in courts. Business as usual to continue building availability. |  | Complete |
| 52 | Investigate introduction of advocates in courts | MWA / MoJ / MSD | MoJ and MSD have reviewed the MWA report. MoJ and MSD will develop an independent victim advocate role in 2008 for implementation in the eight Family Violence Courts in April 2009. | Informed 3.3 | Report in draft Ongoing |
| 53 | Enhanced ability for courts to contact victims directly | MoJ / Police | Already possible, MoJ and Police will continue improving standardised process for CSV1 compliance and referral. |  | Complete |
| 54 | Review purchasing plans for programmes | MoJ | Currently in 2008 tender round. |  | Complete |
| 55 | Improve process for prosecutions for non-attendance at programmes | MoJ / Police | Memorandum of understanding between MoJ and Police for the transfer of prosecutions to Police signed. Transfer completed by June 2008. |  | First stage complete, Ongoing |
| 56 | Establish four additional Family Violence Courts | Judiciary / MoJ | Two further to be established in 2008. | 3.1 | Complete |
| 57 | Family Violence Courts Evaluation | MoJ | Waitakere and Manukau reports combined early 2008. Draft operating guidelines issued for consultation Dec 2007. Report due to TF June 2008. | 3.2 | First stage complete, Ongoing |
| 58 | Forum to identify best practice for information exchange | MoJ | Held March 2007. Best practice ideas generated informed development of guidelines by agencies. |  | Complete |
| 60 | Enforcement of protection orders – police training, performance measures and policies | Police | Initiatives on addressing family violence “big picture” (which include PO’s) complete. Ongoing work continuing. 60a Training 60b Performance measures 60c National investigation and prosecution policies. Protection Orders research response also monitors this work, next report due to Minister end August ‘08. | Many & 4.4 | Many initiatives complete, Ongoing |
| 61 | Support and training for lawyers working in family violence-related areas | Judge Boshier | Workshops for FC lawyers done in ’07, Law Soc also produced a resource booklet. |  | Complete |
| 62 | Define options to improve information sharing between agencies and the Courts | MoJ | Much information sharing already possible (judges in particular). Further work on information sharing will be undertaken as part of the Ministry’s ongoing policy work on domestic violence. | Part of 3.3 | First stage complete Ongoing 2008 & beyond |
| 63 | Simplify application forms for Protection orders | MoJ | Explanatory leaflet complete May ’08. Any changes to the form can only happen by regulation change, which will be explored following amendments to the DVA. |  | First stage complete, Ongoing 2008 & beyond |
| 64 | Improve the use of security resources available to courts | MoJ | A budget bid has been submitted for new security resources and initiatives. If the bid is successful these new initiatives will be implemented at all Courts (tbc May 08). |  | First stage complete, Ongoing 2008 & beyond |
| 65 | Consider an office to provide DVA-specific legal services | LSA MoJ | Currently developing objective and milestones as part of business planning. |  | Ongoing 2008 & beyond |
| 66 | Determine level of attendance and performance of perpetrators at programmes | MoJ | MoJ currently collating and analysing data that will illustrate how attendance at programmes by respondents are managed. Due to complete analysis & report to TF in June ‘08. Result will be used to improve processes and reporting, and improve the management of attendance at programmes by respondents to protection orders. |  | Ongoing 2008 & beyond |
| 67 | Develop options to ensure perpetrators attend and complete programmes | MoJ | Further phase of Action 66. |  | Ongoing 2007/2008 & beyond |
| 68 | Information for perpetrators on programmes | Police | Information distributed |  | Complete |
| 70 | Ensure the range of programmes matches the profiles of perpetrators | Corrections / MoJ | Corrections have completed a comparative analysis of violence programmes in prison (including the violence components of generic programmes) with the DV programmes which offenders based in the community are referred to. Options to potentially address gaps in programmes for prisoners with DV-related offences formulated. Currently analysing these options. On track to meet the 30 June deadline. |  | Ongoing 2007/2008 & beyond |
| 71 | Local Case Collaboration (FVIARS) | CYF / Police | FVIARS phase one complete, second phase - nationwide roll-out underway by mid 2008. | Informs 3.3 | Phase one complete, Ongoing 2008 & beyond |
| Effective Support Services |  |  |  |  |  |
| 72 | Govt investing $9 million over the next four years | MSD | 2006/2007 funding complete 2007/2008 continuing funding of contracts as above, from baseline. |  | Dev. Complete Ongoing to 09/10 |
| 73 | Develop new funding model | MSD | Pathway to Partnership (P2P) developed and ongoing. $20.4 million allocated in 2007. $446 million announced 12 Feb 2008 to fund essential NGO child and family services. | 2.1 | Complete Ongoing |
| 74 | Cost family violence and family support services | MSD | Developed as part of P2P as above | 2.1 | Complete |
| 75 | Build on existing workforce and organisational development initiatives | MSD | P2P Funding announced on 12 Feb 2008 to build a sustainable NGO sector | 2.1 | Dev. complete. Ongoing 2008 & beyond |
| 76 | Continue to promote the use of integrated contracts | MSD | Funding for Outcomes developed & implemented. These contracts now part of FACS core business under the Integrated Contracts team. |  | Complete |

# How this report works

The Ongoing Programme of Action Monitoring Report is usually organised into two sections:

- A summary section – which provides an overview of the key highlights over the previous two months, and identifies the hotspots that need to be monitored closely over the upcoming two months to ensure objectives remain on track.

- A monitoring report section – which includes two key parts:

  - A summary of the progress of each objective over the last three months and an overview of the work that is expected to occur over the next three months.

  - Summary information from the project plans for each objective.

A third section in this report updates progress on ongoing actions from the First Report, the Taskforce’s first programme of action. This section is in a format similar to a traffic light report.

The overall report format is new and still evolving. There are some objectives that require more ongoing information. The Secretariat will work to extend this information with each report.

We have tried to layer the information provided in the report so that Taskforce members can get a snapshot of where things are at and refer to the Monitoring Report section for more detail on each objective, its milestones, and the responsible project managers within each agency if they wish to follow work up or find out more information.

The Taskforce’s planning and reporting hierarchy consists of the following:

- objectives – specific work that has been signalled in the programme of action

- actions –  specific work signalled in the programme of action, as part of an objective and/or in the Taskforce’s work programme which sits beneath the programme of action

- key milestones – taken from individual agency project plans.

- We have also introduced a formal variation process, which aims to:

- maintain the integrity of the Taskforce’s programme of action

- ensure there is transparent communication within the Taskforce about changes to objectives and/or actions

- ensure the objective and actions remain relevant to the Taskforce and its priorities.

The variation process involves:

- completing the attached variation template

- consulting with appropriate Taskforce agencies over the changes to gain agreement and buy-in (this will be left to the responsible Taskforce agency seeking a variation to determine)

- sending a draft of the variation to the Secretariat to review before it is finalised, the Secretariat will then provide feedback and the variation can be finalised

- getting the responsible Taskforce member to sign the variation (thereby finalising the variation)

- sending the finalised variation to the Secretariat

- the Secretariat will brief the Taskforce Chair and seek his sign-off

- the Secretariat advise the agency seeking a variation of the outcome

- the outcome is noted in the Taskforce monitoring report.

A formal variation is required when a Taskforce agency wants to change an objective, action or both.  Formal variations are not required to change milestones, however, any milestone changes need to be provided to the Secretariat so that a log can be kept and changes can be tracked over time. Formal variations are not required for milestones because milestone changes should not compromise an objective and its associated actions.

A formal variation needs to be completed if the deadline for completion of an objective and associated actions changes. This is because the overall objective and actions are compromised.

The variation template is attached to this report, an electronic copy of which can be obtained from the Taskforce Secretariat.

Reporting frequency

Ongoing Programme of Action Monitoring Reports will be produced for each Taskforce meeting. If a Taskforce meeting is changed to a workshop then a report will still be produced but will be circulated in hard copy only.

Other information

- The information in the monitoring report centres on the key milestone information provided by each Taskforce agency.

- To ensure the monitoring report remains current, as each milestone is reported complete it will be dropped from the report. The Secretariat will keep a record of all milestones so that this information can be used at a later date, if necessary.

| To | Peter Hughes | Date |  |
| --- | --- | --- | --- |
| From |  |  |  |
| Security Level | In Confidence |  |  |
| request to amend Work Programme Objective or Action |  |  |  |
| Action | For your approval |  |  |

I am seeking your approval to change an objective or action from the work programme for the Taskforce for Action on Violence within Families.

Current Deliverable:

[Insert Project / Work Programme Objective and/or Action]

[Insert current milestone/s (from project plan template)]

Changed to:

[Insert Project / Work Programme Objective and/or Action]

[Insert new milestone/s (also complete new project plan template)]

Reasons for a Variation Request

A variation to this deliverable has become necessary as:

- [please insert reason/s for variation]

Consultation

In seeking a variation to this deliverable, I have consulted with the following people:

| Name | Position and organisation |
| --- | --- |

Impact

The impacts in agreeing to this change are:

- [add details of any impact such as reporting to Cabinet, other key project timeframes, budget initiatives, reputation, legislation.]

The impacts in not agreeing to this change are:

- [add details of any impact such as reporting to Cabinet, other key project timeframes, budget initiatives, reputation, legislation.]

Recommendation

It is recommended that you:

- agree to a variation to an objective or action found in the Taskforce’s work programme

[Insert Project / Work Programme Objective and/or Action]

[Insert new milestone/s (also complete new project template)]

Approve / Decline

| Xxxxx (Taskforce representative) |  |  |
| --- | --- | --- |
| XXXXX (Taskforce agency) |  | Date |

| Peter Hughes |  |  |
| --- | --- | --- |
| Chair |  | Date |
| Approved  Not Approved  |  |  |