Ongoing Programme of Action

Monitoring Report

May 2009

Prepared by the Secretariat for the Taskforce for Action on Violence within Families

# Contents

Contents	1

Summary	3

Highlights	3

Hotspots	5

Variations	6

Monitoring Report	9

Leadership	11

1.1  Facilitation of the Ongoing Programme of Action	11

1.2  Mäori Programme of Action	12

1.3  Pacific Programme of Action	13

1.4  Child Maltreatment	14

1.5  Family Violence Free Workplaces	16

1.6  Iwi-Led Crime Prevention	18

1.7  Family Violence Clearinghouse	19

1.9  Mäori Research Agenda	21

1.10  Pacific Research Agenda	22

1.11  New Migrant and Refugee Research Agenda	23

1.12  Elder Abuse	24

1.13  Data on NGO Service Delivery	25

Changing Attitudes and Behaviour	28

2.1  Kia Puäwai	28

2.2  Improving Attachment	28

2.3  Conduct Disorder / Severe Anti-Social Behaviour	29

2.4  Curriculum Development	31

2.5  Violence in the Media	35

2.6  Campaign for Action on Family Violence	35

Ensuring Safety and Accountability	40

3.1  Family Violence Courts	40

3.3  Social Services Supporting Courts	41

Effective Support Services	44

4.1  Mäori Service Workforce Development	44

4.2  Pacific Service Workforce Development	44

First Programme of Action update	46

How this report works	52

Variation	54

# Summary

- The Taskforce for Action on Violence within Families’ (the Taskforce) first programme of action initially consisted of 76 actions, which were later consolidated to 53 actions. A progress summary on these 53 actions is provided towards the end of this report.

- The Taskforce’s Ongoing Programme of Action (OPOA) originally consisted of 31 objectives which form the Taskforce’s work programme. Of the original 31 objectives, 22 remain. To meet each objective, actions and milestones have been identified. This report provides a progress report against the objectives, actions and milestones.

- For more information on this report, how it is organised and the formal variation process, please refer to the “How this report works” section at the end of the document.

Objective status

| On track | 13 |
| --- | --- |
| Project re-scoped or minor delay (less than one month) | 3 |
| Alerts or Variations | 6 pending |
| Total number of Objectives remaining | 22 |

## Highlights

This section provides an overview of key Taskforce initiatives for the reporting period of February/March 2008 to May 2009.

### Leadership

### Domestic Violence Act 1995 Review

The Domestic Violence (Enhancing Safety) Bill was introduced into the House on 16 December 2008, and referred to the Justice and Electoral Select Committee, which sought public submissions on the Bill by 27 February 2009.

The remaining proposals in the Domestic Violence Reform Bill have been reinstated on the 2009 Legislative Programme and will be considered at a later stage.

### Changing Attitudes and Behaviour

### Campaign for Action on Family Violence

The Campaign has been working in partnership with Women’s Refuge to promote the “It is OK to Ask for Help” message (also supported by the Refuge’s “Championing Social Change” strategy). The first project under this partnership arrangement has been the promotion of “Tiakina to Whanau – Keep Your Whanau Safe” message to Maori audiences at the 2009 Te Matatini Kapa Haka Festival in Tauranga. Kapa haka teams wore Campaign-branded t-shirts and committed to take the “It is OK to Ask for Help” message back to other events in their towns and communities. Local champions for change have been a cost effective means of promoting positive messages about Family Violence.   Refuge has reported overwhelming support of the Campaign at the Festival, and estimate that we engaged face-to-face with an estimated 15,000 people at the event.

The Super Maori Fullas are brothers from Northland who decided to ride their Harley Davidsons from Cape Reinga to Bluff and back, encouraging others to live a violence free life. Supported by, and promoting, the It’s not OK Campaign, they finished their Ride Against Family Violence on Tuesday 24 February in Kaitaia.  The brothers rode for 18 days and attended 22 community events sharing their message of love and respect for all.  The Super Maori Fullas are now considering how to keep the momentum up and build on the successes of their first road trip.  As well as planned events the brothers had many informal encounters with curious members of the public, and inspired people from all walks of life to share their own story and look on family life in a new way.  They were a big draw card for the news media and stories appeared nationwide and on national television.

## Hotspots

This section highlights objectives that are subject to variation or have been identified as areas of risk. All objectives not mentioned in this section are on track to be completed as planned.

### Alerts

This table highlights areas that have been identified as at risk of not being delivered as planned.

| Objective | Title | Issue | Mitigation |
| --- | --- | --- | --- |
| 1.10 | Pacific Research Agenda | Delayed. Variation submitted, ongoing consultation. | A variation has been drafted for Taskforce consideration. |
| 1.7 | Family Violence Clearinghouse | Delayed. Deadline change requested through variation process. Variation submitted May 2009. | A variation has been drafted for Taskforce consideration. A new deadline of December 2011 is proposed. |
| 2.2 | Improving Attachment | Scope and deadline change. Due to issues arising during the initial project scoping. | A variation has been drafted for Taskforce consideration. A new deadline of July 2010 is proposed. |
| 2.5 | Violence in the Media | Delayed. The Objective will not be complete by the current deadline of February 2009. | A variation has been drafted for Taskforce consideration. A new deadline of November 2009 is proposed. |
| 3.3 | Social Services Supporting courts | Delayed. The Objective will not be complete by the current deadline of April 2009. | A variation will be drafted for Taskforce consideration, following Ministerial direction. |
| 4.2 | Pacific Workforce Development | This work is part of the Pathway to Partnership work, which is currently awaiting Government direction. | Awaiting Government direction. |

### Upcoming Objective Deadlines (next two months)

This table highlights objective deadlines that are due over the next two months, or that have been completed and further deadlines need to be defined. If deadlines are not likely to be met, agencies should contact the Secretariat to discuss a possible variation.

| Objective | Title | Agency | Objective Deadline |
| --- | --- | --- | --- |
| 1.4 | Child Maltreatment | Office of the Children’s Commissioner / Ministry of Social Development | 30 June 2009 |
| 1.7 | Family Violence Clearinghouse | Ministry of Social Development | June 2009 (Variation submitted) |
| 1.11 | New Migrant and Refugee Research Agenda | Ministry of Social Development | April 2009 |
| 4.1 | Mäori Service Workforce Development | Ministry of Social Development | June 2009 |

## Variations

Variations are formal requests for changes to objectives and/or actions in the Taskforce’s Ongoing Programme of Action. The Taskforce approve major changes at Taskforce meetings. Variations are required for major changes, i.e. those that relate to the outcome of a piece of work, or the overall deadline for completion of the work. Any changes to key milestones will be flagged in the Monitoring Report.

Variation Request Process

The table below lists the variations that need to be discussed and agreed by the Taskforce at a future Taskforce meeting.

| Objective | Title (lead agency) | Due | Variation summary | Status |
| --- | --- | --- | --- | --- |
| 1.7 | New Zealand Family Violence Clearinghouse (MSD) | June 2009 | Final deadline change. The NZFVC is seeking approval to extend the deadline to December 2011. | A variation has been submitted for Taskforce consideration. |
| 1.10 | Pacific Research Agenda (Ministry of Pacific Island Affairs (MPIA)) | TBC | Outcome and date change. The MPIA is seeking to withdraw from this action, and focus on supporting the Pacific Programme of Action developed by the Pacific Advisory Group (PAG). | A variation was submitted in November 2008. In consultation with key stakeholders. |
| 2.5 | Violence in the Media (Families Commission) | February 2009 | Final deadline change. A new deadline of November 2009 is proposed. Objective and Actions will remain the same. | A variation has been submitted for Taskforce consideration. |
| 3.3 | Social Services Supporting Courts (Ministry of Justice (MoJ)) | April 2009 | Change to be confirmed. An extension to the deadline is required. | A variation is to be submitted for Taskforce consideration. |
| 4.2 | Pacific Service Workforce Development (Ministry of Social Development) | July 2008 | Final deadline change. Initial deadline was met; however this project was incorporated in the Pathway to Partnership work on workforce provider capacity and capability. | A variation has been submitted for Taskforce consideration. |
| Action 43 (First Report) | Sharing information in a way that promotes the safety and well-being of victims and their families (MoJ) |  | MoJ is seeking to remove this action point from the Taskforce work programme. This is necessary as the work to review the Privacy Act is now being undertaken by the Law Commission and the Privacy Commissioner. | A variation is to be submitted for Taskforce consideration. |
| Action 62 (First Report) | Options to improve information sharing between agencies and the District Court and the Family Court (MoJ) |  | Project to be placed on hold. It is proposed that further work on this action be incorporated into a wider review about to be undertaken by MoJ. | A variation is to be submitted for Taskforce consideration. |
| Action 63 (First Report) | Simplify the application form for protection orders (MoJ) |  | An information sheet on the DVA application process has been developed and is available online. It is proposed that further work on this action be incorporated into a wider review about to be undertaken by MoJ. | A variation is to be submitted for Taskforce consideration. |
| Action 64 (First Report) | Improve the use of security resources available to the courts (MoJ) |  | MoJ is seeking to remove this action point from the Taskforce work programme, and revert to business as usual. | A variation is to be submitted for Taskforce consideration. |
| Action 67 (First Report) | Develop options to ensure perpetrators attend and complete programmes (MoJ) |  | MoJ is seeking to remove this action point from the Taskforce work programme. It is proposed that further work on this action be incorporated into a wider review about to be undertaken by MoJ. | A variation is to be submitted for Taskforce consideration. |

Approved variations

This table includes all approved variations of objectives from the Ongoing Programme of Action.

| Objective | Title | Variation summary | Status |
| --- | --- | --- | --- |
| 2.4 | Curriculum Development | The Objective remained the same, changes to the actions required. | Approved 28 March 2008. |
| 3.3 | Social Service Supporting Courts | The Objective remained the same, changes to the actions required. | Approved 4 April 2008. |

### Complete or removed objectives

The table below lists the objectives that have been removed from the Monitoring Report due to being completed, merging, or now being business as usual.

| Objective | Objective title | Reason for removal | Lead agency | Removed from which report |
| --- | --- | --- | --- | --- |
| 1.8 | Case studies characterising good practice | Complete. | Ministry of Social Development (MSD). | February 2009 |
| 2.7 | Family Violence Death Reviews | Complete. The Family Violence Death Review Committee will report regularly to the Government. | Ministry of Health (MoH). The Secretariat sits within MoH. | February 2009 |
| 4.3 | Service Demand Data | Complete. | MSD. | February 2009 |
| 4.4a | Training our Staff | Combining Objective 4.4a into 1.5 was recommended as the two Objectives cover the same action and outcomes. | ACC Human Resources. | February 2009 |
| 1.1a | Mapping the Ongoing Programme of Action | Outcomes covered in Objective 1.1 through monitoring of the work of the Taskforce by the Secretariat. | Non-Government Organisations (NGOs). | November 2008 |
| 1.5 a, b & c | Family Violence Free Workplaces | Three sub-sections merged into one (Objective 1.5). | ACC, MSD and Police. | First merged in November 2008 |
| 3.2 | Protocols for Family Violence Courts | Complete. | MoJ | November 2008 |
| 4.4b | Training of Staff (Child, Youth and Family (CYF)) | Business as usual, will be monitored within CYF. | CYF | November 2008 |

# Monitoring Report

The following section outlines progress on each key milestone and provides an update on work undertaken in the previous three months (January to March 2009) and work which is upcoming in the next three months (March to May 2009).

## Milestone updates and three month summaries

This section provides updates on each milestone, and updates on both work undertaken in the previous three months and outlines work planned for the upcoming three months.

### Leadership

| ### 1.1 FACILITATION OF THE ONGOING PROGRAMME OF ACTION (OPOA) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Taskforce Secretariat / All Taskforce agencies |  |
| Project Manager |  |  |  | Carra Hamon |  |
| First Programme of Action reference |  |  |  | Action 3 |  |
| Objective and actions (as per Work Programme) Facilitation, implementation and strategic engagement of the Ongoing Programme of Action for specific groups and across all sectors in New Zealand. Actions include: - stewardship of the Ongoing Programme of Action work programme - stewardship of children specific work programme - stewardship of all other work programmes. |  |  |  |  |  |
| Objective deadline |  | Ongoing |  |  |  |
| Purpose To successfully monitor and ensure implementation of the Ongoing Programme of Action. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.1.7 | Protection Orders update to be sent to Minister. |  | April 2009 |  | Completed, draft sent to Taskforce in April. May be sent to the Minister later in the year. |
| 1.1.16 | 1 April Taskforce meeting facilitated |  | 1 April 2009 |  | Complete. |
| 1.1.17 | Monitoring Report for May 2009 prepared. |  | 22 May 2009 |  | Complete. |
| 1.1.18 | 3 June Taskforce meeting facilitated |  | 3 June 2009 |  | On track. |
| 1.1.19 | Facilitate additional meetings |  | July 2009 |  | On track. Additional meetings on Dashboard of indicators and Efficacy of Stopping Violence Programmes. |
| Progress to date (previous 3 months work) - 1 April Taskforce meeting completed. - Planning for 3 June meeting on track. - Initial planning meetings on the Dashboard of Indicators, and Efficacy of Stopping Violence Programmes took place in April and May. Current ongoing work (next 3 months) - Preparing the Monitoring Report for the 3 June 2009 Taskforce meeting. - Planning for 3 June Taskforce meeting. - Additional meetings on the Dashboard of Indicators and Efficacy of Stopping Violence Programmes to take place in June/July 2009. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 1.2 MĀORI PROGRAMME OF ACTION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agencies |  |  |  | Mäori Reference Group (MRG) Ministry of Social Development (MSD) |  |
| Contributors |  |  |  | Te Puni Kökiri, NGOs |  |
| Project Manager |  |  |  | Ann Dysart (MSD) |  |
| First Programme of Action reference |  |  |  | Action 7 |  |
| Objective and actions (as per Work Programme) A Programme of Action focused on eliminating violence in Mäori whänau is developed. Actions include: - developing a Mäori Programme of Action - ensuring the leadership and ownership of the actions at all levels of Te Ao Mäori - ensuring all designated actions are monitored and achieved. |  |  |  |  |  |
| Objective deadline |  | June 2013. |  |  |  |
| Purpose - To develop a process and plan that engages all areas of Te Ao Mäori in owning and addressing the issues of Family Violence and Child Abuse - To progress implementation of Mäori Reference Group’s (MRG) Action Plan in order to achieve zero tolerance of whänau violence. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.2.6 | Develop initial Whänau Ora Indicators. |  | June 2009 |  | Project Plan developed identifying key work areas as follows: - develop a discussion document defining Whänau Ora - provide and co-ordinate Regional Hui - identify and work with existing Whänau Ora indicator workings. |
| 1.2.7 | Develop and publish initial Leadership Toolkit. |  | June 2009 |  | A Communications Plan has been developed providing for key work areas as follows: - rangatahi Hui - stocktake of current relevant communications material for Mäori - develop key messages for Mäori. |
| Background The Taskforce’s Mäori Reference Group (MRG) has developed a Mäori Programme of Action (MPOA) which was presented to the Taskforce. This contained a five year plan for 2008-2013, that was presented and agreed by the Taskforce in August 2008. Progress to date (previous 3 months work) - Initial meeting of the Strategic Mäori reference group with Minister Turia. - Ongoing research to identify the range of wellbeing indicators currently in use both within NZ and internationally. - Community engagement identifying useful tools for inclusion within Resource Kete. - Scan of work currently and previously undertaken in the area of Whanau Ora. - Input into a range of related initiatives including Child Maltreatment, Mäori research agenda, Justice and Police initiatives. Current ongoing work (next 3 months) - Development of Whänau Ora Indicators: - Development of Leadership Resources - Continue to input into other policy work as appropriate - Support the work of the Mäori research agenda - Continue to engage and support the work of Whanau, Hapu and Iwi in ensuring leadership and change. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 1.3 PACIFIC PROGRAMME OF ACTION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Pacific Advisory Group (PAG) Ministry of Social Development (MSD) |  |
| Contributors |  |  |  | Ministry of Pacific Island Affairs, NGOs |  |
| Project Manager |  |  |  | Liz Tanielu (MSD) |  |
| First Programme of Action reference |  |  |  | Action 7 |  |
| Objective and actions (as per Work Programme) A Programme of Action focused on eliminating violence in Pacific families is developed. Actions include: - develop a Pacific Programme of Action (PPOA). - hold discussions with agencies to confirm action areas of responsibility and process for implementation. - develop the leadership action area to be coordinated by MSD with PAG. |  |  |  |  |  |
| Objective deadline |  | June 2013 |  |  |  |
| Purpose To develop and implement a plan to address family violence within Pacific families. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.3.9 | Develop resources for Pacific organisations, families and communities to increase awareness and understanding of causes and effects of family violence. |  | June 2009 |  | Resource plan identified. Work underway to develop priority resource materials. |
| 1.3.10 | Facilitate opportunities to bring together Pacific community leaders to effect attitudinal and behavioural change. |  | June 2009 |  | On track. |
| 1.3.11 | Facilitate opportunities for dialogue between Pacific leaders and stakeholders and mainstream influencers to ensure Pacific communities are actively and consistently involved over the long term. |  | June 2009 |  | This milestone is due for completion in 2009/10 but work has commenced through initial discussions with MPIA on a communications strategy and process for implementation. Opportunities for dialogue have commenced. |
| Progress to date (previous 3 months work) - First PAG meeting for 2009 was held on 26 and 27 April. The meeting included a discussion with Hon. Tariana Turia on priorities for Pacific Peoples. - Resource priorities identified and actions underway. - Community engagement process has commenced. Discussions were held with other agencies to align their community engagement processes and to identify opportunies for joint venture projects. - Advice provided to projects such as Pathways to Partnership, Child Maltreatment, Pacific Research Agenda and Family Violence Court Community Service. Current ongoing work (next 3 months) - Continue with the development of identified priority resources. - Follow through on the community engagement process. - Work with agencies to determine lead and supporting roles for the implementation of the Pacific Research Agenda work programme. - Continue to provide advice to projects such as Pathway to Partnership, Child Maltreatment and the Campaign for Action on Family Violence. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 1.4 CHILD MALTREATMENT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Office of the Children’s Commissioner |  |
| Contributors |  |  |  | MSD, NGOs, NZ Police, Ministries of Justice, Health and Education |  |
| Project Sponsor |  |  |  | Dr John Angus |  |
| Project Manager |  |  |  | Ruth Palmer (MSD) |  |
| First Programme of Action reference |  |  |  | N/A |  |
| Objective and actions (as per Work Programme) The objectives of the second phase are to agree and then carry out the work programme. The work programme comprises an integrated, cross sector approach to preventing child maltreatment. It draws on a growing evidence and knowledge base about the impacts of maltreatment. |  |  |  |  |  |
| Objective deadline |  | 30 June 2009 (second phase) |  |  |  |
| Purpose The Taskforce has agreed to give priority to the prevention of child maltreatment over the next three years, and has agreed the scope, focus and priorities of the proposed work programme. The purpose of the work for 2008 – 2009 is to: - enhance the contribution of the Health, Education and Social Services sectors to prevention of child maltreatment - understand better and take actions to reduce the incidence and prevalence of neglect, in particular of 0 – 5 year olds - strengthen effective community responses. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.4.7 | Project plans for the nine projects are completed. |  | Sept 2008 |  | Project plans for the five priority plans (1.4.8-9 and 1.4.12) are complete. Please see below for the remaining four project plans (‘Progress to date’). |
| 1.4.8 | Complete the review of the Health, Education and Social Service Sector Contributions to child maltreatment (3 of the 9 projects). |  | 31 Mar 2009 |  | All three reviews are completed. A report is currently being prepared for the next Taskforce meeting of the recommendations and findings from these reviews. |
| 1.4.9 | Undertake research into neglect. |  | 30 Jun 2009 |  | On track. |
| 1.4.10 | Prepare advice on how development of the Campaign can further contribute to the prevention of child maltreatment. |  | 31 Aug 2008 |  | Ongoing consideration of national media work in the context of the future development and resourcing of the Campaign as a whole. |
| 1.4.11 | Develop the Campaign to include more specific actions on changing attitudes and behaviours around child abuse and neglect. |  | 30 Jun 2009 |  | On track. |
| 1.4.12 | Take actions to work with communities to strengthen their preventive responses to child maltreatment including: - gathering evidence on what works by 31 December 2008 - providing greater support for successful community approaches by 31 March 2009 - supporting philanthropic sector plans for a trial of new approaches and commencing an evaluation of any trial by 30 June 2009. |  | 30 Jun 2009 |  | On track. |
| Background The Ongoing Programme of Action includes developing a work programme on child maltreatment (including child sexual abuse) that: - focuses on improving outcomes for children - takes account of the different types of child maltreatment - identifies priority areas where the Taskforce can make a difference. Progress to date (previous 3 months work) - Reports are being prepared on the findings and recommendations of the reviews of the Health, Education and Social Services Sectors. - A report has been prepared outlining the findings of the Working with Communities project. - Work continues on the Neglect literature review. Current ongoing work (next 3 months) - Continue work on the agreed 2009 outputs, notably: sector reviews, undertaking the research on neglect, and analysing the information obtained on community approaches. - Finalise the recommendations of the sector reviews and commence work on presenting these findings to the next Taskforce meeting. - Complete research on neglect. Timing / Ongoing / Recommendations / Conclusions Status = on track |  |  |  |  |  |

| ### 1.5 FAMILY VIOLENCE FREE WORKPLACES (MSD / ACC / NZ Police) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | MSD, ACC, Police |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | David Dick (MSD), Danielle George (ACC), Carol Train (Police) |  |
| First Programme of Action reference |  |  |  | N/A |  |
| Objective and actions (as per Work Programme) Family Violence Free Workplaces are developed and implemented through HR policy; link to the Campaign, model for other agencies, role model for public and other workplaces. Actions include: - develop policy - put in place tools and resources - train contact people/family violence co-ordinators - implementation - develop a model for replication in the public sector and private sector. |  |  |  |  |  |
| Objective deadline |  | May 2012 |  |  |  |
| Purpose Family Violence Free Workplaces means staff in these workplaces are aware of and supported with family violence issues. These workplaces are expected to provide low cost, high impact prevention and recovery opportunities for members of the workplace who are affected by family violence. They may be victims, observers or perpetrators. Implementing Family Violence Free Workplaces is expected to decrease workplace stress and increase workplace productivity by empowering and supporting victims and observers of family violence and channelling perpetrators through appropriate channels to help them change their behaviour. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.5.1 | Policy developed and agreed. |  | Dec 2008 |  | Delayed. |
| 1.5.2 | Tools, resources and training to support and promote the policy, and raise awareness of family violence are developed, agreed, and implemented. |  | Dec 2009 |  | On track. |
| 1.5.3 | Assess and evaluate agency programmes. |  | Dec 2010 |  | On track. |
| 1.5.4 | Develop Blueprint/model for implementing Family Violence Free Workplaces in public, private and non-government sectors. |  | June 2011 |  | On track. This Blueprint will be a collaborative piece of work between Police, MSD and ACC. |
| Context and background MSD, ACC and NZ Police have been working toward Objective 1.5 since the development and agreement of the Ongoing Programme of Action in late 2007. The three organisations have met regularly to work together, and share knowledge and learning, and will continue to do so. MSD HR liaise with Project Managers from all three organisations to provide an update for each Monitoring Report. The collaboration reflects the overall objective of developing a Family Violence Free Workplaces blueprint for replication in the public and private sectors. Completed work (since 2007) MSD - General awareness information sessions on family violence held for National Office staff. - In-depth sessions on family violence held for HR staff. - Distributed Campaign posters, including poster display in MSD National Office foyer. - Distributed resources eg. ‘Are you OK?’ booklets. - Established Family Violence Peer Support Programme in Work and Income. - Published resources and information about referral service on the intranet. - Published a highly visible ‘It’s not OK’ advert on intranet homepage. - Published stories on front page of staff intranet about the ‘It’s not OK’ campaign. - Included family violence campaign ‘It’s not OK’ page in 2008 and 2009 Calendar for staff. - Ensured the provision of family violence counselling as a criterion in the RFP for an EAP provider. - Provided service line consultation on the draft Policy and Managers Guidelines. - Draft Policy and Managers’ Guidelines provided to particular business units for consideration on the scope of these documents. - Provided staff with white ribbons on White Ribbon Day (25 November 2008). ACC - Delivered in-depth training on family violence delivered to HR staff. - Developed partnership approach with Stratos. - Developed a support package and launched with Stratos partnership to staff as part of Safety NZ Week – Safety in the Home, available on intranet and via text service. - Published managers’ guide on the intranet. - Developed Policy and launched it as part of Staff Wellbeing Programme. - Re-launched support package and the Policy to complement White Ribbon Day (25 November 2008). - Chief Executive championing of messages across ACC. - All programmes on track and in place across ACC. - Developed an ongoing communications plan to ensure staff awareness and to track progress of programme. Police - Timeline developed with key milestones. - Internal working group established (consisting of HR (lead), Operations group, Policy group, Training Service Centre and District representation). - Draft policy consultation phase ongoing. - Working group discussed feedback and made required changes to draft Policy. - Draft policy was considered in a wider context. - Pursued a tool for employees to report and seek assistance for a range of issues including family violence. Progress to date (previous 3 months work) MSD - Reviewed scope of the draft Policy and Managers’ Guidelines. - Refreshed the language of the Policy based on recent feedback. - Published a new highly visible ‘It’s not OK’ advert on intranet homepage for 2 months. ACC - Nothing to report. Police - Completed draft Policy following consultation phase. - Decision made to not approve Policy and instead develop a toolbox of resources for staff and their families. Current ongoing work (next 3 months) MSD - Seek sign off of the Policy and Managers’ Guidelines from the Leadership Team. - Material and resources will support the launch of the Policy and Guidelines (pending sign off). ACC - Continuing to monitor the effectiveness of the support package at the six month mark (end of June 2009). - Continuing to research the development of the workplace Policy that extends influence to outside the workplace. Police - Work with EAP provider to establish a family violence support package for employees and their families. - Develop a toolbox of resources including training and education on family violence. - Establish support networks to ensure employees and their families feel supported and are aware that they can ask for help. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 1.6 IWI-LED CRIME PREVENTION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | New Zealand Police |  |
| Contributors |  |  |  | Iwi, NGOs, Te Puni Kökiri, MoJ (including Crime Prevention Unit) |  |
| Project Manager |  |  |  | Wally Haumaha |  |
| First Programme of Action reference |  |  |  | N/A |  |
| Objective and actions (as per Work Programme) Iwi-led crime prevention plans which have a focus on the prevention of family violence. Actions include: - provide support to Iwi to develop plans - Iwi-led crime prevention strategies developed in accordance with each Iwi’s identified needs, values and timeframes - Mäori Family Violence scoping studies. |  |  |  |  |  |
| Objective deadline |  | The NZ Police state that this is an iterative and evolving process that is being driven by Iwi. Precise deadlines are neither available nor appropriate at this stage. |  |  |  |
| Purpose In absolute numbers, a high number of Mäori churn through the criminal justice system every year. A new framework for action is being developed by Mäori with assistance from officials. That new framework is Iwi-led Crime Prevention Plans (ICPPs). ICPPs take a long-term, incremental approach to improving Mäori criminal justice outcomes. They are led by Iwi, with assistance from officials. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.6.1 | Iwi populate their crime prevention plan templates. |  | Ngati Whatua me Tainui ki te Tonga, and, Ngai Tahu have set deadlines for first drafts of June 2009. |  | Writers appointed by Iwi are not using the template provided, so officials will condense and refine the core documents from Iwi into the template, once drafts are received. |
| 1.6.2 | Officials condense those templates into A3 summaries. |  | No deadline |  | Pending. |
| 1.6.3 | Summaries presented back to Iwi for confirmation. |  | No deadline |  | Pending. |
| 1.6.4 | Ministerial briefing paper to Ministers of Justice, Police and Mäori Affairs. |  | March 2008 |  | Complete |
| 1.6.5 | Ngapuhi and Te Arawa present their draft plans to Justice Sector Chief Executives Forum |  | April 2009 |  | Complete |
| Background recent work (2007/2008) Police and Te Puni Kökiri have been supporting Iwi with the necessary tools to develop and design their own Plans. The type of support provided includes: - providing Police intelligence to Iwi groups that enable Iwi to understand the crime problems and profiles of Mäori (offenders and victims) within their geographical areas - providing specialised trained staff who are able to take Iwi through a formal problem solving approach to crime prevention methodology training in SARA and POP problem-solving models - providing draft ICPP templates and Guidance Notes for preparation of the Iwi Plans - funding writers nominated by Iwi to begin drafting Iwi-specific crime prevention plans. Progress to date (previous 3 months work) - Ngai Tahu is sourcing funding for a writer to commence the development of their plan. - The Auckland-metro plan is delayed due to funding shortfall. - Ngapuhi and Te Arawa have both produced first drafts of their plans and presented them to a special meeting of Justice Sector Chief Executives (JSCEs, and senior officials from outside the justice sector). - Consultation is still underway (led by Te Puni Kökiri, Hutt Office) to develop an urban approach to reducing offending by Mäori in Wellington. Current ongoing work (next 3 months) - Following the Iwi presentations to the special meeting of JSCEs, the policy lead is now with the Ministry of Justice and Te Puni Kökiri and further discussions with Ministers are forthcoming. Police will continue to stay involved in progress going forward. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 1.7 FAMILY VIOLENCE CLEARINGHOUSE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | Families Commission, NGOs |  |
| Project Manager |  |  |  | Jeff Sheerin/Jolene Armadoros |  |
| First Programme of Action reference |  |  |  | Actions 14 and 15 |  |
| Objective and actions (as per Work Programme) The New Zealand Family Violence Clearinghouse (NZFVC) is enhanced to ensure its efficacy and to become the independent, sustainable, comprehensive one-stop shop for national and international information on family violence. Actions include: - develop a model and systems which optimise the operations of the NZFVC. |  |  |  |  |  |
| Objective deadline |  | June 2009 (Subject to variation requesting deadline change) |  |  |  |
| Purpose To review NZ Family Violence Clearinghouse activities and services and develop a strategy for moving forward. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.7.2 | Scope redevelopment of NZFVC project, identify requirements and develop strategy |  | Sept 2008 |  | Initial scoping work now complete. |
| 1.7.3 | Develop 2-5 year strategy |  | 30 June 2009 |  | Continue discussions around the new strategic plan and associated work programme. |
| 1.7.4 | Develop project plan and secure funding |  | Sept 2008 |  | Complete. Cabinet funding is ongoing. |
| 1.7.5 | Implement new NZFVC website and service |  | July 2009 |  | Some delay. Site now due to go live in July 2009. Delay due to contract negotiations and IT issues. (Subject to variation requesting final deadline change) |
| Progress to date (previous 3 months work) - The operations of the NZFVC website are now in-house within MSD. - Consultation with users and key stakeholders on requirements for the new NZFVC, and working with MSD IT on the information requirements and design. Current ongoing work (next 3 months) - Regular meetings with the NGO consortium Managers to discuss strategic direction for the NZFVC and continuing to consult with key stakeholders and Advisory Group members. - Continued close working with MSD IT on information requirements and design. - Continued working with MSD IT to gain agreement on the capitalisation of redevelopment costs for the new website and associated applications. - Working with NGO Consortium to look at staffing requirements for the Clearinghouse moving forward. - Updating minor content on website so that it is ready for the transition to the new site. - Working on processes / policies for the Clearinghouse moving forward. - Looking into appropriate contracting arrangements with NGO Consortium for after 30 June 2009. Timing / Ongoing / Recommendations / Conclusions Status = Delay (Subject to variation requesting deadline change) |  |  |  |  |  |

| ### 1.9 MĀORI RESEARCH AGENDA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Te Puni Kökiri |  |
| Contributors |  |  |  | MRG, MSD, Families Commission, NGOs |  |
| Project Manager |  |  |  | Te Atarangi Whiu |  |
| First Programme of Action reference |  |  |  | New initiative |  |
| Objective and actions (as per Work Programme) Te Puni Kökiri has completed the first phase of this objective, that is, the development of a Mäori Research Agenda. Te Puni Kökiri is now undertaking the second phase which is to recommend further action. Improve our understanding of the nature of family violence in whänau Mäori and successful models of prevention and intervention. Actions include: - review existing literature - develop a research agenda - link to the Taskforce strategic research agenda for family violence prevention - recommend further action. |  |  |  |  |  |
| Objective deadline |  | A second phase is in development, the deadline is likely to be June 2009 |  |  |  |
| Purpose First phase purpose. To increase the evidence base by providing case studies of a minimum of three Mäori designed, developed and delivered programmes. Second phase purpose. To develop a Research Plan for the Mäori Research Agenda. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.9.3 | Final Report |  | 5 Sept 2008 |  | Complete. Final report and summary report submitted to the Taskforce in December 2008. |
| 1.9.4 | Research Plan for the Mäori Research Agenda |  | June 2009 |  | Meeting with MRG and MSD to progress plan. |
| Second Phase - The second phase of work on this Objective is the development of a Research Plan for the Mäori Research Agenda. This output is likely to comprise the following: - Prioritisation of the Mäori Research Agenda. - Timeframes to complete the prioritised Mäori Research Agenda. - Resources required to complete the prioritised Mäori Research Agenda. - Responsibility (Ministries and agencies) for completing the prioritised Mäori Research Agenda. - The Research Plan will be jointly developed by MRG and MSD in consultation with relevant Ministries and agencies. TPK currently plans to submit the Research Plan to the Taskforce in June 2009. Progress to date (previous 3 months work) - First phase completed. The agenda for research included a literature review, case study analysis and a summative report to the Taskforce. - Publication of the suite of documents that comprises the Mäori Research Agenda. - Development of Research (second phase). Current ongoing work (next 3 months) - Prioritise the Mäori i Research Agenda. - Identify timeframes and resources required to complete the prioritised Mäori Research Agenda - Identify Ministers and agencies responsible for completing the prioritised Mäori Research Agenda Timing / Ongoing / Recommendations / Conclusions Status = The Second phase is underway and on track. |  |  |  |  |  |

| ### 1.10 PACIFIC RESEARCH AGENDA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Pacific Island Affairs (MPIA) |  |
| Contributors |  |  |  | PAG, MSD, Families Commission, NGOs |  |
| Project Manager |  |  |  | Diane Anorpong |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) Key stakeholders are being consulted over the variation to ensure agreement. The below Objective and actions are the original. |  |  |  |  |  |
| Improve our understanding of the nature of family violence in Pacific families and successful models of prevention and intervention. Actions include: - review existing literature - develop research agenda - link to the Taskforce strategic research agenda for family violence prevention - recommend further action. |  |  |  |  |  |
| Objective deadline |  | Final deadline to be confirmed (subject to variation). |  |  |  |
| Purpose To develop an understanding of Pacific family violence research priority topics and the issues which surround Pacific family violence research. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.10.1 | Finalise project plan |  | April 2008 |  | Complete. Project plan finalised, stakeholder discussions complete. |
| 1.10.2 | Consult with Pacific Advisory Group (PAG) |  | June-July 2008 |  | Ongoing. |
| 1.10.3 | Consult with other Pacific stakeholders |  | August 2008 |  | Delayed. |
| 1.10.4 | Completion of report |  | September 2008 |  | Delayed. |
| Background The Pacific Family Violence Research Agenda will sit within a Pacific Research Agenda. Progress to date (previous 3 months work) - MPIA hosted the new PAG members on 26 April and assisted MSD in the induction of new members, including a presentation on MPIA’s current work on community engagement. - MPIA consulted with others on the variation. Current ongoing work (next 3 months) - Finalise agreement for the variation: - continue MPIA’s support for PAG’s Pacific Proggramme of Action, particularly in the work areas of communications, leadership and collaboration. Timing / Ongoing / Recommendations / Conclusions Status = delayed. A variation submitted in November 2008 is still in consultation. |  |  |  |  |  |

| ### 1.11 NEW MIGRANT AND REFUGEE RESEARCH AGENDA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | Dorothy Adams |  |
| First Programme of Action reference |  |  |  | N/A |  |
| Objective and actions (as per Work Programme) Improve our understanding of the nature of family violence in new migrant and refugee families and successful models of prevention and intervention. Actions include: - review existing literature - develop a research agenda - link to the Taskforce strategic research agenda for family violence prevention - recommend further action. |  |  |  |  |  |
| Objective deadline |  | April 2009 |  |  |  |
| Purpose To develop an understanding of family violence and the issues which surround family violence in new migrant and refugee families. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.11.2 | Scoping paper |  | Dec 2008 |  | Complete. Draft research approach has been circulated internally for comment and feedback. |
| 1.11.3 | Recommendations for further action |  | March 2009 |  | Some delay. Further consultation continuing to agree next steps in research programme. |
| Progress to date (previous 3 months work) - A scoping paper setting out an approach for research to build knowledge on family violence prevention in migrant and refugee families has been drafted and circulated internally for comment and feedback. - Discussion with relevant agencies regarding priorities in this field of family violence prevention is taking place. Current ongoing work (next 3 months) - External consultation still continuing to identify the research question this action is intended to contribute towards, and the most appropriate way of addressing the issues. Timing / Ongoing / Recommendations / Conclusions Status = delayed. |  |  |  |  |  |

| ### 1.12 ELDER ABUSE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | Cilla Corlett |  |
| First Programme of Action reference |  |  |  | N/A |  |
| Objective and actions (from work programme) Improve our understanding of the nature of elder abuse and successful models of prevention and intervention. Actions include: - review existing literature - develop a research agenda - link to the Taskforce strategic research agenda for family violence prevention - recommend further action. |  |  |  |  |  |
| Objective deadline |  | 2010 |  |  |  |
| Purpose/Expected Outcome Improved decision-making about viable programme and service delivery to eliminate elder abuse and neglect within the family setting. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.12.2 | Develop a research agenda. |  | 30 July 2008 |  | Complete. Recommended research agenda sent to the Families Commission for inclusion into the Commission’s research agenda. |
| 1.12.4 | Recommend further action. |  | 10 Dec 2008 Mid 2009 2009/10 |  | Complete. Reported to 10 December 2008 Taskforce meeting with recommended priorities for action. Broader consultation with sector to gain wider engagement with plans. Implementation of action plan. |
| Background The proposed research agenda on Elder Abuse and Neglect is covered in the report presented to the Taskforce in December 2008. Progress to date (previous 3 months) - There has been a delay in undertaking broader consultation with sector to gain wider engagement with plans, as we are awaiting Taskforce confirmation to proceed. - MSD and Age Concern are currently working with the Campaign Team to achieve a stronger Campaign focus on older people. Current ongoing work (next 3 months) - Broader consultation with sector to gain wider engagement with plans (timeframe to be confirmed). - Report back to the Taskforce for endorsement of leadership goal arising from the plan, for inclusion in the Taskforce’s Ongoing Programme of Action (timeframe to be confirmed). - Commence implementation of action plan. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 1.13 DATA ON NGO SERVICE DELIVERY |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | NGOs, ACC, MoJ, Police, MoH |  |
| Project Manager |  |  |  | Dorothy Adams |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (from work programme) High quality data available about services delivered by, and the demand for, NGO and agency family violence services. Actions include: - develop systematic and accurate data on services. |  |  |  |  |  |
| Objective deadline |  | Ongoing |  |  |  |
| Purpose To understand the family violence services available and the ongoing demand for services; both volume and type. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.13.1 | Scoping project to understand what output from this project is going to add most value to relevant stakeholders |  | 30 March 2009 |  | - Identified key stakeholders. - Have begun to meet with these stakeholders to understand requirements and what information is already available. |
| 1.13.4 | Project Plan, including identification of already existing data and resource implications, will be produced for further consultation |  | 15 June 2009 |  |  |
| Project re-scoping Note that this project is currently being re-scoped. This Objective will now not be as closely aligned with the Pathway to Partnership initiative. The outcome of the work will not change, however milestones have been modified to reflect the redevelopment. Further milestones will be available once re-scoping is complete. Background Anecdotal evidence suggests the demand for Family Violence Prevention services is increasing. Considerable data exists about the services delivered by, and the demand for, NGO and agency family violence services but this information is not collected or collated in a systematic way so that any gaps can be identified and addressed. Current ongoing work (next 3 months) This project is being re-scoped. During March 2009 scoping will occur to understand what output from this project is going to add most value to relevant stakeholders. This work will then be translated into a Project Plan to be agreed by relevant stakeholders. A draft report with recommendations for how we re-scope this work has been prepared, but decisions have not yet been made. This will happen by mid June with a new Project Plan prepared. Timing / Ongoing / Recommendations / Conclusions Status = project being re-scoped. |  |  |  |  |  |

### Changing Attitudes and Behaviour

| ### 2.1 KIA PUĀWAI |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | All Taskforce members |  |
| Project Manager |  |  |  | Anne Riley |  |
| First Programme of Action reference |  |  |  | Not in first Programme of Action |  |
| Objective and actions (as per Work Programme) Kia Puäwai supported in its implementation by the Taskforce. Taskforce supports initiatives such as: - increasing coverage of intensive home visiting - providing free Early Childhood Education for all vulnerable children aged 18 months – 3 years - developing an integrated identification, assessment and referral system for young children - expanding Early Years hubs and teen parent co-ordinators initiatives - key workers to support at-risk families - expanding Social Workers in Schools. |  |  |  |  |  |
| Objective deadline |  | Ongoing |  |  |  |
| Purpose This cross-agency initiative is building an early years intervention system to help ensure all children flourish in early childhood and reach their potential as young adults capable of developing healthy, respectful and violence-free relationships throughout their lives. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 2.1.3 | B4School check pilot in place. |  | Aug 2008 |  | Complete. Pilot in place. |
| 2.1.4 | Report-back to Cabinet. |  | June 2009 |  | The nature of this work is yet to be confirmed by the new Minister of Social Development (Minister Bennett). |
| Progress to date (previous 3 months work) - MSD has sent a briefing on the early years work to Minister Bennett. The nature of this work is yet to be confirmed by the Minister. Timing / Ongoing / Recommendations / Conclusions Status = some delay, awaiting Ministerial confirmation. |  |  |  |  |  |

| ### 2.2 IMPROVING ATTACHMENT |  |  |  |  |
| --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Health / Auckland District Health Board |  |
| Contributors |  |  | MSD, ACC, MoE, NGOs |  |
| Project Manager |  |  | Pat Tuohy / Carol Stott |  |
| First Programme of Action reference |  |  | N/A |  |
| Objective and actions (as per Work Programme) This Objective is subject to variation, extension of deadline to July 2010). Promote and improve attachment between new-born babies, and their parents and caregivers. Actions include: - progress a pilot - see how well it works - report - draw on key findings from parent support and development programmes already focused on supporting attachment between young children and their parents and caregivers. |  |  |  |  |
| Objective deadline |  | July 2009 (pending variation, extension of deadline to July 2010) |  |  |
| Purpose Supporting the promotion of healthy secure attachment in infants is important for the development of quality relationships between infants and parents and caregivers, and for its effect on human development and wellbeing. Promotion of secure attachment can be provided through provision of information to parents, and support with strategies that enhance attachment and address any parenting concerns. Early intervention is recommended for infants of high-risk carers if developmental or behavioural problems are detected. |  |  |  |  |
| Key Milestones |  |  | Date | Description of Progress |
| 2.2.1 | Use of a new needs assessment and care planning process to allocate additional visits to support fathers and male partners, based on identified risk/need. |  | July 2010 | Phased from July 2010. |
| 2.2.2 | Promotion of infant-parent attachment and assessment of parent /child relationship difficulties as part of a new needs assessment and care planning process in the revised WellChild Framework. |  | July 2010 | Phased from July 2010. |
| 2.2.3 | Training for WellChild Providers to promote secure infant-parent attachment. |  | July 2010 | Phased from July 2010. |
| Background The pilot to prevent Shaken Baby Syndrome (key milestone 2.2.4) did not proceed as initial scoping highlighted issues with the pilot site. Timing / Ongoing / Recommendations / Conclusions Status = delayed. This Objective will be subject to variation. |  |  |  |  |

| ### 2.3 CONDUCT DISORDER / SEVERE ANTI-SOCIAL BEHAVIOUR |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Social Development |  |  |
| Contributors |  |  | MinEdu, MoH, MoJ and Police (Inter-Agency Plan partners). NGOs, Office of the Children’s Commissioner (OCC), and other relevant agencies will be consulted on policy development. |  |  |
| Project Manager |  |  | Saskia Patton |  |  |
| First Programme of Action reference |  |  | N/A |  |  |
| Objective and actions (as per Work Programme) Ensure comprehensive behavioural interventions for children aged 3 – 7 years with conduct problems and their families are delivered in accordance with the Inter-agency Plan by building on the specialist behavioural services already provided by the Ministry of Education. In addition, existing services for older children and young people will be transitioned to evidence-based, best-practice interventions. The Taskforce supports the four action areas in the Inter-Agency Plan: - leadership, coordination, monitoring and evaluation - transition existing service provision to evidence-based, best-practice interventions - establish an intensive, comprehensive behavioural service for 3 -7 year olds - build a shared infrastructure for the delivery of specialist behavioural services. |  |  |  |  |  |
| Objective deadline |  | 2012 |  |  |  |
| Purpose Developing and delivering a suite of services for the 5% of early childhood and primary (and intermediate) school aged children who have conduct problems will reduce the prevalence of young people with these problems. Without appropriate interventions, these children are more at risk of becoming perpetrators of violence. Over time these services are anticipated to result in a subsequent reduction in cases of family violence. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 2.3.2 | Best practice report completed. |  |  | June 2008 | Complete. |
| 2.3.3 | Agency service reviews/stocktake completed. |  |  | Dec 2008 | Complete – initial stocktake complete. |
| Ongoing deliverables still to be confirmed by new Government. |  |  |  |  |  |
| Background This is an inter-agency project which seeks to improve behavioural interventions for 0-17 year olds across service areas of the Ministries of Education, Health, Justice and Social Development (CYF). In particular, it will establish a comprehensive behavioural service for treating children aged 3-7 years (subject to further investment) and transition existing services for older children and young people to evidence-based, best-practice interventions. Progress to date (previous 3 months work) - Best practice report released 17 March 2009 at Taumata Whanonga – From evidence to action behavioural summit hosted by the Ministry of Education. - AGCP close to completing first draft of a second report: Translating Evidence into Practice which is looking at programme selection for 3-7 year olds and a research design to best support the implementation of selected programme(s). - Officials and AGCP ran a workshop on implementation and transition issues 18 March 2009. - MSD hosted Steve Aos from the Washington State Institute for Public Policy who presented key findings on delivery of evidence-based policy in a range of internal and inter-sector forums 18-19 March 2009. Current ongoing work (next 3 months) - AGCP will finalise the Translating Evidence into Practice report (focus on 3-7 year olds’ services) by 30 June 2009. - Review of AGCP work programme within context of new government priorities. - Agencies will follow up on the Ministry of Education hosted Taumata Whanonga, Minster of Justice hosted Drivers of Crime meeting and MSD-led Early Years work to inform future direction of inter-agency conduct problem work. - A report that provides advice on how to engage and support tamariki, taiohi, whanau, hapu and Iwi in delivery of conduct problem programmes by 30 June 2009. Timing / Ongoing / Recommendations / Conclusions Status = new deliverables still to be confirmed. |  |  |  |  |  |

| ### 2.4 CURRICULUM DEVELOPMENT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Education |  |  |
| Contributors |  |  | MSD (MYD), MoH, TPK, MPIA, OCC, NGOs |  |  |
| Project Manager |  |  | Hayley Corbett |  |  |
| First Programme of Action reference |  |  | N/A |  |  |
| Objective and actions (as per Work Programme) Children and young people aged 5-18 years develop the knowledge and skills that they need to support good decision-making, to make healthy choices, and to seek help when they need it. Actions include: - provide support to enable schools to develop their programmes within the New Zealand curriculum to suit the diverse learning needs of their community - strengthen whole-school, strengths-based approaches that promote resilience and confidence in young people and those adults who support them - seek opportunities to identify and respond to children who are affected by family violence. |  |  |  |  |  |
| Objective deadline |  | Ongoing |  |  |  |
| Purpose The purpose of education is to help children and young people reach their potential and develop the competencies they will need to live, learn, work and contribute as active members of their communities. Education contributes to the prevention and reduction of family violence in New Zealand communities by providing a safe environment that teaches and models skills to enable children and young people to manage their own wellbeing and to relate in healthy ways with others. It provides children and young people with the opportunity to learn skills they might not otherwise receive in the home environment. To experience the benefits of education, students must participate and be engaged with the education system. The Ministry of Education supports educators to identify students who are at risk as a result of experiencing, witnessing or engaging in family violence and to work with parents, families and whänau, and other agencies to ensure these students are appropriately supported. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 2.4.1 | Provide support to enable schools to develop their programmes within the New Zealand Curriculum (NZC) to suit the diverse learning needs of their community. - Release final curriculum and supporting resources for schools to support the implementation of the curriculum - Professional leaders are supported to lead curriculum development, establish the conditions for professional learning and involve families / whänau in focusing on student achievement and educational outcomes based on the NZC. |  |  | Ongoing Ongoing | On track. Ongoing support for both Te Marautanga o Aotearoa (Māori Medium curriculum) and New Zealand Curriculum (English medium school). MoE is working with Iwi organisations to develop projects that will help them utilise both the NZC and Te Marautanga o Aotearoa to develop a localised curriculum that reflects the skills, and knowledge that are important for them. MoE continues to plan and implement publication of exemplars of school community engagement and the development of school curriculum to meet local student learning needs. Other curriculum advice and guidance is also being published on line and in print. School Support Services provided advice across the Curriculum. |
| 2.4.2 | Strengthen the implementation of whole-school, strengths-based approaches that promote resilience and confidence in children and young people and those adults who support them. - Support up to 730 teachers per year in developing effective teaching and leadership skills to support the implementation of school-wide approaches to student wellbeing / mental health. This involves strengthening teachers’ understanding of the connections between school organisation, curriculum design and delivery, and community consultation and partnerships. - Identify successful professional learning approaches for teachers from the evaluation of the student wellbeing contracts and incorporate in the design and delivery of ongoing professional development contracts. |  |  | Ongoing Ongoing | On track. An initiative to prevent bullying in schools was launched in July 2008. Ongoing review of progress on school-wide approaches to student wellbeing and mental health. Plan for continuation of this work in participant schools until the end of June 2009. Ten case studies on mental health education have been published and are now available online. These case studies outline various strategies and approaches used by teachers as part of mental health education. Work continues between MoE, the national coordinator and facilitators to review and improve the models used in the delivery of the Student Well-Being and Mental Health contracts. The Taumata Whanonga – evidence to action summit was held on 16/17 March. The summit focussed on establishing key actions required to improve support for children and young people with challenging behaviour. This included consideration of the links between behaviour, educational achievement and student and teacher wellbeing. A draft Action Plan is currently being developed and is expected to be completed by the end of May. |
| 2.4.3 | Seek opportunities to identify and respond to children and young people who are affected by family violence. - Review the quality and accessibility of support available to educators who are concerned about children and young people affected by family violence. - Develop a review of the support received by children and young people identified while at school as affected by family violence (in conjunction with Obj 1.4 Child Maltreatment). |  |  | Ongoing Ongoing | On track. Modifications to the education profile and plan guidelines and templates for children in care continue to be made as it continues to be rolled out into other trials sites throughout the country. Work continues on a review of the Education sector’s contribution to prevention of child maltreatment. A draft discussion document which presents findings from a stocktake of the Early Childhood Education’s contribution to ensuring the care and protection of children has been completed, and is currently being consulted on with the inter-agency Child Maltreatment Prevention Working Group and internally. |
| Background In 2002, the Ministry of Education’s Curriculum Stocktake Report identified that, while many students were achieving at world-class levels, there are wide disparities in outcomes for diverse students. Progress to date (previous 3 months work) 2.4.1 The New Zealand Curriculum Examplars of effective curriculum development are being published online and in print. These are accompanied by guides to help schools apply lessons learned to their own situations. A range of other strategies including communications and in-school support are helping schools develop their own curricula using the NZC. Te Marautanga o Aotearoa (Māori Medium curriculum) was released in September 2008. Implementation of the curriculum commenced in January 2009 and will continue through until December 2010. Implementation support includes development of resources and information to assist schools to design their own school-based curriculum to reflect the skills, knowledge and aspirations of their community. The Ministry of Education is working with Iwi organisations to develop projects that will help them utilise both the NZC and Te Marautanga o Aotearoa to develop a localised curriculum that reflects skills and knowledge. 2.4.2 Whole-school, strengths-based approaches that promote resilience and confidence in children and young people Facilitators continue to work with their contract schools to review progress towards meeting contract outcomes related to implementing school-wide approaches to student wellbeing and mental health. The Ministry of Education continue to monitor data and progress by schools. Data analysis is being used to plan for the continuation of this work in the participant schools until the end of June 2009. The Ministry of Education, the national coordinator and facilitators, continue to review and improve the models used in the delivery of the Student Well-Being and Mental Health contracts and to integrate the learning in ongoing professional development contracts until the end of June 2009. Te Taumata Whanonga – evidence to action summit was held on 16/17 March. The summit focussed on establishing key actions required to improve support for children and young people with challenging behaviour. 2.4.3 Identifying and referring children affected by family violence to appropriate services Modifications to the education profile and plan guidelines and template for children in care have been made as a result of the trial currently underway within the Auckland District Health Board. Modifications continue to be made as it is rolled out into other trial sites throughout the country. Modification to work practice issues for schools, health workers and social workers being made to allow for a more responsive and timely approach to the Health and Education Assessment Project. A process evaluation of the trials is currently being undertaken by an external provider. Current ongoing work (next 3 months) 2.4.1 The New Zealand Curriculum Examples of effective implementation are included in published research and evaluation reports. The number of networked learning clusters where schools work together to develop school curriculum is being increased. Other professional development projects are increasingly being brought into line with the NZC. Support the implementation of Te Marautanga o Aotearoa from January 2009 through until December 2010 by allocating 10 regional coordinators across the country to work in collaboration with other regionally based In-Service Teacher Educators (ISTEs) to support schools within their regions. The release of the Professional Leadership Plan is planned for April 2009. This will provide a plan outlining how the Government intends to work with the sector to achieve the goal of strong professional leadership in every New Zealand school over the next two years. 2.4.2 Whole-school, strengths-based approaches that promote resilience and confidence in children and young people Work continues on the development of a resource called Making a Difference, which will show how eight New Zealand schools are engaging students in positive learning and achievement. The Ministry of Education will continue to update and promote the supporting positive behaviours website. Facilitators will continue to work with their contract schools to review progress towards meeting contract outcomes related to implementing school-wide approaches to student wellbeing and mental health. This work will continue in participant schools until the end of June 2009. The Ministry will continue to work on the development of a draft Action Plan following the Taumata Whanonga – evidence to action summit held in March. A draft plan is expected to be completed by the end of May. 2.4.3 Identifying and referring children affected by family violence The trial of the education profile and plan has been extended to Counties Manukau, Wairarapa, Horowhenua and Lakes District. Work will continue on the review of the educations sector’s contribution to preventing child maltreatment. A discussion document which presents findings from a stocktake of the Early Childhood Education sector’s contribution to ensuring the care and protection of children as part of the Child Maltreatment Prevention Work Programme will be finalised following consultation. Scoping work for the next phase of the review will commence. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 2.5 VIOLENCE IN THE MEDIA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Families Commission |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | Radha Balakrishnan |  |
| First Programme of Action reference |  |  |  | Action 23 |  |
| Objective and actions (as per Work Programme) Create awareness of the impact of violence in the media on children aged between 6 to 11 years. Actions include: - scope an evidence-based public education and awareness programme aimed at parents - scope financial implications - develop an implementation plan. |  |  |  |  |  |
| Objective deadline |  | February 2009 (Variation to change deadline to November 2009 submitted) |  |  |  |
| Purpose To scope a public education and awareness programme around violence in the media (its risks and impact) with an initial focus on parents of 6-11 year olds. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 2.5.2 | Develop plan |  | Oct 2008 |  | Planning work commenced. |
| 2.5.3 | Draft Report circulated for comment |  | Dec 2008 |  | Not commenced. |
| 2.5.4 | Report to the Taskforce |  | Feb 2009 |  | Not commenced. |
| Background Violence in the media and its impact on society generally was raised at the meeting with the Family Violence Ministerial Team and with members of the Multi-Party Working Group on Family Violence, when the Taskforce’s First Report was presented in mid 2007. The first Programme Of Action (POA) included an action to review how violence is portrayed in the media, utilising the 2004 Report on TV Violence in New Zealand, and to advise on implications for the next POA. The Families Commission agreed to lead this work. The Taskforce supported raising awareness of the impact of violence within the media on children and young people. The 2004 report identified middle childhood (between 6-11 years) as a vulnerable age group and it was agreed that children in this group should be the initial focus of any public education work. Timing / Ongoing / Recommendations / Conclusions Status = delayed. Variation to change deadline submitted. |  |  |  |  |  |

| ### 2.6 CAMPAIGN FOR ACTION ON FAMILY VIOLENCE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | MSD / Families Commission |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | Gael Surgenor |  |
| First Programme of Action reference |  |  |  | Actions 29-39 |  |
| Objective and actions (as per Work Programme) Continue the Campaign for Action on Family Violence through: - an advertising campaign - resource development and distribution - Community Action Fund projects. |  |  |  |  |  |
| Objective deadline |  | 30 June 2009 (Ongoing to 2010) |  |  |  |
| Purpose This is a community-based social marketing campaign which aims to influence the behaviour of target audiences, including perpetrators of family violence and their influencers. The programme is based on research into attitudes towards family violence and motivators and barriers to behaviour change. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 2.6.5 | Administering two further rounds of the Community Action Fund to support local projects to support change at a local level. Mid 2008 and early 2009. |  | April 2009 |  | Round Four closed on 31 March 2009. Applicants were encouraged to include a focus on preventing child maltreatment and elder abuse. A total of 133 applications were received – the greatest number of applications received in one round. The panel meets 29 May. |
| 2.6.6 | Continue to support the messages of the television campaign during 2008/09 using the website, the 0800 information line and print resources. |  | June 2009 |  | On track. The total number of visits to the website in March/April was 24,767 and there were 487 calls to the Family Violence Information Line. 47,435 individual resources were distributed. |
| 2.6.7 | Continue a television advertising campaign addressing attitudes to family violence and intimate partner violence during 2008/09 – five weeks of advertising to be run. |  | 12 June 2009 |  | On track. The ‘It’s not OK’ adverts were aired in December 2008 and January 2009. |
| 2.6.8 | Continue to build on the media advocacy work with the national news media to promote more responsible coverage of stories of family violence and provide training and support to enable community spokespeople to engage effectively with local media. |  | 12 June 2009 |  | On track. Media training for community groups is completed, with the focus now being on working with journalism schools. Two training sessions with journalism students took place in March. |
| 2.6.9 | Continue to identify and encourage campaign ‘champions’ and spokespeople, to develop partnerships in business, sport and youth related organisations and to continue to seek opportunities for promotion within popular culture. |  | 12 June 2009 |  | On track. Relationships with national and regional sports teams continued to grow, and the local government forum took place in April, with good outcomes. |
| 2.6.10 | Continue to measure the level of public awareness of the key messages of the Changing Attitudes and Behaviours Campaign. |  | 30 June 2009 |  | #### On track. #### Findings from the third Reach and Retention survey (undertaken in September 2008) show that objectives were met. |
| Background The Campaign for Action on Family Violence (the Campaign) is a four year campaign that calls on everyone to help put an end to family violence in New Zealand. The national campaign was launched with TV advertisements in September 2007. The Campaign message “Family violence – It’s not OK” has struck a chord with New Zealanders and has quickly become part of the kiwi vernacular. The Campaign is supported by a website, an 0800 Information Line and a Community Action Fund (CAF) that provides financial support for community-led activities. Progress to date (previous 3 months work) - The total number of visits to the website in March/April was 24,767 and there were 487 calls to Family Violence Information Line. Work commenced on the redevelopment of the 0800 line reporting tool. - Work also commenced in March on reviewing and updating the campaign website – some restructuring is underway – including the home page, some new links and the addition of further campaign material. Also in March, a website was developed to support the Book of Stories, launched by the Campaign in December 2008. Although accessible from the campaign website, it also has its own url: www.realstories.org.nz. - A total of 47,435 print resources were distributed throughout the 2-month period. - Media training for community groups is complete, although the campaign is still providing support and encouragement. Three journalism schools this year are so far committed to training, with Aoraki Polytechnic in Timaru and WinTech in Hamilton undertaking training in media about family violence. The request has come from Wellington District Crime Manager Mike Arnerich, so that Police at detective level can be better informed about family violence and the language they use when talking to the media. - The Campaign is continuing to grow relationships with sports teams – as well as growing current relationships with the Women’s Refuge, the campaign finalised its partnership with Central Pulse netball franchise in March. As well as player and on-court signage at Pulse games and local games from Gisborne to Malborough, messages will be included in the team’s school programme, radio advertising for Pulse games and pre-match commentary, and thw team’s website and match programmes. - The Poverty Bay Rugby Union has approached the campaign for help in promoting the It’s not OK message, developing a violence-free club culture, and promoting violence-free champions in the community. The Poverty Bay initiative will involve several rugby players or past players as role models, visiting schools and junior rugby games promoting the key messages “Family violence is not OK” and “It is OK to ask for help”. - The Local Government Forum was held on 22 April with more than 20 local authorities represented and eight Mayors, including Local Government New Zealand (LGNZ) President Lawrence Yule. LGNZ chief executive Eugene Bowen was also there. At a separate workshop attended only by Mayors it was decided that local authorities needed to take a leadership role in supporting community-based family violence initiatives. They intend to look at getting it on LGNZ’s annual conference agenda and Lawrence Yule will be seeking a meeting with Peter Hughes about further LGNZ involvement. - The Taiohi Morehu rangatahi leadership project continues to progress. The campaign is working with the Young Enterprise Scheme (YES) programme to introduce, for the first time, the concept of ‘Social Entrepreneurs’ using the YES framework. The campaign is currently working with the Ministry of Education, schools in the Hutt Valley, Orongomai Marae, Upper Hutt City Council, and young people and their whänau to embed the programme in YES. Heretaunga College is first to set up the Social Entrepreneur programme through YES and Taiohi Morehu, and have allocated a teacher and mentor (supported by a youth worker appointed to the project in Orongomai Marae). The programme includes Mäori and Pacific students, who will each receive 24 Level 2 and 3 Business Studies credits (NCEA) as well as Mäori Performing Arts credits (NCEA). - Following on from Te Matatini, the campaign and Women’s Refuge worked with two further kapa haka teams via the Tuhoe Ahurei Festival in April. As a result of participating in the campaign-Refuge initiative at Te Matatini, the Wehi Family, who lead the Te Waka Huia team (which won supreme prize at Te Matatini), feature in Waitakere’s latest Campaign billboard. - The campaign was invited to support the Pacific Island Presbyterian Church’s Fono Samoa in strengthening its capacity to address family violence issues. The campaign worked with Fono Samoa and the Pacific Island Safety and Prevention Project on the development of “Family Violence is Not OK” messages and actions within the church community at the annual fono in Lower Hutt in Wellington, attended by thousands of people from around the country. The church has now asked for follow up support in developing achievable actions at national and regional levels to promote campaign messages and support children and families within the Christian context. Current ongoing work (next 3 months) - Child maltreatment messaging The campaign, with Jigsaw Services, is meeting with community organisations who are undertaking CAF projects to prevent child maltreatment. Workshops have been held in Waitakere in March and Whanganui in April to explore ideas about the actions that people can take to support parents and protect children; in particular, what people can do as part of their everyday lives, at home and at work, to prevent child abuse and neglect. - Older people The campaign will be developing messaging and resources – alongside Age Concern, TOA Pacifci, Te Oranga Kuia and Kaumatua Services, Older People’s Policy and Office of Senior Citizens – for Elder Abuse Day on 15 June. - Local Government Forum As a result of the local government forum, the campaign has agreed to develop a mayoral toolkit to support leadership around community-based family violence prevention. A draft kit will be presented to the LGNZ annual conference. Work will continue on strengthening current relationships with local governments over the next three months, with an emphasis on supporting TAs to develop family violence prevention plans. - Many voices Building on the success of their Ride Against Family Violence this year, the campaign, with the Mäori Reference Group and E Tu Whänau Ora team, will continue to work with the Super Mäori Fullas to promote violence-free messages and support communities’ action. The draft business toolkit will be work-shopped with a number of business stakeholders, including business leaders. Work will soon begin with the NZ Army, which has asked the campaign for support in addressing attitudes towards violence and in promoting positive parenting, healthy relationships and non-violence. There are opportunities for a number of NGOs to partner with the Army to support its long-term goals. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

### Ensuring Safety and Accountability

| ### 3.1 FAMILY VIOLENCE COURTS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Judiciary / Ministry of Justice |  |
| Contributors |  |  |  | Police, NGOs |  |
| Taskforce Liaison |  |  |  | Justine Cornwall |  |
| Project Manager |  |  |  | Karyn McLean |  |
| First Programme of Action reference |  |  |  | Action 56 |  |
| Objective and actions (as per Work Programme) Two new Family Violence Courts established. Actions include: - project planning - identification of locations - stakeholder consultation - implementation. |  |  |  |  |  |
| Objective deadline |  | April 2009. The Whangarei Family Violence Court opened in May 2009. |  |  |  |
| Purpose To ensure all parties are prepared ahead of the implementation to support new Family Violence Courts being established. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 3.1.3 | Stakeholder consultation |  | Sept 2008 |  | The Whangarei Family Violence Court opened in May 2009. The Palmerston North court has been operational since 12 September 2008. |
| 3.1.4 | Communications strategy |  | Early 2009 |  | A variation was sought in July 2008 to delay the communications strategy to allow for the implementation of new courts. |
| 3.1.5 | Implementation of two new Family Violence Courts |  | May 2009 |  | A Variation was sought in July 2008 regarding the opening of the Whangarei Family Violence Court moving to April 2009. The Whangarei Court will now not open until May 2009. Milestone changed to reflect this delay. |
| Progress to date (previous 3 months work) - Whangarei Family Violence Court opened in May 2009. - Family Violence Court (FVC) training has now been completed. In early February 2009, a two day workshop was held in Whangarei. Court staff, the Judiciary, and other key stakeholders who will be involved in the Whangarei FVC attended. The workshop addressed four key areas: - dynamics of domestic violence - philosophy of FVCs in New Zealand - the FVCs National Operating Guidelines - best practice for working together with local communities. Current ongoing work (next 3 months) - Training was completed in early February 2009. Timing / Ongoing / Recommendations / Conclusions Status = complete (Whangarei Family Violence Court) = complete (Palmerston North Family Violence Court). |  |  |  |  |  |

| ### 3.3 SOCIAL SERVICES SUPPORTING COURTS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development / Ministry of Justice |  |
| Contributors |  |  |  | Police, MWA, NGOs, ACC |  |
| Project Manager |  |  |  | Anne Riley / Justine Cornwall |  |
| First Programme of Action reference |  |  |  | Action 52 |  |
| Objective and actions (as per Work Programme) A social services system modelled around family violence courts to support the courts by linking services to ensure victims and observers are kept safe, perpetrators are kept accountable and responsible, and families are assisted with their recovery needs. Actions include: - introduction of Independent Victim Advocate / support person role in all Family Violence Courts - introduce specialist enhanced case management staff in all Family Violence Courts - referral and funding for non-mandated stopping violence programme providers for offenders. |  |  |  |  |  |
| Objective deadline |  | April 2009. Note that a variation to extend the date for completion of this objective is being drafted for Taskforce consideration subject to Ministerial Direction. |  |  |  |
| Purpose A social services system modelled around family violence courts to support the courts by linking services to ensure victims and observers are kept safe, perpetrators are kept accountable and responsible, and families are assisted with their recovery needs. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 3.3.2 | Scoping and developing Family Violence Court Community Service (FVCCS), formerly called Independent Victim Advocate (IVA). |  | March 2009 |  | Delayed. Scoping and development of the FVCCS has been underway since July 2008. There has been delay in the consultation with NGOs, Judiciary, and key stakeholders. |
| 3.3.3 | Introduce specialist enhanced case management staff in all Family Violence Courts (FVCs) |  | TBC |  | No completion date confirmed as yet. |
| 3.3.5 | Consultation with other agencies and non-government organisations on the development of the role of the FVCCS |  | Feb 2009 |  | Delayed. Consultation has been ongoing from August 2008, and has not yet been completed. It has not been possible to determine a completion date for this work. |
| 3.3.6 | The FVCCS will be rolled out in FVCs. |  | From Sept 2009 |  | Delayed. MSD will manage the selection process for the organisations to tender for the FVCCS. |
| Background The former Government announced that it would move towards fully funding actions 1 and 3 of this Objective from 2008/2009 (Introduction of Independent Victim Advocate/support person role in all FVCs, and referral and funding for non-mandated stopping violence programme providers for offenders). Progress to date (previous 3 months work) - Consultation with other agencies, NGOs, and the Judiciary took place from August to December 2008, and has continued through the beginning of 2009. The development of guiding principles and a process map is still ongoing, with a completion date not confirmed. Current ongoing work (next 3 months) - The role description for the FVCCS has been completed. Finalisation and sign off will be sought once national guiding principles and a process map have been completed. - The management of the selection process, including preparing documentation, for the provider(s) that will recruit and train the eight FVCCS is ongoing. - Development of the framework for a collaboration protocol has been delayed. A meeting scheduled for February 2009 for NGO members of the Taskforce to meet with the Ministry of Justice, the Ministry of Social Development, and NZ Police to progress the finalisation of the FVCCS role was postponed. - Recruiting for the FVCCS role has been delayed until the guiding principles and process map have been developed and agreed to. Timing / Ongoing / Recommendations / Conclusions Status = delayed. Note that a variation to extend the date for completion of this objective is being drafted for Taskforce consideration. |  |  |  |  |  |

### Effective Support Services

| ### 4.1 MĀORI SERVICE WORKFORCE DEVELOPMENT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Social Development |  |  |
| Contributors |  |  | TPK, NGOs, MoE |  |  |
| Project Manager |  |  | Ann Dysart |  |  |
| First Programme of Action reference |  |  | Action 7 |  |  |
| Objective and actions (as per Work Programme) Mäori Service Workforce Development. Actions include: - 60 Mäori trained to work with the Mauri Ora framework - ongoing support of trained practitioners. |  |  |  |  |  |
| Objective deadline |  | June 2009 |  |  |  |
| Purpose This proposal will allow for continued investment in the training and support of practitioners who work with Mäori whänau/communities where there is violence. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 4.1.9 | Cross Credit Whänau Ora Training to a Diploma in Social Work |  |  | May 2009 | Currently have one PTE recognising prior learning, working toward wider PTE acceptance. Due date has been brought forward. |
| 4.1.11 | Develop strategy for attendance on Mauri Ora Training to meet high demand for placement |  |  | April 2009 | Placement issues consolidated mid April and on track for completion. |
| 4.1.12 | Ensure expansion into identified areas is seamless |  |  | March 2009 | Completed. |
| Current ongoing work (next 3 months) - Due to high demand to attend Mauri Ora training programmes a waiting list for programmes is to be developed. - Expansion of the programme into the areas of: Mataatua, Bay of Plenty and Taamaki Makaurau-Auckland Central. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 4.2 PACIFIC SERVICE WORKFORCE DEVELOPMENT |  |  |  |  |
| --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Social Development |  |
| Contributors |  |  | MPIA, NGOs, MoE |  |
| Project Manager |  |  | Richard Joblin |  |
| First Programme of Action reference |  |  | Action 7 |  |
| Objective and actions (as per Work Programme) Variation to adjust Objective deadline submitted. Pacific Service Workforce Development. Actions include: - preparation of a project plan to guide workforce training and development in family violence services for Pacific families - developing a long-term approach to NGO provider capability building under the Pathway to Partnership plan. This approach will support the development of Pacific family violence social service providers and workforce. |  |  |  |  |
| Objective deadline |  | July 2008 (Variation to change deadline submitted) |  |  |
| Purpose This work plans to increase the quality and diversity of services working to eliminate family violence in the Pacific communities. This will include identifying the capacity and capability of this workforce and the avenues needed to further build and support Pacific People in working to stop family violence in Pacific Families. |  |  |  |  |
| Key Milestones |  |  | Date | Description of Progress |
| 4.2.1 | Project plan developed under Pathway to Partnership (P2P) to address building provider workforce capability and capacity. This will include the development of the Pacific workforce. |  | July 2008 | Complete. However, on 8 August 2008 the then Minister for Social Development and Employment considered a report on strengthening collaborative action under P2P. The Minister agreed to the development of a longer-term investment approach to provider capability building by March 2009. |
| 4.2.2 | The project plan on development of the Pacific workforce included within the P2P plan to further develop the NGO social services sector. |  | April 2009 | Delayed. Awaiting Ministerial Direction. |
| New Action added Note that an additional action has been added to this Objective. The initial action was completed in July 2008. However, the P2P Steering Group decided that funding should be reallocated to accelerate the move of essential services to full funding. Subsequently the then Minister for Social Development and Employment agreed to a longer-term investment approach to provider and workforce capability building being developed by March 2009. Pacific NGO provider and workforce development has been included in this longer-term approach under P2P. The new additional action reflects this work. Background Pacific service workforce development is now incorporated under the P2P plan on a work-stream to address providers’ ability to build workforce capability and capacity. A Steering Group made up of representatives from community-based organisations has overseen the development of the P2P plan. A representative from the Pacific Advisory Group (PAG) is on this steering group. A variation to this Objective is in the submission process. Current ongoing work (next 3 months) This work is subject to variation. Work is continuing on reviewing current investment in the capability of NGO social services towards developing a capability framework for 2009 onwards. The Pacific service work force in family violence is included in this work. Timing / Ongoing / Recommendations / Conclusions Status = delayed. Variation to change deadline submitted. |  |  |  |  |

# First Programme of Action update

Summary Analysis

The Taskforce for Action on Violence within Families’ (the Taskforce) first programme of action initially consisted of 76 actions which were developed from the Taskforce’s First Report. This was consolidated to 53 actions.

Of these 53 actions, 30 are complete. Work has commenced on another 13 actions and these are now either ongoing, business as usual, or are annual events. The remaining ten actions have been subsumed into the Ongoing Programme of Action and, along with other ongoing work, are now reported on, and monitored through, the regular Monitoring Reports provided to every Taskforce meeting.

Key to ‘Status’ column

Complete = Action complete. May have informed development of work in Ongoing Programme of Action.

OPOA = Work in these actions has been incorporated into the Ongoing Programme of Action, refer to Objective number.

Ongoing or Annual = Initial stage complete, currently Ongoing or business as usual. Some are Annual occurrences.

| # | Action | Agency | Information | OPOA # | Status |
| --- | --- | --- | --- | --- | --- |
| Leadership |  |  |  |  |  |
| 1 | Developing the next Programme of Action (POA) | All TF | OPOA released Feb 2008 | 1.1 | Complete |
| 3 | Successful implementation of POA | All TF | Incorporated into OPOA | 1.1 & 1.1a | Complete, ongoing reporting |
| 7 | Drawing on Mäori and Pacific advisory groups | MSD | Representatives on Taskforce (TF), ongoing MRG and PAG meetings advise the TF. | Led to 1.2, 1.3, 1.6, 1.9, 1.10, 2.4, 4.1, 4.2 | OPOA |
| 8 | Incorporating migrant and refugee perspectives | MSD | Informed OPOA, also further research included in OPOA. | 1.11 | OPOA |
| 9 | Aligning business planning to reflect Taskforce vision | Sec. | SOIs to be regularly monitored. | 1.1 | Annual |
| 12 | Maintain overview of government strategies to ensure goals and activities are complementary with our work | All TF | Business as usual. Secretariat watching brief to ensure TF are aware of all relevant government strategies. All TF agencies info share on new strategies, and maintain overview of relevant government strategies. | 2.1 2.3 | Complete to date, Ongoing |
| 13 | Family Violence research strategy | FC | Initial report provided Oct 2007. Ongoing consultation with other research agendas. | Informs 1.9-1.12 Led to 1.13 | Ongoing |
| 14 | Monitoring the level of family violence in NZ | FC | Refer to Research Strategy, Action 13. | Led to 1.13 & 1.7 | Ongoing |
| 15 | Horizontal learning | MSD | Incorporated into OPOA. | 1.7 | OPOA |
| 19 | Evaluate the first POA | MSD | Ongoing actions from POA are monitored through regular Monitoring Reports. | 1.1a | Complete |
| 21 | Families Commission research programme | FC | 3 year research complete 21a Improving Family Violence surveillance data 21b Elder abuse and neglect research – released Feb 2008 | Informed OPOA | Complete |
| 22 | ACC research programme | ACC | 22a Sensitive claims 22b Effectiveness evaluation 22c Whänau Ora research 22d Evidence based guidelines. |  | Complete |
| Changing attitudes and behaviour |  |  |  |  |  |
| 23 | Review violence in media | FC | Informed development of 2.5 | 2.5 | Complete |
| 29 | Using research to guide Campaign strategy | MSD | The Campaign continues to 2010, with further development being guided by research and evaluation | 2.6 | OPOA |
| 35 | Campaign strategy | MSD / FC | As above | 2.6 | OPOA |
| 36 | Mass media campaign | MSD / FC | Phase one started Sept 2007, Phase two started Feb 2008. Both phase adverts repeated in 2008 and early 2009. | 2.6 | OPOA |
| 37 | Nurturing leaders… | MSD | Business as usual. Identified (and funded) through the Community Action Fund. | 2.6 | OPOA |
| 38 | Partnerships with NGOs | MSD/ FC | NGO groups are contracted to be funded for services. | P2P | Ongoing |
| 39 | Community Action Fund | MSD | 97 initiatives funded in first three rounds. Fourth round currently open. | 2.6 | OPOA |
| 40 | Building knowledge – media advocacy etc | MSD/ FC | 40a media advocacy - FACS 40b FV awareness training – also led to 1.5 40c Toolkit re-released 40d White Ribbon day | 2.6 2.6 1.5 2.6 - | OPOA OPOA OPOA Complete Annual |
| 4142 | Family violence death reviews | MoH | Family Violence Death Review Committee established. | 2.7 | OPOA |
| Ensuring Safety and Accountability |  |  |  |  |  |
| 43 | Sharing information in a way that promotes safety and wellbeing | Previously MoJ | The Law Commission and the Privacy Commissioner are exploring approaches to the issue of government information sharing. The Law Commission is due to release an issues paper in the first half of 2009. Subject to variation process. |  | Initial work complete, Ongoing |
| 44 | Family Violence victims know what support and services are available | MoJ | Communications material developed and distributed. Available on Family Court website. |  | Complete |
| 45 | Maximising safety factors when managing court rosters | MoJ | Security policy complete, sent to all courts as a circular on 1 April 2008. |  | Complete |
| 46 | Increased thresholds for legal aid eligibility | MoJ | Thresholds increased. New legal aid regulations in force from Mar 2007. |  | Complete |
| 47 | Begin a review of legal aid remuneration rates | LSA | Review complete. Changes recommended. Budget 2008 approved 10% increase for 2008/2009. |  | Complete |
| 48 | Improving information courts provide about legal aid | MoJ | Info updated and provided in court info packs and in DV packs, Dec 2007. Court staff also provided with info for public enquiries. |  | Complete |
| 49 | Testing fixed fees for legal aid | MoJ / LSA | Testing complete. Three things were tested – fixed fees, the removal of prior approval requirements for standard family grants and proforma invoices. The removal of prior approval was implemented in October 2008 alongside revised family steps and disbursements. Fixed fees and proforma invoices are on hold. |  | Complete |
| 50 | Building safe and effective programmes for couples and families | MSD / MoJ | Service specifications set. MoJ in consultation with NZ Assoc of Counsellors, timeframes to be set. |  | Ongoing |
| 51 | Build capacity of interpreters in Courts | MSD / MoJ | More interpreters available in courts. Business as usual to continue building availability. |  | Complete |
| 52 | Investigate introduction of advocates in courts | MWA / MoJ / MSD | Investigation completed by MWA. Refer OPOA Objective 3.3 for further work. | 3.3 | Complete |
| 53 | Enhanced ability for courts to contact victims directly | MoJ / Police | Already possible, MoJ and Police will continue improving standardised process for CSV1 compliance and referral. |  | Complete |
| 54 | Review purchasing plans for programmes | MoJ | Reviewed. 2008 tender round complete. |  | Complete |
| 55 | Improve process for prosecutions for non-attendance at programmes | MoJ / Police | Memorandum of understanding between MoJ and Police for the transfer of prosecutions to Police signed. Transfer completed in June 2008. |  | Complete |
| 56 | Establish four additional Family Violence Courts | Judiciary / MoJ | Four established. Another established in Palmerston North in Sept 2008, one more due to open in May 2009 in Whangarei. | 3.1 | Complete |
| 57 | Family Violence Courts Evaluation | MoJ | Waitakere and Manukau evaluation complete. Released August 2008. | 3.2 | Complete |
| 58 | Forum to identify best practice for information exchange | MoJ | Held March 2007. Best practice ideas generated informed development of guidelines by agencies. |  | Complete |
| 60 | Enforcement of protection orders (POs) – police training, performance measures and policies | Police | Initiatives on addressing family violence “big picture” (which include PO’s) complete. Ongoing work includes; 60a Training 60b Performance measures 60c National investigation and prosecution policies. | Many & 4.4 | Complete. Ongoing work |
| 61 | Support and training for lawyers working in family violence-related areas | Judge Boshier | Workshops for FC lawyers done in 2007. Law Soc also produced a resource booklet. Similar training is likely to be ongoing. |  | Complete |
| 62 | Define options to improve information sharing between agencies and the Courts | MoJ | Information sharing already occurs between the Family Court and the District Court. Background papers and process maps have been drafted for internal review. Consultation with external stakeholders was planned for Nov/Dec 08, however project currently on hold. A variation will be sought for this objective. |  | First stage complete Ongoing 2008 & beyond |
| 63 | Simplify application forms for Protection orders | MoJ | An information sheet on the DVA application process has been produced and is available online. Further work is to be deferred subject to Ministerial Direction on domestic violence legislative reforms and consequential amendments to the DVA Rules and Regulations. A variation will be sought for this objective. |  | Form complete. Simplifying forms is ongoing. |
| 64 | Improve the use of security resources available to courts | MoJ | The action area of the Taskforce work programme is to be reverted to business as usual, and is currently subject to the variation process. |  | First stage complete, Ongoing 2008 & beyond. |
| 65 | Consider an office to provide DVA-specific legal services | LSA MoJ | Currently developing objective and milestones as part of business planning. |  | Ongoing 2008 & beyond |
| 66 | Determine level of attendance and performance of perpetrators at programmes | MoJ | A report into the findings was completed on 30 September 2008 The results were to be fed into Action 67. |  | Complete |
| 67 | Develop options to ensure perpetrators attend and complete programmes | MoJ | Further phase of Action 66. Currently subject to variation process, may be removed from the Taskforce work programme. Subject to Ministerial direction, the Ministry of Justice is looking to undertake a project on programme provision with the goal of improving service delivery. |  | Ongoing 2008/2009 & beyond |
| 68 | Information for perpetrators on programmes | Police | Information distributed. |  | Complete |
| 70 | Ensure the range of programmes matches the profiles of perpetrators | Corrections / MoJ | Options to potentially address gaps in programmes for prisoners with DV-related offences formulated. Corrections currently analysing these options. |  | Ongoing 2007/2008 & beyond |
| 71 | Local Case Collaboration (FVIARS) | CYF / Police | FVIARS nationwide roll-out complete. Now business as usual. | Informs 3.3 | Phase one complete, Ongoing 2008 & beyond |
| Effective Support Services |  |  |  |  |  |
| 72 | Govt investing $9 million over the next four years | MSD | 2006/2007 contracts and funding took place. Continued funding of contracts from baseline. |  | Develop Complete Ongoing to 09/10 |
| 73 | Develop new funding model | MSD | Pathway to Partnership (P2P) developed and ongoing. $20.4 million allocated in 2007. $446 million announced 12 Feb 2008 to fund essential NGO child and family services. | 2.1/4.2 | Complete OPOA |
| 74 | Cost family violence and family support services | MSD | Costing tool developed as part of P2P as above. |  | Complete |
| 75 | Build on existing workforce and organisational development initiatives | MSD | P2P Funding announced on 12 Feb 2008 to build a sustainable NGO sector. Ongoing. | 2.1/4.2 | Develop complete. Ongoing 2008 & beyond |
| 76 | Continue to promote the use of integrated contracts | MSD | Funding for Outcomes developed and implemented. These contracts now part of FACS core business under the Integrated Contracts team. |  | Complete |

# How this report works

The Ongoing Programme of Action Monitoring Report is organised into two sections:

- A summary section – which provides an overview of the key highlights over the previous two months, and identifies the hotspots that need to be monitored closely over the upcoming two months to ensure Objectives remain on track.

- A monitoring report section – which includes two key parts:

    - Summary information from the project plans for each Objective.

    - A summary of the progress of each Objective over the last three months and an overview of the work that is expected to occur over the next three months.

The Taskforce’s planning and reporting hierarchy consists of the following:

- Objectives – specific work that has been signalled in the programme of action

- Actions –  specific work signalled in the programme of action, as part of an Objective and/or in the Taskforce’s work programme which sits beneath the programme of action

- Key Milestones – taken from individual agency project plans.

There is also a formal variation process, which aims to:

- maintain the integrity of the Taskforce’s programme of action

- ensure there is transparent communication within the Taskforce about changes to Objectives and/or actions

- ensure the Objective and actions remain relevant to the Taskforce and its priorities.

A formal variation is required when a Taskforce agency wants to change an Objective, action or both. Formal variations are not currently required to change key milestones. However, any key milestone changes must be provided to the Secretariat and will be tracked in this Monitoring Report.

The variation template is attached to this report. An electronic copy can be obtained from the Taskforce Secretariat.

Reporting frequency

Ongoing Programme of Action Monitoring Reports will be produced for each Taskforce meeting. If a Taskforce meeting is changed to a workshop then a report will still be produced but will be circulated in hard copy only.

Other information

- The information in the monitoring report centres on the key milestone information provided by each Taskforce agency.

- To ensure the monitoring report remains current, as each milestone is reported complete it will be dropped from the report. The Secretariat will keep a record of all milestones so that this information can be used at a later date, if necessary.

| To | The Taskforce for Action on Violence within Families | Date |  |
| --- | --- | --- | --- |
| From |  |  |  |
| Security Level | In Confidence |  |  |
| Variation: request to amend Work Programme Objective |  |  |  |
| Action | For your approval |  |  |

I am seeking the Taskforce’s approval to change an Objective or action from the work programme for the Taskforce for Action on Violence within Families.

Current Deliverable:

[Insert Project / Work Programme Objective and/or Action]

[Insert current milestone/s (from project plan template)]

Changed to:

[Insert Project / Work Programme Objective and/or Action]

[Insert new milestone/s (also complete new project plan template)]

Reasons for a Variation Request

A variation to this deliverable has become necessary as:

- [please insert reason/s for variation]

Consultation

In seeking a variation to this deliverable, I have consulted and gained agreement from the following people:

| Name | Position and organisation |
| --- | --- |

Impact

The impacts in agreeing to this change are:

- [add details of any impact such as reporting to Cabinet, other key project timeframes, budget initiatives, reputation, legislation.]

The impacts in not agreeing to this change are:

- [add details of any impact such as reporting to Cabinet, other key project timeframes, budget initiatives, reputation, legislation.]

Recommendation

It is recommended that you:

- agree to a variation to an Objective or action found in the Taskforce’s work programme

[Insert Project / Work Programme Objective and/or Action]

[Insert new milestone/s (also complete new project template)]

Approve / Decline

| (Taskforce representative) |  |  |
| --- | --- | --- |
| (Taskforce agency) |  | Date |

| Peter Hughes |  |  |
| --- | --- | --- |
| Chair |  | Date |
| Approved  Not Approved  |  |  |