Ongoing Programme of Action

Monitoring Report

November 2008

Prepared by the Secretariat for the Taskforce for Action on Violence within Families

# Contents

Contents	3

Summary	5

Highlights	5

Hotspots	9

Variations	9

Alerts	9

Upcoming Objective Deadlines (next two months)	10

Changes to Monitoring Process	11

Monitoring Report	13

Three month summaries and milestone updates	15

Leadership	15

1.1  Facilitation of The Ongoing Programme of Action 	15

1.2  Maori Programme of Action	16

1.3  Pacific Programme of Action	17

1.4  Child Maltreatment	18

1.5  Family Violence Free Workplaces (MSD / ACC / NZ Police)	19

1.6  Iwi-Led Crime Prevention	22

1.7  Family Violence Clearinghouse	22

1.8  Case Studies Characterising Good Practice	24

1.9  Maori Research Agenda	25

1.10  Pacific Research Agenda	26

1.11  New Migrant and Refugee Research Agenda	27

1.12  Elder Abuse	28

1.13  Data on NGO Service Delivery	29

Changing Attitudes and Behaviour	31

2.1  Kia Puawai	31

2.2  Improving Attachment	31

2.3  Conduct Disorder / Severe Anti-Social Behaviour	32

2.4  Curriculum Development	34

2.5  Violence in the Media	37

2.6  Campaign for Action on Family Violence	37

2.7  Family Violence Death Review Project	40

Ensuring Safety and Accountability	41

3.1  Family Violence Courts	41

3.3  Social Services Supporting Courts	42

Effective Support Services	45

4.1  Maori Service Workforce Development	45

4.2  Pacific Service Workforce Development	45

4.3  Service Demand Data	47

4.4a  Training our Staff	47

First Programme of Action update	49

How this report works	55

# Summary

The Taskforce for Action on Violence within Families’ (the Taskforce) first programme of action initially consisted of 76 actions, which were later consolidated to 53 actions. A progress summary on these actions is provided towards the end of this report.

The Taskforce’s Ongoing Programme of Action (OPOA) originally consisted of 31 objectives which form the Taskforce’s work programme. Due to some of these being completed, there are now 26 objectives remaining. To meet each objective, actions and milestones have been identified. This report provides a progress report against the objectives, actions and milestones.

As objectives are completed or become business as usual, they are dropped from the Monitoring Report.

For more information on this report, how it is organised and the current formal variation process, please refer to the “how this report works” section at the end of the document.

Objective status

| On track | 16 |
| --- | --- |
| Complete or ‘Business as Usual’ | 5 |
| Alerts | 1 |
| Variations | 4 pending |
| Total number of objectives | 26 |

Changes to objectives

Objective 1.1a - Mapping the Ongoing Programme of Action. Following discussions with lead agencies of this objective it became clear that the outcomes were contained within objective 1.1 through monitoring of the work of the Taskforce by the Secretariat.

Objective 3.2 - Protocols for Family Violence Courts has been deleted. This objective is now complete.

Objective 4.4b - Training of Staff (CYF). This objective has been deleted as it is now business as usual and will be monitored within CYF.

Objective 1.5 - Family Violence Free Workplaces. The three lead agencies on this work, ACC, MSD and NZ Police are now working together to report on this Objective using one update. This was previously three, 1.5a, 1.5b and 1.5c and are now included in 1.5. The objective, purpose and actions have not changed, neither have deadlines. There has been some consolidation of key milestones.

## Highlights

This section provides an overview of key Taskforce initiatives for the reporting period of beginning of September 2008 to beginning of November 2008.

### Leadership

### Maori Programme of Action

Taskforce member organisations have provided the Maori Reference Group (MRG) with dedicated champions. These champions will work with the MRG representatives who will lead work on addressing the Actions as provided for in the MRG Programme of Action.

### Domestic Violence Act 1995 Review

Cabinet approved amendments to the Domestic Violence Act 1995 and related legislation in May this year. The Domestic Violence Reform Bill has been tabled in the House. It will be introduced when Parliament reopens, subject to the Government’s decision if and when to reinstate the Bill.

### Child Maltreatment Prevention

An additional Taskforce meeting was held on 4 November to discuss the Child Maltreatment Prevention work programme.  Presentations were given by Dr Pat Touhy (Ministry of Health) and Dr Patrick Kelly (Starship Hospital). The first presentation discussed attachment, focussing on the critical importance of early relationships between infants/children and their caregivers, and the intergenerational effects of socio-emotional and psychological damage.  The second presentation discussed the role of the health system in preventing child maltreatment, and the potential child protection role for the health system workforce.

### Changing Attitudes and Behaviour

### Campaign for Action on Family Violence

There were 35 successful applicants in the third round of the Community Action Fund. The fourth round is open for applications and will close in March 2009. The opening date for applications has been brought forward to give applicants more time to prepare their applications through the summer months.

The third reach and retention tracking survey conducted in September 2008 shows positive trends for awareness of the campaign with overall awareness up to 95 per cent, an increase from 89 per cent in April 2008.  Survey results show the TV advertisements are having a strong impact on Maori (98 per cent males and 99 per cent females) and Pacific (90 per cent males and 89 per cent females) population groups.  More than one in five (22 per cent) of those who have seen the TV advertisements reported taking some action as a result.

The data collection for the attitudes towards family violence face-to-face survey is now complete and involved 2,500 face to face interviews with New Zealanders.  The survey asks about New Zealanders’ attitudes, values and beliefs about family violence, the propensity to act, and awareness of the Campaign for Action on Family Violence. The data is currently being analysed.

### Family Violence Death Reviews

The first meeting of the Family Violence Death Review Committee (FVDRC) was held on 2 October, with an induction day held the day before. A representative of the Taskforce will be attending the meeting in February 2009 to present on the work of the Taskforce, and ensure ongoing communication and collaboration between the FVDRC and the Taskforce. This committee will review all deaths attributed to family violence, and recommend ways of ensuring a reduction in the number of deaths.

As this objective has been completed it will be removed from future Monitoring Reports. The Committee will annually update the government, with the Taskforce also receiving the reports. Ongoing business as usual will be monitored by the Ministry of Health, as the lead agency for this work.

### Ensuring Safety and Accountability

### Family Violence Courts

The Palmerston North Family Violence Court became operational on 12 September 2008.  The Whangarei Family Violence Court is to open in April 2009, and training for key stakeholders has been confirmed for February 2009.

### Social Services Supporting Family Violence Courts

The Project Plan and Terms of Reference for this objective have been finalised and agreed. The Ministry of Justice has begun work on developing the role of an independent victim advocate / support person to provide support and assistance to victims of domestic violence in the Family Violence Courts in conjunction with MSD.  A draft role description for the advocate role was sent out to NGOs and external government agencies in September 2008.

NGO members of the Taskforce met with Ministry of Justice, MSD, Police and the Chief District Court Judge to discuss the advocate role in October 2008.  As a result of this meeting it was agreed that a framework for a collaboration protocol would be developed and agreement gained about the overarching principles, goals and objectives for getting information about victims through to the Court.  This framework will be developed over November/December 2008.

### Effective Support Services

### Pathway to Partnership

The Pathway to Partnership working group is well through the process of working with social service family violence service providers.  The majority of providers have already received a contract variation with the 2008/09 full funding rate increases.

Discussions are currently being held with providers to understand the full cost of their essential services.  Over the next few months there will also be joint regional workshops on the results based accountability model for providers and for MSD staff

From here, planning on how communities, government and the sector work together to deliver high-quality, effective services to families, children and young people will progress.

As the next phase of Pathway to Partnership progresses, there will be a focus on how agencies work together to achieve the results we want to see in our communities. While additional funding is a key component, Pathway to Partnership is, just as importantly, about changing the way agencies work together and work with families.

## Hotspots

This section highlights objectives that are subject to variation or have been identified as areas of risk. All objectives not mentioned in this section are on track to be completed as planned.

### Variations

Variations are formal requests for changes to objectives and/or actions in the Taskforce’s Ongoing Programme of Action. This table includes all approved Variations of objectives from the Ongoing Programme of Action.

| Approved variations |
| --- |
| Objective | Title | Variation summary | Status |
| 3.3 | Social Service Supporting Courts | The objective remains the same, changes to the actions required. | Approved 4 April 2008. |
| 2.4 | Curriculum Development | The objective remains the same, changes to the actions required. | Approved 28 March 2008. |

### Alerts

This table highlights areas that have been identified as at risk of not being delivered as planned.

| Objective | Title | Issue | Mitigation |
| --- | --- | --- | --- |
| 2.2 | Improving Attachment | Due to issues coming to light during initial project scoping, this objective is likely to be the subject of a variation. | To be confirmed in early 2009. |

### Upcoming Objective Deadlines (next two months)

This table highlights Objective deadlines that are due over the next two months, or that have been completed and further deadlines need to be defined. If deadlines are not likely to be met, agencies should contact the Secretariat to discuss a possible variation.

| Objective | Title | Agency | Objective Deadline |
| --- | --- | --- | --- |
| 1.9 | Maori Research Agenda | Te Puni Kokiri | December 2008 |
| 1.12 | Elder Abuse | Ministry of Social Development | December 2008 |
| 2.5 | Violence in the Media | Families Commission | February 2009 |

## Changes to Monitoring Process

The Secretariat has recently reviewed the monitoring process. Part of this review has been ensuring that Objectives and Actions are outcome focussed, with the understanding that process milestones are important in tracking work towards outcomes.

The reason for the review is that, after almost a year of working towards the objectives of the Ongoing Programme of Action, there is a need to ensure that reporting remains focussed on the key pieces of work.

The review of the monitoring process is also directly related to the changes to the variation process. A variation process that involves the Taskforce approving major changes is likely to be developed. Major changes would be those that relate to the outcome of a piece of work, or the deadline for completion of the outcome. Any changes to the process to achieve an outcome would be flagged in the Monitoring Report. How the Taskforce will approve these major changes has yet to be confirmed.

Variation Request Process

The variations below have not yet been approved, and will be progressed once the variation process is finalised.

| Objective | Title | Variation summary | Status |
| --- | --- | --- | --- |
| 1.9 | Maori Research Agenda | There has been some delay to this project due to lack of availability of specialist Maori contractors, case study organisations and the expert steering group. A revised deadline of 5 September 2008 has been requested. | Submitted 18 July. This variation has now been overtaken. |
| 1.10 | Pacific Research Agenda | Changes to actions have been requested, although the objective will remain the same. | Initial variation submitted in June was not approved. A new variation will be submitted. |
| 3.1 | Family Violence Courts | The objective remains the same. The objective deadline has been missed. The Palmerston North Court became operational in September 2008, the Whangarei Court is due to be operational in April 2009. | Submitted 31 July by the Judiciary (through MoJ). |
| 4.2 | Pacific Service Workforce Development | This project plan is now part of the Pathway to Partnership work on workforce provider capacity and capability. Although a project plan was completed within the deadline, the Steering Group has decided that other areas are of first priority. | Submitted 22 July, not approved. Due to be resubmitted. |
| Action 66 (first programme of action) | Determine level of attendance and performance of perpetrators at programmes | The Ministry of Justice is currently collating and analysing data. A final report will be completed by 30 September 08. The results from this will be used to inform Action 67. | Submitted 31 July. This variation has now been overtaken. |

# Monitoring Report

The Detailed Milestone Updates and Three Month Summaries section. This section outlines progress on each milestone and provides an update on work undertaken in the previous three months (September to November) and work which is upcoming in the next three months (December to February).

## Three month summaries and milestone updates

This section provides updates on each milestone, and updates on both work undertaken in the previous three months and work planned for the upcoming three months.

### Leadership

| 1.1 FACILITATION OF THE ONGOING PROGRAMME OF ACTION (OPOA) |
| --- |
| Lead agency | Taskforce Secretariat / All Taskforce agencies |
| Project Manager | Carra Hamon |
| First Programme of Action reference | Action 3 |
| Objective and actions (as per Work Programme) Facilitation, implementation and strategic engagement of the Ongoing Programme of Action for specific groups and across all sectors in New Zealand. Actions include: stewardship of the Ongoing Programme of Action work programme stewardship of children specific work programme stewardship of all other work programmes. |
| Objective deadline | Ongoing |
| Purpose To successfully monitor and ensure implementation of the Ongoing Programme of Action. |
| Key Milestones | Date | Description of Progress |
| 1.1.7 | Protection Orders update to be sent to Minister. | April 09 | Delayed until March/April 2009. Delay will enable a full one-year progress report to be developed. |
| 1.1.9 | Review of all objectives, actions and milestones in the Monitoring Report. | 31 Dec 08 | On track. As directed by the Chair of the Taskforce. This will include a review of the variation process. |
| 1.1.10 | Monitoring Report for September prepared and sent with 1 October meeting papers. | 18 Sept 08 | Complete. |
| 1.1.11 | Facilitate additional Taskforce meetings. | 4 Nov 08 19 Nov 08 | Complete. |
| 1.1.12 | Monitoring Report for November prepared and sent with 10 December meeting papers. | 28 Nov 08 | On track |
| Progress to date (previous 3 months work) Review of Monitoring Report format and variation process. An additional Taskforce meeting on Child Maltreatment Prevention and on Te Rito were held on 4 November and 19 November respectively. Current ongoing work (next 3 months) Preparing the Monitoring Report for the 10 December 2008 Taskforce meeting. Planning for 2009, including meeting dates and upcoming reporting. Planning for the February workshop. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 1.2 MAORI PROGRAMME OF ACTION |
| --- |
| Lead agencies | Maori Reference Group (MRG) Ministry of Social Development (MSD) |
| Contributors | Te Puni Kokiri, NGOs |
| Project Manager | Ann Dysart (MSD) |
| First Programme of Action reference | Action 7 |
| Objective and actions (as per Work Programme) A Programme of Action focused on eliminating violence in Maori whänau is developed. Actions include: developing a Maori Programme of Action ensuring the leadership and ownership of the actions at all levels of Te Ao Maori ensuring all designated actions are monitored and achieved. |
| Objective deadline | June 2013. (As from September 2008 MRG is consolidating the Action Plan that covers a five year period from October 2008 to June 2013) |
| Purpose To develop a process and plan that engages all areas of Te Ao Maori in owning and addressing the issues of Family Violence and Child Abuse To progress implementation of MRG’s Action Plan in order to achieve zero tolerance of whanau violence. |
| Key Milestones | Date | Description of Progress |
| 1.2.4 | Launch Maori Programme of Action (MPOA) | June 08 | Complete. The draft MPOA was signed-off by the Taskforce at its meeting on 6 August, and has been distributed to relevant officials. |
| 1.2.5 | Work towards establishing an action plan for 2008 - 2009 and priorities for next five years | August 08 | Complete. An Action Plan for 2009 – 2013 has been developed and was presented to MRG at the 24 September meeting. Further work to take place at future meetings. |
| Background The Taskforce’s MRG has developed a Maori Programme of Action (MPOA). Progress to date (previous 3 months work) Notes being collated for the Regional Hui completed earlier this year. Writing the Action Plan for 2009 – 2013. Current ongoing work (next 3 months) Collation of Regional Hui notes for analysis and dissemination to MRG. Ongoing work and consolidation of the Action Plan for 2009 – 2013. Work with agencies through the dedicated champions the Taskforce members have provided to ensure input into all key policy work. Timing / Ongoing / Recommendations / Conclusions Status = On track. |

| 1.3 PACIFIC PROGRAMME OF ACTION |
| --- |
| Lead agency | Pacific Advisory Group (PAG) Ministry of Social Development (MSD) |
| Contributors | Ministry of Pacific Island Affairs, NGOs |
| Project Manager | Liz Tanielu (MSD) |
| First Programme of Action reference | Action 7 |
| Objective and actions (as per Work Programme) Programme of Action focused on eliminating violence in Pacific families is developed. Actions include: Develop a Pacific Programme of Action (PPOA). Hold discussions with agencies to confirm action areas of responsibility and process for implementation. Develop the leadership action area to be coordinated by MSD with PAG. |
| Objective deadline | June 2013 (second phase). |
| Purpose To develop and implement a plan to address family violence within Pacific families. (This updated purpose statement reflects the second phase of the work on this objective) |
| Key Milestones | Date | Description of Progress |
| 1.3.4 | Release of Pacific POA | Sept 08 | Completed. |
| 1.3.5 | Hold discussions with agencies on the action areas and implementation process. | Oct 08 | Commenced. Discussions continue to be held with agencies to further develop the process and action areas. To be completed in November 2008. |
| 1.3.6 | Finalise implementation timeline and actions areas. | Nov 08 | Ongoing – some minor delay. |
| 1.3.7 | Key agreed milestones incorporated into the TF monitoring report. | Jan 09 |  |
| 1.3.8 | PAG membership reviewed and updated. | Feb 09 |  |
| Progress to date (previous 3 months work) Individual meetings with senior officials from agencies responsible for PPOA action areas to define work programmes had commenced. PAG provided advice to projects such as Child Maltreatment, Pathway to Partnership, Pacific Research Agenda, and the Family Violence Campaign. With the completion of the PPOA and the current implementation focus, discussions have commenced on PAG’s future direction, role and membership. Current ongoing work (next 3 months) Complete meetings with government agencies on the implementation phase of the PPOA. Provide Pacific advice to projects such as Pathway to Partnership, Child Maltreatment, Pacific Research Agenda, and the Family Violence Campaign. Finalise and update PAG’s role and membership. Timing / Ongoing / Recommendations / Conclusions Status = On track. |

| 1.4 CHILD MALTREATMENT |
| --- |
| Lead agency | Office of the Children’s Commissioner |
| Contributors | MSD, NGOs, NZ Police, Ministries of Justice, Health and Education |
| Project Sponsor | Dr Cindy Kiro |
| Project Manager | John Angus / Ruth Palmer (MSD) |
| First Programme of Action reference | N/A |
| Objective and actions (as per Work Programme) The objectives of the second phase are to agree and then carry out the work programme. The work programme comprises an integrated, cross sector approach to preventing child maltreatment. It draws on a growing evidence and knowledge base about the impacts of maltreatment. |
| Objective deadline | 30 June 2009 (second phase) |
| Purpose The Taskforce has agreed to give priority to the prevention of child maltreatment over the next three years, and has agreed the scope, focus and priorities of the proposed work programme. The purpose of the work for 2008 – 2009 is to: Enhance the contribution of the health, education and social services sectors to prevention of child maltreatment. Understand better and take actions to reduce the incidence and prevalence of neglect, in particular of 0 – 5 year olds. Strengthen effective community responses. |
| Key Milestones | Date | Description of Progress |
| 1.4.5 | Work programme agreed. | Aug 08 | Completed. Final full agreement at 1 October Taskforce meeting. |
| 1.4.7 | Project plans for the nine projects are completed. | Sept 08 | Project plans for the five priority plans (1.4.8-9 and 1.4.12 are completed). In regard to the remaining four project plans, please see below (‘Progress to date’). |
| 1.4.8 | Complete the review of the Health, Education and Social Service Sector Contributions to child maltreatment (3 of the 9 projects). | 31 Mar 09 | Commenced and on track. |
| 1.4.9 | Undertake research into neglect. | 30 Jun 09 | On track. |
| 1.4.10 | Prepare advice on a child maltreatment prevention phase of the Campaign. | 31 Aug 08 | Will be reported at 10 December meeting. |
| 1.4.11 | Commence a child maltreatment phase of the Campaign. | 30 Jun 09 | On track. |
| 1.4.12 | Take actions to work with communities to strengthen their preventive responses to child maltreatment including: gathering evidence for what works by 31 December 2008 providing greater support for successful community approaches by 31 March 2009 supporting philanthropic sector plans for a trial of new approaches and commencing an evaluation of any trial by 30 June 2009. | 30 Jun 09 | On Track. |
| Background The Ongoing Programme of Action, includes developing a work programme on child maltreatment (including child sexual abuse) that: focuses on improving outcomes for children takes account of the different types of child maltreatment identifies priority areas where the Taskforce can make a difference. Progress to date (previous 3 months work) Work has commenced on the review of the Health and Social Services Sectors, the Working with Communities project, Coordination, Neglect and Campaign work streams. The External Advisory Group (EAG) met with Taskforce members on 4 November. The EAG will continue to be available for expert advice throughout 2008 – 2009. Project plans for the five priority plans (1.4.8-9 and 1.4.12 are completed). In regard to the remaining four project plans: A project plan for 1.4.10 will be considered after the decision of the Taskforce at the December meeting. A project plan for the strategic conversation project will be completed in the new year after discussions with the projects sponsor. Project plans for the research and improving coordination and collaboration of prevention activities will be completed in the new year after some initial scoping work and a brief literature review. Current ongoing work (next 3 months) Continue work on the agreed 2008 – 2009 outputs. Timing / Ongoing / Recommendations / Conclusions Status = on track |

| 1.5 FAMILY VIOLENCE FREE WORKPLACES (MSD / ACC / NZ Police) |
| --- |
| Lead agency | MSD, ACC, Police |
| Contributors | NGOs |
| Project Manager | David Dick (MSD), Danielle George (ACC), Carol Train (Police) |
| First Programme of Action reference | N/A |
| Objective and actions (as per Work Programme) Family Violence-Free Workplaces are developed and implemented through HR policy – link to Campaign, model for other agencies, role model for public and other workplaces. Actions include: develop policy put in place tools and resources training of contact people/family violence co-ordinators implementation develop a model for replication in the public sector and private sector. |
| Objective deadline | May 2012 |
| Purpose Family Violence Free Workplaces means staff in those workplaces are aware and supported around issues to do with family violence. These workplaces are expected to provide low cost high impact prevention and recovery opportunities for members of the workplace who are affected by family violence. They may be victims, observers or perpetrators. Implementing Family Violence Free Workplaces is expected to decrease workplace stress, and increase workplace productivity by empowering and supporting victims and observers of family violence and channelling perpetrators through appropriate channels to help them change their behaviour. |
| Key Milestones | Date | Description of Progress |
| 1.5.1 | Policy developed and agreed. | Dec 2008 | On track. |
| 1.5.2 | Tools, resources and training to support and promote the policy, and raise awareness of family violence are developed, agreed, and implemented. | Dec 2009 | On track. |
| 1.5.3 | Assessment and evaluation of agency programmes. | Dec 2010 | On track. |
| 1.5.4 | Develop Blueprint/model for implementing Family Violence Free Workplaces in public, private and non-government sectors. | June 2011 | On track. This Blueprint will be a collaborative work between Police, MSD and ACC. |
| Context and background Objective 1.5 was initially split into three project plans reflecting the work of MSD (1.5a), ACC (1.5b) and the NZ Police (1.5c). All three organisations have been working toward the same Objective since the development and agreement of the Ongoing Programme of Action in late 2007. MSD, ACC and NZ Police have met regularly to work together, share knowledge and learning, and will continue to do so. MSD HR will liaise with Project Managers from all three organisations to provide updated information for each Monitoring Report. The consolidation of these work programmes into one project plan will more clearly reflect the overall Objective of developing a Family Violence-Free Workplaces model for replication in the public sector and private sector. The Objective and Actions, and deadlines for completion have not changed. The only addition is that ACC has completed the first phase (to Dec 2008), and will continue ongoing work with the next phase to review the effectiveness of the support packages, tracking of progress and research effectiveness. Completed work (since 2007) MSD General awareness information sessions on family violence held for National Office staff. In-depth sessions on family violence held for HR staff. Campaign posters distributed and poster display in National Office foyer. Distributed resources eg. ‘Are you OK?’ booklets. Establishment of Family Violence Peer Support Programme in Work and Income. Published resources and information about referral service on the intranet. Published a highly visible ‘It’s not OK?’ advert on intranet homepage. Included family violence campaign ‘It’s not OK?’ page in 2008 Calendar for staff. Ensured the provision of family violence counselling as a criterion in the RFP for an EAP provider. ACC In-depth training on family violence delivered to HR staff. Partnership approach developed with Stratos. Development of a support package on family violence for staff. Support package and partnership launched to staff as part of Safety NZ Week – Safety in the Home, available on intranet and via text service. Manager’s guide published on intranet. Policy development, launched as part of Staff Wellbeing Programme. Police Timeline developed with key milestones. Internal working group established (consisting of HR (lead), Operations group, Police group, Training Service centre and District representation). Draft policy finalised. Progress to date (previous 3 months work) MSD Completed service line consultation on the draft Policy. Completed service line consultation on the draft Managers Guidelines to support the Policy. ACC Support package publicised to staff via staff DVD and launched by the General Manager Strategic Policy & Research. All programmes are now on track and in place across ACC (completion of first phase by Dec 2008). Police A working group was established to provide feedback for the writing of the draft policy. The working group included representation from HR, Policy, Operations and District. The final draft version is now complete. Current ongoing work (next 3 months) MSD Progress draft Policy and Managers’ Guidelines through the approval process and plan for implementation (by taking it to the MSD Leadership Team for consideration). Ministry promotional material and resources will be provided to staff to further raise awareness. Material and resources will support the launch of the Policy and Guidelines (pending approval from the Leadership Team). Review of Work and Income Peer Support Programme due in November 2008. ACC Re-launching support package and the Policy to complement White Ribbon Day (25 November 2008). Chief Executive championing the messages across ACC. Review the effectiveness of the support package at the six month mark (end of December 2008). Research the development of the workplace Policy that extends influence to outside the workplace. Develop ongoing communications plan to ensure staff awareness and track progress of programme. Police The final draft version of the Policy will go to GM:HR for approval to start formal consultation process. Once the consultation period is complete, appropriate changes will be made and the final Policy will go to the Police Executive for formal sign off. The completed policy will be signed off by 31 December 2008. Timing / Ongoing / Recommendations / Conclusions Status = On track. |

| 1.6 IWI-LED CRIME PREVENTION |
| --- |
| Lead agency | New Zealand Police |
| Contributors | Iwi, NGOs, Te Puni Kokiri, MoJ (including Crime Prevention Unit) |
| Project Manager | Wally Haumaha |
| First Programme of Action reference | N/A |
| Objective and actions (as per Work Programme) Iwi-led crime prevention plans which have a focus on the prevention of family violence Actions include: provide support to iwi to develop plans iwi-led crime prevention strategies developed in accordance with each iwi’s identified needs, values and timeframes. Maori Family Violence scoping studies (new Action, detail provided below). |
| Objective deadline | The NZ Police state that this is an iterative and evolving process that is being driven by iwi. Precise deadlines are neither available, nor appropriate at this stage. |
| Purpose In absolute numbers, a high number of Maori churn through the criminal justice system every year. A new framework for action is being developed by Maori with assistance from officials. That new framework is Iwi-led Crime Prevention Plans (ICPPs). ICPPs take a long-term, incremental approach to improving Maori criminal justice outcomes. They are led by iwi, with assistance from officials. |
| Key Milestones | Date | Description of Progress |
| 1.6.1 | Iwi to populate their crime prevention plan templates | No deadline | On track |
| 1.6.2 | Officials to condense those templates into A3 summaries | No deadline | Pending |
| 1.6.3 | Summaries to be presented back to iwi for confirmation | No deadline | Pending |
| 1.6.4 | Ministerial briefing paper to Ministers of Justice, Police and Maori Affairs | March 2008 | Complete |
| New Action (as above) - Maori Family Violence scoping studies. The Commissioner has asked his Maori Focus Forum to go back to each of their Districts and begin compiling a comprehensive profile on family violence issues among Maori regionally. He further requested Police Policy Group to provide technical assistance. This has culminated in a three page scoping document for each of the forum members to take back to their areas to complete. It is hoped that this will help facilitate ICPPs, by giving iwi a very specific focus (the idea is that they will start small and grow over time) while at the same time progressing whole of Government work on Family Violence. Background recent work (2007/2008) Police and Te Puni Kökiri have been supporting iwi with the necessary tools to develop and design their own Plans. The type of support provided includes: providing Police intelligence to iwi groups that enable iwi to understand the crime problems and profiles of Mäori (offenders and victims) within their geographical areas providing specialised trained staff who are able to take iwi through a formal problem solving approach to crime prevention crime prevention methodology training in SARA and POP models providing draft Iwi Crime Prevention Plan templates and Guidance Notes for preparation of the Iwi Plans funding writers nominated by iwi to begin drafting iwi-specific crime prevention plans. Progress to date (previous 3 months work) Amendments have been made to Te Arawa's plan, following public submissions and substantive approval from iwi. A writer has been appointed for the joint plan for Auckland-metro, but awaits terms of reference. Ngapuhi have appointed a writer who is near completion of the first draft. A writer for Waikato has been appointed and will begin writing the plan soon. Te Tau Ihu had already prepared a crime prevention plan prior to the commencement of the ICPP process, and are in the throes of re-validating that. Ngai Tahu are about to commence engaging with runaka throughout the South Island. Current ongoing work (next 3 months) Police are continuing to work with iwi across all Police districts. The inter-agency working group (NZP, TPK, MoJ) has re-convened, meeting as required. TPK has indicated that they see much of the remaining work as operational, and see their regional offices as the main point of contact in the next phases. A status report has been developed and is being circulated monthly to the key inter-agency group, plus other Government Stakeholders. Police are leading an exploratory budget bid to provide funding for the process required to compile the plan and some small pilot projects. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 1.7 FAMILY VIOLENCE CLEARINGHOUSE |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | Families Commission, NGOs |
| Project Manager | Jeff Sheerin |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) The New Zealand Family Violence Clearinghouse (NZFVC) is enhanced to ensure its efficacy and to become the independent, sustainable, comprehensive one-stop shop for national and international information on family violence. Actions include: develop a model and systems which optimise the operations of the NZFVC. |
| Objective deadline | June 2009 |
| Purpose To review NZ Family Violence Clearinghouse activities and services and develop a strategy for moving forward. |
| Key Milestones | Date | Description of Progress |
| 1.7.2 | Scope redevelopment of NZFVC project, identify requirements and develop strategy | Sept 2008 | Now well underway. We have been consulting with key stakeholders to look at requirements for the NZFVC moving forward and MSD IT to gather requirements for the new website. |
| 1.7.3 | Develop 2-5 year strategy | 30 June 2009 | We have started discussions around the new strategic plan and associated work programme. We are currently reviewing previous plans and will be sending a new draft out to key stakeholders for comment in December. |
| 1.7.4 | Develop project plan and secure funding | Sept 2008 | Complete. Planning for long term sustainable clearinghouse website from 1 March 2009. Cabinet funding is ongoing. |
| 1.7.5 | Implement new clearinghouse website and service | 28 Feb 2009 | Planning now underway and initial work definitions document developed with MSD IT. We are aiming to have the site live in March 2009. |
| Progress to date (previous 3 months work) Work is underway for a new NZFVC website on the basis of the IT operations for the NZFVC now being in-house in MSD. The current focus is on gathering user needs and ideas around the look and feel of a new NZFVC website. We currently have an online survey in circulation and have been undertaking meetings with key stakeholders and Advisory Group members. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 1.8 CASE STUDIES CHARACTERISING GOOD PRACTICE |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | NGOs, MoJ, Police |
| Project Manager | Dorothy Adams |
| First Programme of Action reference | N/A |
| Objective and actions (as per Work Programme) Case studies characterising good practice in service aimed at eliminating family violence are developed and made publicly available. Actions include: scope and identify existing good practice models record the characteristics of their success index and deposit in Family Violence Clearinghouse. |
| Objective deadline | October 2008 |
| Purpose To describe and generalise good practice principles as they apply to family violence prevention. |
| Key Milestones | Date | Description of Progress |
| 1.8.3 | Final case studies | Oct 2008 | Completed |
| Background Current evaluative activities will be used to identify good practice models. The project will commence by drawing on one of the evaluative activities that support the Campaign for Action on Family Violence (the Campaign). The case studies will therefore focus on the practice of family violence prevention through social marketing. The aim of the evaluation project is to investigate and illustrate the impact of the Campaign on selected communities. It will focus on collecting information on observable and recorded changes relating to family violence over time in selected communities. As part of this evaluation two case studies will be produced that illustrate and explain “significant changes” arising from the Campaign. Progress to date (previous 3 months work) Case studies have been completed. Digital stories have been developed, describing and documenting good practice in family violence prevention. One digital story has been completed, and the second will be complete by the end of December 2008. Current ongoing work (next 3 months) Digital stories documenting case studies of good practice will be indexed and deposited in Family Violence Clearinghouse in 2009. Timing / Ongoing / Recommendations / Conclusions Status = Completed. This Objective will be deleted from future Monitoring Reports. |

| 1.9 MAORI RESEARCH AGENDA |
| --- |
| Lead agency | Te Puni Kökiri |
| Contributors | MRG, MSD, Families Commission, NGOs |
| Project Manager | Te Atarangi Whiu |
| First Programme of Action reference | New initiative |
| Objective and actions (as per Work Programme) Improve our understanding of the nature of family violence in whänau Mäori and successful models of prevention and intervention. Actions include: review existing literature develop a research agenda link to the Taskforce strategic research agenda for family violence prevention recommend further action. |
| Objective deadline | 5 September 2008 [Completed to 5 September. Further work outlined, completion date to be determined.] |
| Purpose To increase the evidence base by providing case studies of a minimum of three Maori designed, developed and delivered programmes. |
| Key Milestones | Date | Description of Progress |
| 1.9.2 | Key findings presentation to Taskforce meeting | 6 Aug 2008 | Complete. Key findings noting paper distributed to Taskforce. Not presented at October Taskforce meeting as Secretariat advised that it had a full agenda. |
| 1.9.3 | Final Report | 5 Sep 2008 | Summative report completed, but need to draft a document that summarises the suite of outputs (literature review, 3 case studies and summative report) and recommended research agenda. |
| Background Te Puni Kōkiri is working to identify current information regarding family violence for Maori, and looking at culturally distinct models of prevention and intervention for Maori. It is expected that an agenda for research will emerge from this work. Three key outputs for this work were identified: Output One: A literature review intended to identify current information on Maori family violence, information gaps, inconsistencies, and themes within the literature on family violence and Maori. Output Two: A case study analysis of existing Maori designed, developed and delivered initiatives that address family violence. Output Three: A summative report that analyses output one and two and identifies research priorities to form a Maori Research Agenda. Progress to date (previous 3 months work) Key deliverables completed – literature review, case studies and summative report Current ongoing work (next 3 months) Drafting report summarising the suite of outputs (literature review, 3 case studies and summative report) and recommended research agenda Timing / Ongoing / Recommendations / Conclusions Status = Complete to 5 September. Variation submitted for delayed timing, but now overtaken. |

| 1.10 PACIFIC RESEARCH AGENDA |
| --- |
| Lead agency | Ministry of Pacific Island Affairs (MPIA) |
| Contributors | PAG, MSD, Families Commission, NGOs |
| Project Manager | Diane Anorpong |
| First Programme of Action reference |  |
| Objective and actions (as per Work Programme) The variation submitted in July 2008 was not approved, a new variation is due to be submitted. The below objective is the original objective. |
| Improve our understanding of the nature of family violence in Pacific families and successful models of prevention and intervention. Actions include: Review existing literature Develop research agenda Link to the Taskforce strategic research agenda for family violence prevention Recommend further action. |
| Objective deadline | Final deadline to be confirmed (subject to variation). |
| Purpose To develop an understanding of Pacific family violence research priority topics and the issues which surround Pacific family violence research. |
| Key Milestones | Date | Description of Progress |
| 1.10.1 | Finalise project plan | April 2008 | Complete. Project plan finalised, stakeholder discussions completed. |
| 1.10.2 | Consult with Pacific Advisory Group (PAG) | June-July 2008 | Ongoing. Initial discussion at first available meeting (Oct 2008), ongoing consultation taking place. |
| 1.10.3 | Consult with other Pacific stakeholders | August 2008 | Delayed. |
| 1.10.4 | Completion of report | September 2008 | Delayed. |
| Background The Pacific Family Violence Research Agenda will sit within a Pacific Research Agenda. Progress to date (previous 3 months work) On 15 October MPIA met with PAG again about its Family and Sexual Violence work. MPIA presented the draft findings of its Pacific Sexual Violence Prevention Report and received feedback, MPIA also outlined its future direction for family violence work which is to focus on supporting the Pacific Programme of Action. Current ongoing work (next 3 months) MPIA will meet with Elizabeth Powell, Director Pacific Development at Counties Manukau District Health Board and Liz Tanielu to discuss links between the Pacific Programme of Action and the Counties Manukau District Health Board (CMDHB) Pacific Family Violence Action Plan. The Ministry is committed to supporting the Pacific Programme of Action sitting within the Family Violence Taskforce and developed by the PAG. The Ministry intends to provide advice on the implementation of this work programme and support opportunities for dialogue between Pacific leaders and other stakeholders. Timing / Ongoing / Recommendations / Conclusions Status = delayed. The variation submitted in June 2008 was not approved. A new variation is due to be submitted. |

| 1.11 NEW MIGRANT AND REFUGEE RESEARCH AGENDA |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | NGOs |
| Project Manager | Dorothy Adams |
| First Programme of Action reference | N/A |
| Objective and actions (as per Work Programme) Improve our understanding of the nature of family violence in new migrant and refugee families and successful models of prevention and intervention. Actions include: review existing literature develop a research agenda link to the Taskforce strategic research agenda for family violence prevention recommend further action. |
| Objective deadline | To be provided after the scoping phase, in December 2008 |
| Purpose A statement of purpose will be developed in the scoping phase. |
| Key Milestones | Date | Description of Progress |
| 1.11.1 | Synthesis of literature | April 2008 | Annotated bibliography completed. |
| 1.11.2 | Scoping paper | Dec 2008 | On track. |
| 1.11.3 | Recommendations for further action | March 2009 | On track. |
| Progress to date (previous 3 months work) A scoping paper setting out an approach to research to strengthen knowledge on family violence prevention in migrant and refugee families has been drafted and circulated to Officials from MSD and Office for Ethnic Affairs and Department of Labour for feedback. Current ongoing work (next 3 months) Once feedback has been incorporated, further consultation to recommend further action. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 1.12 ELDER ABUSE |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | NGOs |
| Project Manager | Cilla Corlett |
| First Programme of Action reference | N/A |
| Objective and actions (from work programme) Improve our understanding of the nature of elder abuse and successful models of prevention and intervention. Actions include: review existing literature develop a research agenda link to the Taskforce strategic research agenda for family violence prevention recommend further action. |
| Objective deadline | Final deadline to be confirmed by December 2008 (NB: date changed from October as not possible to present at October Taskforce meeting) |
| Purpose/Expected Outcome Improved decision-making about viable programme and service delivery to eliminate elder abuse and neglect within the family setting. |
| Key Milestones | Date | Description of Progress |
| 1.12.2 | Develop a research agenda. | 30 July 2008 | Completed. MSD and Age Concern NZ have prepared a report to the Taskforce with recommended priorities for further action on elder abuse and neglect (with a recommended research agenda included as part of this). |
| 1.12.3 | Link to the Taskforce strategic research agenda for family violence prevention. | Complete | Completed. Sent the recommended research agenda to the Families Commission for inclusion into the Commission’s research agenda. |
| 1.12.4 | Recommend further action. | -10 Dec 2008 -February 2009 -2009/10 | -On track. Report to Taskforce (for Taskforce December 2008 meeting) with recommended priorities for action. (milestone date changed as could not go to Oct Taskforce meeting). -Broader consultation with sector to gain wider engagement with plans -Implementation of action plan |
| Background The proposed research agenda on Elder Abuse and Neglect is covered in the report to the Taskforce in December 2008. Progress to date (previous 3 months work) Priorities for further action identified. Initial consultation with sector on issues and priorities. The report for the Taskforce’s October meeting was not included on the agenda due to competing priorities. It has been re-scheduled for the Taskforce’s December 2008 meeting. Current ongoing work (next 3 months) Report to Taskforce (for Taskforce December 2008 meeting) on work undertaken on elder abuse and neglect to date, with an outline of proposed priorities for further action. Broader consultation with sector to gain wider engagement with plans. Commence implementation of action plan. Timing / Ongoing / Recommendations / Conclusions Status = On track. Final deadline to be confirmed. |

| 1.13 DATA ON NGO SERVICE DELIVERY |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | NGOs, ACC, MoJ, Police, MoH |
| Project Manager | Dorothy Adams |
| First Programme of Action reference |  |
| Objective and actions (from work programme) High quality data available about services delivered by, and on the demand for, NGO and agency family violence services. Actions include: develop systematic and accurate data on services. |
| Objective deadline | Ongoing |
| Purpose To understand the family violence services available and the ongoing demand for services – both volume and type. This work is aligned with the “Pathway to Partnership” initiative. |
| Key Milestones | Date | Description of Progress |
| 1.13.1 | Scoping study and project plan. | July 2008 | Complete. Planning completed based on undertaking data collection analysis first. |
| 1.13.2 | Determine reporting and monitoring information requirements, data currently available and data collection methods. | TBC | Work has been re-prioritised to allow resources to complete information model trial activity. Timeline (including completion date) being re-planned at present to align with outcomes framework. |
| 1.13.3 | Determine requirements for reporting and evaluation systems support (linked to the Outcomes Framework Project). | TBC | Deferred until outcomes framework completed. Timeline being re-planned at present to align with 13.3.2. |
| 1.13.4 | Conduct a monitoring and reporting trial of an information model with NGO and MSD participants. | 30 Oct 2008 | Completed. Preliminary trial of the information model completed. Areas for enhancement and clarification identified and to be incorporated in the model before further trial conducted. 30 March 2008 |
| 1.13.5 | Define the requirements that relate to potential ongoing information management solutions. | TBC | Follows data collected in 1.13.2. Due to re-planning, the completion date is now to be confirmed. |
| Background As part of Pathway to Partnership (P2P) initiative, which is aimed at ensuring a sustainable social sector for NGOs providing essential services for families, children and young people, a data monitoring system that focuses on outcome measures will be developed and implemented in collaboration with the sector. This monitoring system will provide high quality data about service outcomes. All essential Family Violence prevention services will be part of this initiative. Current ongoing work (next 3 months) Terms of Reference for investigating the development of a data collection system was approved by the Pathway to Partnership Management Group. The key milestones and deliverables are currently being re-planned to align with interdependencies to other Pathway to Partnership workstreams. Timing / Ongoing / Recommendations / Conclusions Status = Currently re-planning to align with Pathway to Partnership outcomes framework. |

### Changing Attitudes and Behaviour

| 2.1 KIA PUAWAI |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | All Taskforce members |
| Project Manager | Anne Riley |
| First Programme of Action reference | Not in first Programme of Action |
| Objective and actions (as per Work Programme) Kia Puawai supported in its implementation by the Taskforce. Taskforce supports initiatives such as: increasing coverage of intensive home visiting providing free Early Childhood Education for all vulnerable children aged 18 months – 3 years developing an integrated identification, assessment and referral system for young children expanding Early Years hubs and teen parent co-ordinators initiatives key workers to support at-risk families expanding Social Workers in Schools. |
| Objective deadline | Ongoing |
| Purpose This cross-agency initiative is building an early years intervention system to help ensure all children flourish in early childhood and reach their potential as young adults capable of developing healthy, respectful and violence free relationships throughout their lives. |
| Key Milestones | Date | Description of Progress |
| 2.1.2 | Progress report delivered to Ministers on results of evaluations of pilot programmes to improve outcomes for children and their families. | Nov 08 | Complete. The Chair of SDC has agreed that the November report be incorporated into the June 2009 report on options to improve access and co-ordination of early years services. See Key Milestone 2.1.4. |
| 2.1.3 | B4School check pilot in place | Aug 08 | Complete. Pilot in place. |
| 2.1.4 | Report-back to Cabinet. | June 09 | On track. |
| Progress to date (previous 3 months work) Work has continued on evaluating four pilot programmes to improve outcomes for children and their families. This work informed the June 2009 report back to Cabinet on future funding decisions. The B4School pilot being progressed by the MoH is in place. Delivery of the Check started in four DHBs (Waikato, Nelson Marlborough, MidCentral and Lakes) in June 2008. The remaining DHBs across the country started delivery of the B4School Check from September 2008. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 2.2 IMPROVING ATTACHMENT |
| --- |
| Lead agency | Ministry of Health / Auckland District Health Board |
| Contributors | MSD, ACC, MinEdu, NGOs |
| Project Manager | Pat Tuohy / Carol Stott |
| First Programme of Action reference | N/A |
| Objective and actions (as per Work Programme) Promote and improve attachment between new-born babies and parents and care-givers. Actions include: progress a pilot see how well it works report draw on key findings from parent support and development programmes already focused on supporting attachment between young children and parents and caregivers. |
| Objective deadline | July 2009 |
| Purpose Supporting the promotion of healthy secure attachment in infants is important for the development of quality relationships between infants and parents and caregivers, and for its effect on human development and wellbeing. Promotion of secure attachment can be provided through provision of information to parents, and support with strategies that enhance attachment and address any parenting concerns. Early intervention is recommended for infants of high-risk carers if developmental or behavioural problems are detected. |
| Key Milestones | Date | Description of Progress |
| 2.2.1 | Inclusion of an additional visit in the Well Child Framework for first time parents, especially fathers and male partners. | July 2009 | Project planning commenced. |
| 2.2.2 | Promotion of infant-parent attachment and assessment of parent /child relationship difficulties in revised Well Child Framework. | July 2009 | Project planning commenced. |
| 2.2.3 | Training for Well Child Providers to promote secure infant-parent attachment. | July 2009 | Project planning commenced. |
| 2.2.4 | Establishment of a pilot in the Auckland District Health Board area to prevent Shaken Baby Syndrome (head injuries to babies caused by violent shaking). | TBC | This pilot did not proceed due to issues that arose during scoping. |
| Background The pilot to prevent Shaken Baby Syndrome (key milestone 2.2.4) did not proceed as initial scoping highlighted issues with the pilot site. Timing / Ongoing / Recommendations / Conclusions Status = This Objective is likely to be the subject of a variation, to be confirmed in early 2009. |

| 2.3 CONDUCT DISORDER / SEVERE ANTI-SOCIAL BEHAVIOUR |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | MinEdu, MoH, MoJ and Police (Inter-Agency Plan partners). NGOs, OCC, and other relevant agencies will be consulted on policy development. |
| Project Manager | Saskia Patton |
| First Programme of Action reference | N/A |
| Objective and actions (as per Work Programme) Ensure comprehensive behavioural interventions for children aged 3 – 7 years with conduct problems and their families are delivered in accordance with the Inter-agency Plan by building on the specialist behaviours services already provided by the Ministry of Education. In addition, there will be the transitioning of existing services to older children and young people to evidence-based, best-practice interventions. The Taskforce supports the four action areas in the Inter-Agency Plan: leadership, co-ordination, monitoring and evaluation transition existing service provision to evidence-based, best-practice interventions establish an intensive, comprehensive behavioural service for 3 -7 year olds build a shared infrastructure for the delivery of specialist behavioural services. |
| Objective deadline | 2012 |
| Purpose Developing and delivering a suite of services for the 5% of early childhood and primary (and intermediate) school aged children who have conduct problems will reduce the prevalence of young people with these problems. Without appropriate interventions, these children are more at risk of becoming perpetrators of violence. Over time these services are anticipated to result in a subsequent reduction in cases of family violence. |
| Key Milestones | Date | Description of Progress |
| 2.3.2 | Best practice report completed | June 2008 | Some delay. Draft completed – agreement being sought on sign-off for publication |
| 2.3.3 | Agency service reviews/stocktake completed | Dec 2008 | On track |
| Background This is an inter-agency project which seeks to improve behavioural interventions for 0-17 year olds across service areas of the Ministries of Education, Health, Justice and Social Development (CYF). In particular, it will establish a comprehensive behavioural service for children aged 3-7 years (subject to further investment) and transition existing services to older children and young people to evidence-based, best-practice interventions. Progress to date (previous 3 months work) The Advisory Group on Conduct Problems (AGCP) had its first meeting on 14 November 2007 and has met seven times in 2008. Members of the AGCP have finalised the best practice report which is now due to be printed and released in early December. AGCP is currently drafting a second report which is considering programme selection for 3-7 year olds and a research design to best support the implementation of selected programme(s). Agencies are continuing to undertake a stocktake of current services that may need to be transitioned to evidence-based practice. Current ongoing work (next 3 months) AGCP will finalise the second of the best practice reports (focus on services for 3 – 7 year-olds). The next meeting of the AGCP will be held on 28 November. MSD will be developing an implementation plan to support the delivery of the Inter-agency Plan. Timeframes on delivery of new services to 3 – 7 year-olds subject to decisions on further investment. Te Roopu Kaitiaki will be drafting a report reviewing the evidence base and research requirements in considering the development of parallel Te Ao Mäori-based services. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 2.4 CURRICULUM DEVELOPMENT |
| --- |
| Lead agency | Ministry of Education |
| Contributors | MSD (MYD), MoH, TPK, MPIA, OCC, NGOs |
| Project Manager | Hayley Corbett |
| First Programme of Action reference | N/A |
| Objective and actions (as per Work Programme) Children and young people aged 5-18 years develop the knowledge and skills that they need to support good decision-making, to make healthy choices, and to seek help when they need it. Actions include: provide support to enable schools to develop their programmes within the New Zealand curriculum to suit the diverse learning needs of their community strengthen whole-school, strengths-based approaches that promote resilience and confidence in young people and those adults who support them seek opportunities to identify and respond to children who are affected by family violence. |
| Objective deadline | Ongoing |
| Purpose The purpose of education is to help children and young people reach their potential and develop the competencies they will need to live, learn, work and contribute as active members of their communities. Education contributes to the prevention and reduction of family violence in New Zealand communities by providing a safe environment that teaches and models skills to enable children and young people to manage their own well-being and to relate in healthy ways with others. It provides children and young people with the opportunity to learn skills they might not otherwise receive in the home environment. To experience the benefits of education, students must participate and be engaged with the education system. The Ministry of Education supports educators to identify students who are at risk as a result of experiencing, witnessing or engaging in family violence and to work with parents, families and whänau, and other agencies to ensure these students are appropriately supported. |
| Key Milestones | Date | Description of Progress |
| 2.4.1 | Provide support to enable schools to develop their programmes within the New Zealand curriculum (NZC) to suit the diverse learning needs of their community. Release final curriculum and supporting resources for schools to support the implementation of the curriculum Professional leaders are supported to lead curriculum development, establish the conditions for professional learning and involve families/whanau in focusing on student achievement and educational outcomes based on the NZC. | Ongoing Ongoing | On track. Te Marautanga o Aotearoa (Māori Medium curriculum) was released in September 2008. The implementation of the New Zealand Curriculum (English medium school) is ongoing through 2008. The second report on the exploratory studies of ‘early adopters’ of the New Zealand Curriculum (NZC) has been received and we continue to plan for these exemplars to be published in early 2009. |
| 2.4.2 | Strengthen the implementation of whole-school, strengths-based approaches that promote resilience and confidence in children and young people and those adults who support them. Support up to 730 teachers per year in developing effective teaching and leadership skills to support the implementation of school-wide approaches to student well being / mental health. This involves strengthening teachers’ understanding of the connections between school organisation, curriculum design and delivery and community consultation and partnerships. Identify successful professional learning approaches for teachers from the evaluation of the student wellbeing contracts and incorporate in the design and delivery of ongoing professional development contracts. | Ongoing Ongoing | On track. On 3 July 2008, initiative to prevent bullying in schools was launched. Facilitators are working with their contract schools to review progress towards meeting contract outcomes related to implementing school-wide approaches to student wellbeing and mental health. Data analysis is being used to plan for the continuation of this work in the participant schools until June 2009. On-going. The Ministry of Education, the national coordinator and facilitators are continuing to review and improve the models used in the delivery of the Student Well-Being and Mental Health contracts. |
| 2.4.3 | Seek opportunities to identify and respond to children and young people who are affected by family violence. Review the quality and accessibility of support available to educators who are concerned about children and young people affected by family violence. Develop a review of the support received by children and young people identified while at school as affected by family violence (in conjunction with obj 1.4 Child Maltreatment). | Ongoing Ongoing | On track. Modifications to the education profile and plan guidelines and templates for children in care have been made as a result of the trial currently underway within the Auckland District Health Board. Work is about to commence on implementing the child maltreatment prevention project plan. |
| Background In 2002, the Ministry of Education’s Curriculum Stocktake Report identified that, while many students were achieving at world-class levels, there are wide disparities in outcomes for diverse students. Progress to date (previous 3 months work) 2.4.1 The New Zealand Curriculum The second report on the exploratory studies of ‘early adopters’ of the New Zealand Curriculum (NZC) has been received and we continue to plan for these exemplars to be published in early 2009, with the first articles in schools at the beginning of February. The document for Te Marautanga o Aotearoa (Mäori Medium curriculum) was released in September 2008. Implementation will commence in January 2009 through until December 2010. Implementation support includes development of resources and information to assist schools to design their own school-based curriculum. 2.4.2 Whole-school, strengths-based approaches that promote resilience and confidence in children and young people On 3 July 2008, the Ministry of Education launched a four pronged approach to support school staff, parents and students in preventing bullying in schools. Facilitators are working with their contract schools to review progress towards meeting contract outcomes related to implementing school-wide approaches to student wellbeing and mental health. Data is analysis is being used to plan for the continuation of this work in the participant schools until June 2009. The Ministry, the national coordinator and facilitators are continuing to review and improve the models used in the delivery of the Student Well-Being and Mental Health contracts and to integrate the learning in ongoing professional development contracts. 2.4.3 Identifying and referring children affected by family violence to appropriate services Modifications to the education profile and plan guidelines and template for children in care have been made as a result of the trial currently underway within the Auckland District Health Board. Current ongoing work (next 3 months) 2.4.1 The New Zealand Curriculum The second report on the exploratory studies of ‘early adopters’ of the New Zealand Curriculum (NZC) has been received and we continue to plan for these exemplars to be published in early 2009, with the first articles in schools at the beginning of February. Work will continue in preparation for the implementation of Te Marautanga o Aotearoa from January 2009 through until December 2010. Work continues on the Principals’ Leadership Strategy, which is planned for release in February 2009. This strategy will provide a three to five year plan outlining how the Government intends to work with the sector to achieve the goal of strong professional leadership in every New Zealand school by 2012. 2.4.2 Whole-school, strengths-based approaches that promote resilience and confidence in children and young people Work continues on the development of a resource called Making a Difference which will show how eight New Zealand schools are engaging students in positive learning and achievement. We will continue to update and promote the supporting positive behaviours website. Facilitators will continue to work with their contract schools to review progress towards meeting contract outcomes related to implementing school-wide approaches to student wellbeing and mental health. Data is analysis is being used to plan for the continuation of this work in the participant schools until June 2009. The Ministry of Education, the national coordinator and facilitators are continuing to review and improve the models used in the delivery of the Student Well-Being and Mental Health contracts and to integrate the learning in ongoing professional development contracts. 2.4.3 Identifying and referring children affected by family violence The trial of the education profile and plan will be extended to Counties Manakau, Wairarapa, Horowhenua and Lakes District. The trial is about to begin in Counties Manukau and work on extending it to Horowhenua/Wairarapa and Lakes District is in the planning stage. Work will continue on the implementation of the project plan for the review of the education sector’s contribution to child maltreatment prevention, as part of Objective 1.4. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 2.5 VIOLENCE IN THE MEDIA |
| --- |
| Lead agency | Families Commission |
| Contributors | NGOs |
| Project Manager | Radha Balakrishnan |
| First Programme of Action reference | Action 23 |
| Objective and actions (as per Work Programme) Create awareness of impact of violence in the media on children aged between 6 to 11 years. Actions include: scope an evidence-based public education and awareness programme aimed at parents scope financial implications develop an implementation plan. |
| Objective deadline | February 2009 |
| Purpose To scope a public education and awareness programme around violence in the media (its risks and impact) with an initial focus on parents of 6-11 year olds. |
| Key Milestones | Date | Description of Progress |
| 2.5.2 | Develop plan | Oct 2008 | Planning work commenced |
| 2.5.3 | Draft Report circulated for comment | Dec 2008 | Not commenced |
| 2.5.4 | Report to the Taskforce | Feb 2009 | Not commenced |
| Background Violence in the media and its impact on society generally was raised at the meeting with the Family Violence Ministerial Team and with members of the Multi-Party Working Group on Family Violence, when the Taskforce’s First Report was presented in mid 2007. The first programme of action included an action to review how violence is portrayed in the media and in particular the 2004 Report on TV Violence in New Zealand, and advise on implications for the next Programme of Action. The Families Commission agreed to lead this work. The Taskforce supported raising awareness of the impact of violence within the media on children and young people. The 2004 report identified middle childhood (between 6-11 years) as a vulnerable group and it was agreed that this group should be the initial focus of any public education work. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 2.6 CAMPAIGN FOR ACTION ON FAMILY VIOLENCE |
| --- |
| Lead agency | MSD / Families Commission |
| Contributors | NGOs |
| Project Manager | Gael Surgenor |
| First Programme of Action reference | Actions 29-39 |
| Objective and actions (as per Work Programme) Continue the Campaign for Action on Family Violence through: an advertising campaign resource development and distribution Community Action Fund projects. |
| Objective deadline | 30 June 2009 (Ongoing to 2010) |
| Purpose This is a community-based social marketing campaign which aims to influence the behaviour of target audiences, including perpetrators of family violence and their influencers. The programme is based on research into attitudes and towards family violence and motivators and barriers to behaviour change. |
| Key Milestones | Date | Description of Progress |
| 2.6.5 | Administering two further rounds of the Community Action Fund to support local projects to support change at a local level. Mid 2008 and early 2009. | Nov 2008 | Third round complete. A fourth round will open for applications in November 2008 and will close March 2009. |
| 2.6.6 | Continue to support the messages of the television campaign during 2008/09 using the website, the 0800 information line and print resources. | June 2009 | The 0800 telephone line continues to provide information and support to an average 600 callers per month. The television advertisements are having a sustained impact on website visit numbers and with about 7,000 visits per month from August through to October. New resources will be developed depending on the development of the next phase of the campaign which is currently being scoped. |
| 2.6.7 | Continue a television advertising campaign addressing attitudes to family violence and intimate partners violence during 2008/09 – five weeks of advertising to be run. | 12 June 2009 | The “It’s not OK” ads will resume on TV in the week commencing 14 December, traditionally a stressful time for families in the run up to Christmas. The “It’s not OK” ads will air in the week beginning 4 January and the Stories of Positive change ads will feature in the week beginning 25 January, |
| 2.6.8 | Continue to build on the media advocacy work with the national news media to promote more responsible coverage of stories of family violence and provide training and support to enable community spokespeople to engage effectively with local media | 12 June 2009 | Successful two week media campaign by the Wanganui Chronicle, working with the campaign team. Media training workshop delivered to Police Family Violence coordinators in Auckland, 23 October - Excellent feedback. Worked with community spokespeople to get stories around the Police Crime Statistics in local newspapers. |
| 2.6.9 | Continue to identify and encourage campaign ‘champions’ and spokespeople, to develop partnerships in business, sport and youth related organisations and to continue to seek opportunities for promotion within popular culture. | 12 June 2009 | New approaches from sporting organisations wanting to work with the campaign – from Touch Rugby New Zealand and from the Super 14 rugby franchise, The Hurricanes. Hamilton City Council It’s not OK campaign to run throughout the month of December 2008, featuring billboards, coasters, local media promotion. Working with students from Upper Hutt, Heretaunga, Taita and Wainuiomata Colleges on a marae-based leadership initiative addressing issues of violence in the home. |
| 2.6.10 | Continue to measure the level of public awareness of the key messages of the Changing Attitudes and Behaviours Campaign | 30 June 2009 | The third reach and retention tracking survey conducted in September 2008 shows very positive trends for awareness of the Campaign. Face-to-Face survey: The data collection for the attitudes towards family violence survey is now complete. |
| Background The Campaign for Action on Family Violence (the campaign) is a four year campaign that calls on everyone to help put an end to family violence in New Zealand. The national campaign was launched with TV advertisements in September 2007. The campaign message “Family violence – It’s not OK” has struck a chord with New Zealanders and has quickly become part of the kiwi vernacular. The campaign is supported by a website, an 0800 Information Line and a Community Action Fund that provides financial support for community-led activities. Progress to date (previous 3 months work) Resources continue to be distributed and the 0800 telephone line continues to provide information and support. The campaign’s media advocacy work is continuing. Advertisements from the second phase of the campaign screened for one week, from 7 September. Work is beginning on 35 successful projects approved in the third round of the Community Action Fund, announced in August. Current ongoing work (next 3 months) Additional weeks of the phase one and phase two adverts are going to air in December and January 2009. Results of a nationwide face to face survey that will specifically explore attitudes about violence towards women, inter-partner violence, and child abuse are being analysed and will be available to Taskforce in December 2008. A community study is underway that will provide an in-depth analysis of the impact of the campaign. Timing / Ongoing / Recommendations / Conclusions Status = on track. |

| 2.7 FAMILY VIOLENCE DEATH REVIEW PROJECT |
| --- |
| Lead agency | Ministry of Health |
| Contributors | MSD, MoJ, Police, NGOs |
| Project Manager | (FVDRC Secretariat: Aphra Green) |
| First Programme of Action reference | Action 42 |
| Objective and actions (as per Work Programme) To establish the Family Violence Death Review Committee (FVDRC). |
| Objective deadline | 31 June 2008 - Complete |
| Purpose The Family Violence Death Review Committee is being established to understand why family violence deaths occur and to enable changes to systems and practices that may contribute to the prevention of future deaths. |
| Key Milestones | Date | Description of Progress |
| 2.7.7 | Induction and first meeting of the Committee | By 30 Oct 2008 | Completed |
| Progress to date (previous 3 months work) The Ministry of Health held an induction day for the FVDRC on 1 October 2008, and the FVDRC held its first meeting on 2 October 2008. Current ongoing work (next 3 months) The FVDRC is progressing work on the establishment issues it is required to address in its first year of operation (as outlined in its Terms of Reference). Timing / Ongoing / Recommendations / Conclusions Status = Completed. This objective will be deleted from future Monitoring Reports. |

### Ensuring Safety and Accountability

| 3.1 FAMILY VIOLENCE COURTS |
| --- |
| Lead agency | Judiciary / Ministry of Justice |
| Contributors | Police, NGOs |
| Taskforce Liaison | Justine Cornwall |
| Project Manager | Karyn McLean/Dominic Lepa |
| First Programme of Action reference | Action 56 |
| Objective and actions (as per Work Programme) Two new Family Violence Courts established. Actions include: project planning identification of locations stakeholder consultation implementation. |
| Objective deadline | A variation was sought to extend this deadline to April 2009 |
| Purpose To ensure all parties are prepared ahead of the implementation to support new Family Violence Courts being established. |
| Key Milestones | Date | Description of Progress |
| 3.1.3 | Stakeholder consultation | Sept 2008 | Date changed, reflected in Variation. A variation has been submitted to allow for the new timeframe for the Whangarei Family Violence Court opening in April 2009. The Palmerston North court is now operational. |
| 3.1.4 | Communications strategy | Early 2009 | A variation was sought in July 2008 to delay the communications strategy to allow for the implementation of new courts. |
| 3.1.5 | Implementation of two new Family Violence Courts | April 2009 | The Palmerston North Family Violence Court became operational on 12 September 2008. A Variation was sought in July 2008 regarding the opening of the Whangarei Court moving to April 2009 and Palmerston North to September 2008. |
| Progress to date (previous 3 months work) The Chief District Court Judge has confirmed Palmerston North and Whangarei as the locations for the new Family Violence Courts. Palmerston North was implemented in September 2008 with Whangarei to follow, likely to be in April 2009. Staff/stakeholder training and consultation has been completed for the Palmerston North Family Violence Court. Current ongoing work (next 3 months) Planning for the opening of the Whangarei Family Violence Court in early 2009 continues, and a training date has been confirmed for February 2009. Timing / Ongoing / Recommendations / Conclusions Status = The Palmerston North Family Violence Court is now operational. The Whangarei Family Violence Court is likely to be operational by April 2009. |

| 3.3 SOCIAL SERVICES SUPPORTING COURTS |
| --- |
| Lead agency | Ministry of Social Development / Ministry of Justice |
| Contributors | Police, MWA, NGOs, ACC |
| Project Manager | Ann Riley / Justine Cornwall |
| First Programme of Action reference | Action 52 |
| Objective and actions (as per Work Programme) A social services system modelled around family violence courts to support the courts by linking services to ensure victims and observers are kept safe, perpetrators are kept accountable and responsible, and families are assisted with their recovery needs. Actions include: introduction of Independent Victim Advocate / support person role in all Family Violence Courts introduce specialist enhanced case management staff in all Family Violence Courts referral and funding for non-mandated stopping violence programme providers for offenders. |
| Objective deadline | April 2009 |
| Purpose A social services system modelled around family violence courts to support the courts by linking services to ensure victims and observers are kept safe, perpetrators are kept accountable and responsible, and families are assisted with their recovery needs. |
| Key Milestones | Date | Description of Progress |
| 3.3.2 | Scoping and developing Family Violence Court Community Service (FVCCS), formerly called Independent Victim Advocate (IVA). | Dec 2008 | Scoping and development of the FVCCS has been underway since July. Consultation with NGOs, Judiciary, and key stakeholders will be completed by the end of November with a view to signing-off the role and framework for a collaboration protocol, by the beginning of December (milestone date adapted to reflect this date). |
| 3.3.3 | Introduce specialist enhanced case management staff in all Family Violence Courts (FVCs) | TBC | There has been a delay in this work. MoJ is currently assessing other funding streams to fund this initiative. This work is ongoing. No completion date confirmed as yet. |
| 3.3.5 | Consultation with other agencies and non-government organisations on the development of the role of the FVCCS | Aug/Nov 2008 | The Ministry of Justice ran two workshops, in August and November, with NGOs to discuss the FVCCS role description. NGOs have also worked with MoJ, the Chief District Court Ju8dge, Police and MSD in drafting a framework for a collaboration protocol. The protocol will outline the roles and responsibilities of the FVCCS, Police Prosecutor, and Victim Advisor in the provision of victim information to the Court. This framework will be developed over November/December 2008 |
| 3.3.6 | The FVCCS will be rolled out in FVCs. | From July 2009 | MSD will manage the selection process for the organisations to tender for the FVCCS. It is expected that the contracts for organisations to provide the FVCCS will be signed off in early 2009, and FVCCS recruited and trained by mid-2009. The milestone date has been changed from April 2009 to reflect the delay due to the development of a framework for a collaboration protocol as outlined in 3.3.5. |
| Background A variation to this objective was approved by the Chair of the Taskforce on 4 April 2008. The variation was sought because the previous deliverables and milestones did not align with the direction the Chief District Court Judge has set for the Family Violence Courts (FVCs). The Government has announced that it will move towards fully funding actions 1 and 3 of this objective from 2008/2009 (Introduction of Independent Victim Advocate/support person role in all FVCs, and referral and funding for non-mandated stopping violence programme providers for offenders). Progress to date (previous 3 months work) The Ministry of Justice, in liaison with MSD, Police and NGOs, began work on developing the role of a Family Violence Court Community Services (FVCCS), formerly called independent victim advocate in July. This role will provide support and assistance to victims of domestic violence in the FVCs. Consultation with other agencies, NGOs, and the Judiciary took place from August to November. In mid-November, discussions took place with NGOs, Police, MSD and key stakeholders to finalise the role description and develop a framework for a protocol. The protocol will outline the roles and responsibilities of the FVCCS, Police Prosecutor, and Victim Advisor in the provision of victim information to the Court. The role description for the FVCCS and framework for the protocol will be completed and signed off by early December 2008. Current ongoing work (next 3 months) The management of the selection process, including preparing documentation, for the provider(s) that will recruit and train the 8 FVCCS. A framework for a collaboration protocol is to be developed and will contain information about the overarching principles, goals and objectives for getting information about victims through to the court. This protocol will also determine how information is given to the Judge. The framework protocol is to be developed to go alongside the role description. Recruiting for the Independent Advocate role has been delayed until the framework has been developed and agreed to. Timing / Ongoing / Recommendations / Conclusions Status = slight delay due to ongoing consultation with key stakeholders on the draft role description for the FVCCS and framework for the protocol. |

### Effective Support Services

| 4.1 MAORI SERVICE WORKFORCE DEVELOPMENT |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | TPK, NGOs, MinEdu |
| Project Manager | Ann Dysart |
| First Programme of Action reference | Action 7 |
| Objective and actions (as per Work Programme) Maori Service Workforce Development. Actions include: 60 Maori trained to work with the Mauriora framework. Ongoing support of trained practitioners. |
| Objective deadline | June 2009 |
| Purpose This proposal will allow for continued investment in the training and support of practitioners who work with Maori whanau/communities where there is violence. |
| Key Milestones | Date | Description of Progress |
| 4.1.6 | Ongoing assessment and further training, including assisting Mauri Ora practitioners to meet annual licensing and supervision requirements (follows 4.1.3). | Dec 2008 | A further range of training is currently being contracted to maintain levels of supervision and facilitation training. |
| 4.1.7 | Training modules completed (follows 4.1.4). | Nov 2008 | On track |
| 4.1.8 | Development of supervision systems (follows 4.1.5). | Dec 2008 | Underway, training begun. |
| 4.1.9 | Cross Credit Whanau Ora Training to a Diploma in Social Work. | June 2008 | Discussions toward this accreditation are underway. |
| 4.2.0 | Development of a new Leaders Strategy aimed at programmes for rangatahi. | Dec 2008 | Preparing submission for approval of the programme by Te Korowai Aroha O Aotearoa’s governing body. |
| Progress to date (previous 3 months work) Negotiations are complete for the next round of training. New resources developed, including DVD of Maori leaders speaking on family violence. To be distributed. Current ongoing work (next 3 months) The Provider is continuing to work with Te Kaiawhina Ahumahi to progress the recognition of learning provided. It is envisaged that students will eventually be able to cross credit Mauri Ora Training to a Diploma of Social Work. Timing / Ongoing / Recommendations / Conclusions Status = On track. |

| 4.2 PACIFIC SERVICE WORKFORCE DEVELOPMENT |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | MPIA, NGOs, MinEdu |
| Project Manager | Richard Joblin |
| First Programme of Action reference | Action 7 |
| Objective and actions (as per Work Programme) Variation submitted to adjust Objective, awaiting approval. Pacific Service Workforce Development. Actions include: preparation of a project plan to guide workforce training and development in family violence services for Pacific families. |
| Objective deadline | July 2008 (Variation submitted to change deadline, awaiting approval) |
| Purpose This work plans to increase the quality and diversity of services working to eliminate family violence in the Pacific communities. This will include identifying the capacity and capability of this workforce and the avenues needed to further build and support Pacific People in working to stop family violence in Pacific Families. |
| Key Milestones | Date | Description of Progress |
| 4.2.1 | Project plan developed under Pathway to Partnership to address building provider workforce capability and capacity. This will include the development of the Pacific workforce. | TBC | This work is now incorporated under the Pathway to Partnership plan. On 8 August the Minister for Social Development considered a report on strengthening collaborative action under Pathway to Partnership. The Minister agreed to a longer-term investment approach to provider capability building being developed by March 2009 and that contracts for provider development funding will be reviewed for consistency with this approach as they come up for renewal. |
| Background This work is now incorporated within the Pathway to Partnership (P2P) plan. On 12 February 2008, the Government announced an additional funding package for the P2P plan worth $446 million, to be phased in over the next four years. Pacific service workforce development is incorporated under the work-stream to address providers’ ability to build workforce capability and capacity. A steering group for the P2P plan has overseen the development of P2P over the last year. A representative from the PAG is on this steering group. Current ongoing work (next 3 months) The P2P workforce and provider development project plan is currently being clarified. A variation to this objective is to be approved. Timing / Ongoing / Recommendations / Conclusions Status = delayed. Variation to be approved. |

| 4.3 SERVICE DEMAND DATA |
| --- |
| Lead agency | Ministry of Social Development |
| Contributors | NGOs, MoJ, MoH, ACC, Police |
| Project Manager | Dorothy Adams |
| First Programme of Action reference | N/A |
| Objective and actions (as per Work Programme) Monitor increases in demand for family violence services resulting from the Campaign to create sustainable responses to increased demand. Actions include: develop monitoring framework create a system response mechanism. |
| Objective deadline | October 2008 |
| Purpose To identify changes in service demand associated with the roll out of the Campaign for Action on Family Violence. |
| Key Milestones | Date | Description of Progress |
| 4.3.2 | Repeat quantitative measures as above. | June 2008 | Completed |
| 4.3.3 | Triangulation of quantitative data from qualitative field work. | October 2008 | Completed |
| Background Monitoring systems were developed to measure the initial impact in service demand associated with the Campaign for Action on Family Violence. These monitoring systems included data from the 0800 number, CYF and Police. The quantitative measures included in these monitors will be repeated. Qualitative data collected from the NGO sector in selected communities will compliment the quantitative monitors. The qualitative data collection will focus on the contribution that the Campaign for Action on Family Violence has had on any change in service demand experienced by the NGO sector since the commencement of the Campaign. Progress to date (previous 3 months work) Qualitative and quantitative data has been analysed to provide information on changes in service demand associated with the roll out of the Campaign for Action on Family Violence. A report on service demand trends has been drafted. Current ongoing work (next 3 months) Report will be circulated to key service lines. Timing / Ongoing / Recommendations / Conclusions Status = completed. This Objective will be deleted from future Monitoring Reports. |

| 4.4a TRAINING OUR STAFF NB: there are only some agencies for whom it is relevant to complete a training project plan. |
| --- |
| Lead agency | ACC |
| Contributors | All agencies |
| Project Manager | Refer to objective 1.5 |
| First Programme of Action reference | Refer to objective 1.5 |
| Objective and actions (as per Work Programme) Taskforce agencies at the point of contact with communities are enabled to respond to victims, observers and perpetrators effectively and safely. Actions include: assess available training options develop training that meets organisational needs plan and implement. |
| Objective deadline | Refer to objective 1.5 |
| Purpose To ensure frontline ACC staff are equipped with the skills and tools to respond to victims, spectators or perpetrators of Family Violence whether they be staff, clients of ACC or members of the communities in which ACC staff belong. |
| Key Milestones | Date | Description of Progress |
| 4.4.1 | Frontline staff skills developed | 31 Mar 2009 | Work continues to investigate an appropriate training provider. |
| 4.4.3 | Training plan developed for all staff | 31 Mar 2009 | Modular based training identified as best solution is being investigated following feedback from staff stakeholders. |
| This objective relates directly to Objective 1.5 – Family Violence Free Workplaces (FVFW). Ongoing work Work continuing to identify training options and best fit approach – limited success on finding successful programme to date – 3 options trialled and considered, now looking at international research and progress in this space. Implementation window for training expected to be May/June 2009 following completion of identified and agreed training modules. |

# First Programme of Action update

Summary Analysis

The Taskforce for Action on Violence within Families’ (the Taskforce) first programme of action initially consisted of 76 actions which were developed from the Taskforce’s First Report. This was consolidated to 53 actions.

Of these 53 actions, 29 are complete. Work has commenced on another 15 actions and these are now either ongoing, business as usual, or are annual events. The remaining nine actions have been subsumed into the Ongoing Programme of Action and, along with other ongoing work, are now reported on and monitored through the regular Monitoring Reports provided to every Taskforce meeting.

Key to ‘Status’

Complete = Action complete. May have informed development of work in Ongoing Programme of Action.

OPOA = Work in these actions has been incorporated into the Ongoing Programme of Action, refer to objective number.

Ongoing or Annual = Initial stage complete, currently Ongoing or business as usual. Some are Annual occurrences.

| # | Action | Agency | Information | OPOA # | Status |
| --- | --- | --- | --- | --- | --- |
| Leadership |
| 1 | Developing the next Programme of Action (POA) | All TF | OPOA released Feb 2008 | 1.1 | Complete |
| 3 | Successful implementation of POA | All TF | Incorporated into OPOA | 1.1 & 1.1a | Complete, ongoing reporting |
| 7 | Drawing on Maori and Pacific advisory groups | MSD | Representatives on TF, ongoing MRG and PAG meetings advise the TF. | Led to 1.2, 1.3, 1.6, 1.9, 1.10, 2.4, 4.1, 4.2 | OPOA |
| 8 | Incorporating migrant and refugee perspectives | MSD | Informed OPOA | 1.11 | OPOA |
| 9 | Aligning business planning to reflect Taskforce vision | Sec. | Next round of SOIs (2008/2009) to be monitored. | 1.1 | Annual Ongoing |
| 12 | Maintain overview of government strategies to ensure goals and activities are complementary with our work | All TF | Business as usual. Secretariat watching brief to ensure TF are aware of all relevant govt strategies. All TF agencies info share on new strategies, and maintain overview of relevant govt strategies. | 2.1 2.3 | Complete to date, Ongoing |
| 13 | Family Violence research strategy | FC | Initial report provided Oct 2007, gaps analysis and other areas where work needed. Discussion doc sent early 2008 on topic priority – ongoing work being done through 2008 in consultation with other research agendas. | Informs 1.9-1.12 Led to 1.13 NGO data | Ongoing |
| 14 | Monitoring the level of family violence in NZ | FC | Refer to Research Strategy | Led to 1.13 & 1.7 | Ongoing |
| 15 | Horizontal learning | MSD | Incorporated into OPOA, Ongoing | 1.7 | OPOA |
| 19 | Evaluate the first POA | MSD | Workshop April 2007. Remaining ongoing actions from POA will be monitored through regular Monitoring Reports. | 1.1a | Complete |
| 21 | Families Commission research programme | FC | 3 year research complete 21a Improving Family Violence surveillance data 21b Elder abuse and neglect research – released Feb 2008 | Informed OPOA | Complete |
| 22 | ACC research programme | ACC | 22a Sensitive claims 22b Effectiveness evaluation 22c Whanau Ora research - ongoing 22d Evidence based guidelines. |  | Complete 22c only is Ongoing |
| Changing attitudes and behaviour |
| 23 | Review violence in media | FC | Informed development of 2.5 | 2.5 | Complete |
| 29 | Using research to guide Campaign strategy | MSD | The Campaign continues to 2010, with further development being guided by research and evaluation | 2.6 | OPOA |
| 35 | Campaign strategy | MSD / FC | As above | 2.6 | OPOA |
| 36 | Mass media campaign | MSD / FC | Phase one started Sept 2007, Phase two started Feb 2008. Both phase adverts to be repeated in 2008 and early 2009. | 2.6 | OPOA |
| 37 | Nurturing leaders… | MSD | Business as usual. Identified (and funded) through the Community Action Fund. | 2.6 | OPOA |
| 38 | Partnerships with NGOs | MSD/ FC | NGO groups are contracted to be funded for local initiatives. | P2P | Ongoing |
| 39 | Community Action Fund | MSD | 97 initiatives funded in first three rounds. Fourth round open. | 2.6 | OPOA |
| 40 | Building knowledge – media advocacy etc | MSD/ FC | 40a media advocacy - FACS 40b FV awareness training – also led to 1.5 40c Toolkit re-released 40d White Ribbon day | 2.6 2.6 1.5 2.6 - | OPOA Ongoing Ongoing Complete Annual |
| 4142 | Family violence death reviews | MoH | Family Violence Death Review Committee first meeting Oct 2008. | 2.7 | OPOA |
| Ensuring Safety and Accountability |
| 43 | Sharing information in a way that promotes safety and wellbeing | Previously MoJ | The Law Commission and the Privacy Commissioner are exploring approaches to the issue of government information sharing. The Law Commission will release an issues paper in the first half of 2009. |  | Initial work complete, Ongoing |
| 44 | Family Violence victims know what support and services are available | MoJ | New comms material developed and distributed at end 2007/early 2008. Available on Family Court website. |  | Complete |
| 45 | Maximising safety factors when managing court rosters | MoJ | Security policy complete, and was sent to all courts as a circular on 1 April 2008. |  | Complete |
| 46 | Increased thresholds for legal aid eligibility | MoJ | Thresholds increased. Legal aid regulations in force from Mar 2007. |  | Complete |
| 47 | Begin a review of legal aid remuneration rates | LSA | Review complete. Changes recommended. Budget 2008 approves 10% increase for 2008/2009. |  | Complete |
| 48 | Improving information courts provide about legal aid | MoJ | Info updated and provided in court info packs and in DV packs, Dec 2007. Court staff also provided with info for public enquiries. |  | Complete |
| 49 | Testing fixed fees for legal aid | MoJ / LSA | Testing complete. Three things were tested – fixed fees, the removal of prior approval requirements for standard family grants and proforma invoices. The removal of prior approval was implemented in October 2008 alongside revised family steps and disbursements. Fixed fees and proforma invoices are on hold. |  | Complete |
| 50 | Building safe and effective programmes for couples and families | MSD / MoJ | Service specifications set. MoJ in consultation with NZ Assoc of Counsellors, timeframes to be set. |  | Ongoing |
| 51 | Build capacity of interpreters in Courts | MSD / MoJ | More interpreters available in courts. Business as usual to continue building availability. |  | Complete |
| 52 | Investigate introduction of advocates in courts | MWA / MoJ / MSD | Investigation completed by MWA. Refer OPOA Objective 3.3 for further work. | 3.3 | Complete |
| 53 | Enhanced ability for courts to contact victims directly | MoJ / Police | Already possible, MoJ and Police will continue improving standardised process for CSV1 compliance and referral. |  | Complete |
| 54 | Review purchasing plans for programmes | MoJ | 2008 tender round complete. |  | Complete |
| 55 | Improve process for prosecutions for non-attendance at programmes | MoJ / Police | Memorandum of understanding between MoJ and Police for the transfer of prosecutions to Police signed. Transfer completed in June 2008. |  | Complete |
| 56 | Establish four additional Family Violence Courts | Judiciary / MoJ | Four established. Another established in Palmerston North in Sept 2008, one more due to open in early 2009 in Whangarei. | 3.1 | Complete |
| 57 | Family Violence Courts Evaluation | MoJ | Waitakere and Manukau evaluation complete. Released August 2008. | 3.2 | Complete |
| 58 | Forum to identify best practice for information exchange | MoJ | Held March 2007. Best practice ideas generated informed development of guidelines by agencies. |  | Complete |
| 60 | Enforcement of protection orders (POs) – police training, performance measures and policies | Police | Initiatives on addressing family violence “big picture” (which include PO’s) complete. Ongoing work continuing. 60a Training 60b Performance measures 60c National investigation and prosecution policies. Protection Orders research response also monitors this work, next report due to Minister end Sept 2008. | Many & 4.4 | Complete. Ongoing work |
| 61 | Support and training for lawyers working in family violence-related areas | Judge Boshier | Workshops for FC lawyers done in 2007, Law Soc also produced a resource booklet. Similar training is likely to be ongoing. |  | Complete |
| 62 | Define options to improve information sharing between agencies and the Courts | MoJ | Information sharing already occurs between the Family Court and the District Court. Background papers and process maps have been drafted for internal review. Consultation with external stakeholders is planned for Nov/Dec 08. |  | First stage complete Ongoing 2008 & beyond |
| 63 | Simplify application forms for Protection orders | MoJ | The explanatory leaflet has been completed and has been placed on the Family Court’s Website. Copies are also available through Courts. Simplifying the protection order forms is ongoing and will be undertaken as part of the review of the Domestic Violence Act’s Rules and Regulations. |  | Form complete. Simplifying forms is ongoing. |
| 64 | Improve the use of security resources available to courts | MoJ | The Ministry of Justice is currently preparing another new initiative bid for additional resources. It will also be reviewing how it uses existing resources to ensure it is getting best value for money. |  | First stage complete, Ongoing 2008 & beyond |
| 65 | Consider an office to provide DVA-specific legal services | LSA MoJ | Currently developing objective and milestones as part of business planning. |  | Ongoing 2008 & beyond |
| 66 | Determine level of attendance and performance of perpetrators at programmes | MoJ | A report into the findings was completed on 30 September 2008 The report summarised data collected from a sample of Family Courts and provides an indication of attendance of respondents at stopping violence programmes. |  | Complete |
| 67 | Develop options to ensure perpetrators attend and complete programmes | MoJ | Further phase of Action 66. Options are currently being considered |  | Ongoing 2007/2008 & beyond |
| 68 | Information for perpetrators on programmes | Police | Information distributed |  | Complete |
| 70 | Ensure the range of programmes matches the profiles of perpetrators | Corrections / MoJ | Options to potentially address gaps in programmes for prisoners with DV-related offences formulated. Currently analysing these options. |  | Ongoing 2007/2008 & beyond |
| 71 | Local Case Collaboration (FVIARS) | CYF / Police | FVIARS phase one complete and evaluation complete, second phase - nationwide roll-out underway. | Informs 3.3 | Phase one complete, Ongoing 2008 & beyond |
| Effective Support Services |
| 72 | Govt investing $9 million over the next four years | MSD | 2006/2007 contracts complete and funding took place. Continued funding of contracts from baseline. |  | Dev. Complete Ongoing to 09/10 |
| 73 | Develop new funding model | MSD | Pathway to Partnership (P2P) developed and ongoing. $20.4 million allocated in 2007. $446 million announced 12 Feb 2008 to fund essential NGO child and family services. | 2.1 | Complete OPOA |
| 74 | Cost family violence and family support services | MSD | Costing tool developed as part of P2P as above. | 2.1 | Complete |
| 75 | Build on existing workforce and organisational development initiatives | MSD | P2P Funding announced on 12 Feb 2008 to build a sustainable NGO sector. Ongoing. | 2.1 | Dev. complete. Ongoing 2008 & beyond |
| 76 | Continue to promote the use of integrated contracts | MSD | Funding for Outcomes developed and implemented. These contracts now part of FACS core business under the Integrated Contracts team. |  | Complete |

# How this report works

The Ongoing Programme of Action Monitoring Report is organised into two sections:

- A summary section – which provides an overview of the key highlights over the previous two months, and identifies the hotspots that need to be monitored closely over the upcoming two months to ensure objectives remain on track.

- A monitoring report section – which includes two key parts:

    - Summary information from the project plans for each objective.

    - A summary of the progress of each objective over the last three months and an overview of the work that is expected to occur over the next three months.

The Taskforce’s planning and reporting hierarchy consists of the following:

- Objectives – specific work that has been signalled in the programme of action

- Actions –  specific work signalled in the programme of action, as part of an objective and/or in the Taskforce’s work programme which sits beneath the programme of action

- Key Milestones – taken from individual agency project plans.

We have also introduced a formal variation process, which aims to:

- maintain the integrity of the Taskforce’s programme of action

- ensure there is transparent communication within the Taskforce about changes to objectives and/or actions

- ensure the objective and actions remain relevant to the Taskforce and its priorities.

A formal variation is required when a Taskforce agency wants to change an objective, action or both. Formal variations are not currently required to change key milestones. However, any key milestone changes must be provided to the Secretariat so that a log can be kept and changes can be tracked over time.

The variation template is attached to this report. An electronic copy can be obtained from the Taskforce Secretariat.

Reporting frequency

Ongoing Programme of Action Monitoring Reports will be produced for each Taskforce meeting. If a Taskforce meeting is changed to a workshop then a report will still be produced but will be circulated in hard copy only.

Other information

The information in the monitoring report centres on the key milestone information provided by each Taskforce agency.

To ensure the monitoring report remains current, as each milestone is reported complete it will be dropped from the report. The Secretariat will keep a record of all milestones so that this information can be used at a later date, if necessary.

| To | The Taskforce for Action on Family Violence | Date |  |
| --- | --- | --- | --- |
| From |  |
| Security Level | In Confidence |
| request to amend Work Programme Objective or Action |
| Action | For your approval |

I am seeking your approval to change an objective or action from the work programme for the Taskforce for Action on Violence within Families.

Current Deliverable:

[Insert Project / Work Programme Objective and/or Action]

[Insert current milestone/s (from project plan template)]

Changed to:

[Insert Project / Work Programme Objective and/or Action]

[Insert new milestone/s (also complete new project plan template)]

Reasons for a Variation Request

A variation to this deliverable has become necessary as:

- [please insert reason/s for variation]

Consultation

In seeking a variation to this deliverable, I have consulted with the following people:

| Name | Position and organisation |
| --- | --- |

Impact

The impacts in agreeing to this change are:

- [add details of any impact such as reporting to Cabinet, other key project timeframes, budget initiatives, reputation, legislation.]

The impacts in not agreeing to this change are:

- [add details of any impact such as reporting to Cabinet, other key project timeframes, budget initiatives, reputation, legislation.]

Recommendation

It is recommended that you:

- agree to a variation to an objective or action found in the Taskforce’s work programme

[Insert Project / Work Programme Objective and/or Action]

[Insert new milestone/s (also complete new project template)]

Approve / Decline

| Xxxxx (Taskforce representative) |  |  |
| --- | --- | --- |
| XXXXX (Taskforce agency) |  | Date |

| Peter Hughes |  |  |
| --- | --- | --- |
| Chair |  | Date |
| Approved ( Not Approved ( |

# Footnotes

Note that the Inter-agency Plan references establishing an intensive, comprehensive behavioural service for 3 -7 year olds, the ongoing work programme discusses delivery to 3-8 year olds.